## Risk Scoring Guide
BUILDING AND INFRASTRUCTURE CONSTRUCTION - RISK SCORING METHODOLOGY
PROBABILITY SCALE (1-5):
1 - Very Low (0-10%): Highly unlikely to occur
2 - Low (11-30%): Unlikely but possible
3 - Medium (31-50%): Moderate chance of occurrence
4 - High (51-80%): Likely to occur
5 - Very High (81-100%): Almost certain to occur
IMPACT SCALE (1-5):
1 - Minimal: <$50K impact, minor schedule delay
2 - Low: $50K-$200K impact, 1-2 week delay
3 - Medium: $200K-$500K impact, 1-4 week delay
4 - High: $500K-$1M impact, 1-2 month delay
5 - Critical: >$1M impact, >2 month delay
RISK SCORE CALCULATION (Probability × Impact):
1-3: Very Low Risk (Accept)
4-7: Low Risk (Accept and monitor)
8-14: Medium Risk (Monitor and manage)
15-19: High Risk (Detailed mitigation plan)
20-25: Critical Risk (Immediate action required)
RISK RESPONSE STRATEGIES:
• Accept: Monitor with no active response
• Mitigate: Reduce probability or impact
• Transfer: Share risk with third party
• Avoid: Eliminate risk through scope change
• Escalate: Elevate to higher authority
RISK SCORE MATRIX
Probability\Impact | 1-Minimal | 2-Low | 3-Medium | 4-High | 5-Critical
1-Very Low | 1 | 2 | 3 | 4 | 5
2-Low | 2 | 4 | 6 | 8 | 10
3-Medium | 3 | 6 | 9 | 12 | 15
4-High | 4 | 8 | 12 | 16 | 20
5-Very High | 5 | 10 | 15 | 20 | 25

## Risks
Risk_ID | Risk_Description | Category | Probability | Impact | Risk_Score | Status | Owner | Mitigation_Strategy | Contingency_Plan | Target_Date | Notes
R001 | Weather delays impacting construction schedule | Strategic | 3 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Weather delays impacting construction schedule... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R002 | Material cost escalation beyond budget | Strategic | 3 | 3 |  | Open | Site Superintendent | Implement comprehensive mitigation strategy for Material cost escalation beyond budget... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R003 | Labor shortage affecting timeline | Strategic | 3 | 3 |  | Open | Architects | Implement comprehensive mitigation strategy for Labor shortage affecting timeline... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R004 | Safety incidents causing work stoppages | Strategic | 3 | 3 |  | Open | Engineers | Implement comprehensive mitigation strategy for Safety incidents causing work stoppages... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R005 | Environmental compliance violations | Strategic | 3 | 3 |  | Open | Contractors | Implement comprehensive mitigation strategy for Environmental compliance violations... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R006 | Permit approval delays | Operational | 3 | 3 |  | Open | Safety Officers | Implement comprehensive mitigation strategy for Permit approval delays... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R007 | Soil condition surprises requiring redesign | Operational | 3 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Soil condition surprises requiring redesign... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R008 | Equipment breakdown causing delays | Operational | 3 | 3 |  | Open | Site Superintendent | Implement comprehensive mitigation strategy for Equipment breakdown causing delays... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R009 | Subcontractor performance issues | Operational | 3 | 3 |  | Open | Architects | Implement comprehensive mitigation strategy for Subcontractor performance issues... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R010 | Design changes increasing costs | Operational | 3 | 3 |  | Open | Engineers | Implement comprehensive mitigation strategy for Design changes increasing costs... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R011 | Utility relocation complications | Technical | 3 | 3 |  | Open | Contractors | Implement comprehensive mitigation strategy for Utility relocation complications... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R012 | Neighbor complaints and legal issues | Technical | 3 | 3 |  | Open | Safety Officers | Implement comprehensive mitigation strategy for Neighbor complaints and legal issues... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R013 | Quality control failures requiring rework | Technical | 3 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Quality control failures requiring rework... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R014 | Supply chain disruptions | Technical | 3 | 3 |  | Open | Site Superintendent | Implement comprehensive mitigation strategy for Supply chain disruptions... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R015 | Site access restrictions | Technical | 3 | 3 |  | Open | Architects | Implement comprehensive mitigation strategy for Site access restrictions... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R016 | Regulatory requirement changes | Financial | 3 | 3 |  | Open | Engineers | Implement comprehensive mitigation strategy for Regulatory requirement changes... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R017 | Foundation issues discovery | Financial | 3 | 3 |  | Open | Contractors | Implement comprehensive mitigation strategy for Foundation issues discovery... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R018 | Technology integration challenges | Financial | 3 | 3 |  | Open | Safety Officers | Implement comprehensive mitigation strategy for Technology integration challenges... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R019 | Budget overrun due to scope creep | Financial | 3 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Budget overrun due to scope creep... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction
R020 | Timeline compression impacts on quality | Financial | 3 | 3 |  | Open | Site Superintendent | Implement comprehensive mitigation strategy for Timeline compression impacts on quality... | Contingency plan for Construction Project risk management | 2025-08-30 | Industry-specific risk for Building and Infrastructure Construction

## Assumptions
Assumption_ID | Assumption_Description | Category | Confidence_Level | Impact_if_False | Validation_Method | Status | Owner | Validation_Date | Notes
A001 | Weather conditions within historical norms | Strategic | High | Medium | Document Review | Valid | Project Manager | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A002 | Material availability at projected costs | Strategic | High | Medium | Document Review | Valid | Site Superintendent | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A003 | Labor availability at planned rates | Strategic | High | Medium | Document Review | Valid | Architects | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A004 | Permit approvals within expected timeframes | Strategic | High | Medium | Document Review | Valid | Engineers | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A005 | Site conditions as per initial surveys | Strategic | High | Medium | Document Review | Valid | Contractors | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A006 | Subcontractor performance reliability | Operational | High | Medium | Document Review | Valid | Safety Officers | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A007 | Equipment availability and functionality | Operational | High | Medium | Document Review | Valid | Project Manager | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A008 | Design stability without major changes | Operational | High | Medium | Document Review | Valid | Site Superintendent | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A009 | Regulatory requirement stability | Operational | High | Medium | Document Review | Valid | Architects | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A010 | Budget adequacy for scope completion | Operational | High | Medium | Document Review | Valid | Engineers | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A011 | Timeline feasibility with current resources | Technical | High | Medium | Document Review | Valid | Contractors | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A012 | Quality standards achievability | Technical | High | Medium | Document Review | Valid | Safety Officers | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A013 | Safety protocol effectiveness | Technical | High | Medium | Document Review | Valid | Project Manager | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A014 | Environmental compliance capability | Technical | High | Medium | Document Review | Valid | Site Superintendent | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A015 | Technology integration success | Technical | High | Medium | Document Review | Valid | Architects | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A016 | Stakeholder cooperation and support | Financial | High | Medium | Document Review | Valid | Engineers | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A017 | Utility coordination effectiveness | Financial | High | Medium | Document Review | Valid | Contractors | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A018 | Site access availability | Financial | High | Medium | Document Review | Valid | Safety Officers | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A019 | Insurance coverage adequacy | Financial | High | Medium | Document Review | Valid | Project Manager | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation
A020 | Risk mitigation strategy effectiveness | Financial | High | Medium | Document Review | Valid | Site Superintendent | 2025-08-15 | Critical assumption for Building and Infrastructure Construction implementation

## Issues
Issue_ID | Issue_Description | Category | Priority | Severity | Status | Owner | Resolution_Plan | Target_Date | Actual_Date | Notes
I001 | Supply chain disruptions affecting material delivery | Process | Medium | Medium | Open | Project Manager | Develop comprehensive resolution plan for Supply chain disruptions affecting material delive... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I002 | Skilled labor shortage in local market | Process | Medium | Medium | Open | Site Superintendent | Develop comprehensive resolution plan for Skilled labor shortage in local market... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I003 | Equipment breakdown frequency | Process | Medium | Medium | Open | Architects | Develop comprehensive resolution plan for Equipment breakdown frequency... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I004 | Design coordination challenges | Process | Medium | Medium | Open | Engineers | Develop comprehensive resolution plan for Design coordination challenges... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I005 | Permit processing delays | Process | Medium | Medium | Open | Contractors | Develop comprehensive resolution plan for Permit processing delays... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I006 | Weather impact on outdoor work | Technical | Medium | Medium | Open | Safety Officers | Develop comprehensive resolution plan for Weather impact on outdoor work... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I007 | Quality control gaps | Technical | Medium | Medium | Open | Project Manager | Develop comprehensive resolution plan for Quality control gaps... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I008 | Safety protocol compliance | Technical | Medium | Medium | Open | Site Superintendent | Develop comprehensive resolution plan for Safety protocol compliance... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I009 | Subcontractor coordination difficulties | Technical | Medium | Medium | Open | Architects | Develop comprehensive resolution plan for Subcontractor coordination difficulties... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I010 | Site logistics optimization | Technical | Medium | Medium | Open | Engineers | Develop comprehensive resolution plan for Site logistics optimization... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I011 | Environmental compliance monitoring | Resource | Medium | Medium | Open | Contractors | Develop comprehensive resolution plan for Environmental compliance monitoring... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I012 | Cost control challenges | Resource | Medium | Medium | Open | Safety Officers | Develop comprehensive resolution plan for Cost control challenges... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I013 | Schedule compression impacts | Resource | Medium | Medium | Open | Project Manager | Develop comprehensive resolution plan for Schedule compression impacts... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I014 | Technology adoption resistance | Resource | Medium | Medium | Open | Site Superintendent | Develop comprehensive resolution plan for Technology adoption resistance... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I015 | Communication gaps between teams | Resource | Medium | Medium | Open | Architects | Develop comprehensive resolution plan for Communication gaps between teams... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I016 | Documentation completeness | Quality | Medium | Medium | Open | Engineers | Develop comprehensive resolution plan for Documentation completeness... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I017 | Risk assessment accuracy | Quality | Medium | Medium | Open | Contractors | Develop comprehensive resolution plan for Risk assessment accuracy... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I018 | Change management processes | Quality | Medium | Medium | Open | Safety Officers | Develop comprehensive resolution plan for Change management processes... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I019 | Stakeholder expectation alignment | Quality | Medium | Medium | Open | Project Manager | Develop comprehensive resolution plan for Stakeholder expectation alignment... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction
I020 | Performance monitoring effectiveness | Quality | Medium | Medium | Open | Site Superintendent | Develop comprehensive resolution plan for Performance monitoring effectiveness... | 2025-08-21 |  | Critical issue requiring attention for Building and Infrastructure Construction

## Dependencies
Dependency_ID | Dependency_Description | Type | Criticality | Status | Owner | Required_Date | Actual_Date | Impact_if_Delayed | Notes
D001 | Permit approvals from local authorities | Internal | High | Pending | Project Manager | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D002 | Material deliveries per schedule | Internal | High | Pending | Site Superintendent | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D003 | Equipment availability and maintenance | Internal | High | Pending | Architects | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D004 | Weather conditions for outdoor work | Internal | High | Pending | Engineers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D005 | Utility connections and relocations | Internal | High | Pending | Contractors | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D006 | Subcontractor mobilization | Internal | High | Pending | Safety Officers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D007 | Site preparation completion | Internal | High | Pending | Project Manager | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D008 | Design finalization and approvals | Internal | Medium | Pending | Site Superintendent | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D009 | Environmental clearances | Internal | Medium | Pending | Architects | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D010 | Safety training completion | Internal | Medium | Pending | Engineers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D011 | Insurance policy activation | External | Medium | Pending | Contractors | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D012 | Quality control setup | External | Medium | Pending | Safety Officers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D013 | Technology system implementation | External | Medium | Pending | Project Manager | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D014 | Stakeholder approval processes | External | Medium | Pending | Site Superintendent | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D015 | Budget release approvals | External | Low | Pending | Architects | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D016 | Regulatory inspection schedules | External | Low | Pending | Engineers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D017 | Neighbor notification completion | External | Low | Pending | Contractors | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D018 | Site access arrangements | External | Low | Pending | Safety Officers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D019 | Emergency response plan activation | External | Low | Pending | Project Manager | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success
D020 | Project team mobilization | External | Low | Pending | Site Superintendent | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Building and Infrastructure Construction success