## Lessons Learned Overview
ENTERPRISE RESOURCE PLANNING IMPLEMENTATION - LESSONS LEARNED
Project: ERP Implementation
Date: July 31, 2025
PMI 2025 Standards Compliant
LESSONS LEARNED SUMMARY
Lesson_ID | Lesson_Description | Category | Impact_Level | Recommendation | Future_Application | Stakeholder | Date_Identified | Status | Notes
LL001 | Business process standardization must precede system configuration | Process | High | Implement best practice based on: Business process standardization must precede syst... | Apply to future ERP Implementation projects | ERP Project Manager | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL002 | Data cleansing requirements are consistently underestimated in planning | Process | High | Implement best practice based on: Data cleansing requirements are consistently under... | Apply to future ERP Implementation projects | Business Process Owners | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL003 | User training should begin during system configuration phase | Process | High | Implement best practice based on: User training should begin during system configura... | Apply to future ERP Implementation projects | IT Architects | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL004 | Change management communication must be continuous throughout project | Technical | High | Implement best practice based on: Change management communication must be continuous... | Apply to future ERP Implementation projects | End Users | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL005 | Integration testing requires dedicated environments and extended timelines | Technical | Medium | Implement best practice based on: Integration testing requires dedicated environment... | Apply to future ERP Implementation projects | Change Managers | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL006 | Executive sponsorship visibility directly impacts user adoption rates | Technical | Medium | Implement best practice based on: Executive sponsorship visibility directly impacts ... | Apply to future ERP Implementation projects | Executive Sponsors | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL007 | Customization decisions should prioritize long-term maintainability | Management | Medium | Implement best practice based on: Customization decisions should prioritize long-ter... | Apply to future ERP Implementation projects | ERP Project Manager | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL008 | Go-live support requires 24/7 coverage for initial stabilization period | Management | Medium | Implement best practice based on: Go-live support requires 24/7 coverage for initial... | Apply to future ERP Implementation projects | Business Process Owners | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL009 | Performance testing must include realistic data volumes and user loads | Management | Low | Implement best practice based on: Performance testing must include realistic data vo... | Apply to future ERP Implementation projects | IT Architects | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects
LL010 | Post-implementation optimization is essential for ROI realization | Strategic | Low | Implement best practice based on: Post-implementation optimization is essential for ... | Apply to future ERP Implementation projects | End Users | 2025-07-31 | Validated | Critical lesson for Enterprise Resource Planning Implementation projects