## Open Action Items
NETWORK INFRASTRUCTURE AND COMMUNICATIONS - OPEN ACTION ITEM LOG
Project: Network Implementation
Date: July 31, 2025
PMI 2025 Standards Compliant
ACTION ITEM TRACKING
Action_ID | Action_Description | Priority | Status | Owner | Due_Date | Completion_Date | Progress_% | Dependencies | Notes
AI001 | Complete network capacity planning and future growth analysis | High | In Progress | Network Architects | 2025-08-30 |  | 25 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI002 | Implement redundancy and failover mechanisms across infrastructure | High | In Progress | Network Engineers | 2025-09-04 |  | 32 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI003 | Deploy network security segmentation and access controls | High | In Progress | Security Specialists | 2025-09-09 |  | 39 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI004 | Establish comprehensive performance monitoring and alerting | High | In Progress | Operations Teams | 2025-09-14 |  | 46 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI005 | Implement configuration management and version control procedures | Medium | In Progress | End Users | 2025-09-19 |  | 53 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI006 | Finalize vendor support agreements and escalation procedures | Medium | In Progress | Vendors | 2025-09-24 |  | 60 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI007 | Complete network documentation and topology diagrams | Medium | Not Started | Network Architects | 2025-09-29 |  | 67 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI008 | Establish change management procedures and approval workflows | Medium | Not Started | Network Engineers | 2025-10-04 |  | 74 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI009 | Execute comprehensive network testing and validation procedures | Low | Not Started | Security Specialists | 2025-10-09 |  | 81 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success
AI010 | Deploy staff training program for network operations and maintenance | Low | Completed | Operations Teams | 2025-10-14 | 2025-07-31 | 100 | Dependent on Network Implementation milestone completion | Critical action for Network Infrastructure and Communications success