## Stakeholder Register
Construction Project - Stakeholder Register
Generated: July 15, 2025 ¦ PMI 2025 Standards Compliant ¦ Classification: Confidential
Stakeholder ID | Name | Title | Organization | Category | Role | Responsibilities | Influence | Interest | Current Engagement | Desired Engagement | Communication Preference | Frequency | Key Concerns | Expectations | Contact Information | Notes
SH-001 | Plumbing Contractor | Construction Project Manager | Executive Leadership | Executive Leadership | Executive Sponsor and Strategic Decision Maker | Strategic oversight, resource allocation, organizational alignment, executive decision making | Very High | High | Supportive | Leading | Executive Briefings | Monthly | ROI achievement, competitive advantage, organizational transformation | Strategic value delivery, minimal business disruption, clear communication | chief.executive.officer@company.com | Active stakeholder requiring regular engagement
SH-002 | Site Superintendent | Site Superintendent | Technology Leadership | Executive Leadership | Technical Strategy and Architecture Oversight | Technology strategy, architecture approval, technical risk management, vendor relationships | Very High | Very High | Leading | Leading | Technical Reviews | Weekly | Technical feasibility, integration complexity, security and compliance | Technical excellence, scalable architecture, innovation leadership | chief.technology.officer@company.com | Active stakeholder requiring regular engagement
SH-003 | Construction Manager | Senior Construction Manager | Financial Leadership | Executive Leadership | Financial Oversight and Budget Management | Budget approval, financial performance monitoring, cost control, ROI measurement | High | High | Supportive | Leading | Financial Reports | Monthly | Budget adherence, cost control, financial returns, risk management | Budget compliance, clear financial benefits, transparent reporting | chief.financial.officer@company.com | Active stakeholder requiring regular engagement
SH-004 | Architect | Lead Architect | Project Analysis Department | Technical Teams | Construction Implementation Lead and Subject Matter Expert | Design Prototype development, construction method selection, data strategy, technical implementation | High | Very High | Leading | Leading | Technical Workshops | Daily | Design Prototype quality compliance, data quality, technical performance, scalability | Technical excellence, advanced capabilities, innovation opportunities | data.science.director@company.com | Active stakeholder requiring regular engagement
SH-005 | Structural Engineer | Structural Engineer | Information Technology | Technical Teams | Infrastructure and Platform Support | Infrastructure provisioning, system integration, security implementation, operational support | Medium | High | Supportive | Leading | Technical Meetings | Weekly | System reliability, security compliance, operational impact, resource requirements | Stable infrastructure, clear requirements, adequate resources | it.infrastructure.manager@company.com | Active stakeholder requiring regular engagement
SH-006 | Civil Engineer | Civil Engineering Manager | Business Operations | Business Users | Business Process Owner and End User Representative | Requirements definition, process cost efficiency, user acceptance, change management | Medium | Very High | Supportive | Leading | Business Workshops | Weekly | Process efficiency, user adoption, business value, operational impact | Improved efficiency, user-friendly systems, comprehensive design validation | business.operations.manager@company.com | Active stakeholder requiring regular engagement
SH-007 | Safety Officer | Chief Safety Officer | Legal and Compliance | Regulatory Bodies | Permit and Regulatory Approval and Risk Management | Compliance inspection, regulatory requirements, risk assessment, audit support | High | Medium | Neutral | Leading | Compliance Reports | Monthly | Regulatory compliance, data privacy, audit requirements, risk management | Full compliance, comprehensive documentation, risk mitigation | compliance.officer@company.com | Active stakeholder requiring regular engagement
SH-008 | Quality Inspector | Quality Control Inspector | Customer Success | Customers/End Users | Customer Impact Assessment and Experience Cost Efficiency | Customer impact analysis, experience cost efficiency, feedback collection, satisfaction measurement | Medium | High | Supportive | Leading | Customer Reports | Monthly | Customer satisfaction, service quality, experience improvement, competitive advantage | Enhanced customer experience, improved service delivery, competitive differentiation | customer.experience.director@company.com | Active stakeholder requiring regular engagement
SH-009 | Construction Vendor Representative | Electrical Subcontractor | Technology Vendor | External Partners | Technology Platform Provider and Implementation Support | Platform implementation, technical support, best practices guidance, performance cost efficiency | Medium | High | Leading | Leading | Technical Collaboration | Daily | Successful implementation, customer satisfaction, platform adoption, technical excellence | Successful construction implementation, positive customer experience, long-term partnership | ai/ml.vendor.representative@company.com | Active stakeholder requiring regular engagement
SH-010 | Plumbing Contractor | Senior Plumbing Contractor | Project Management Office | Project Team | Project Coordination and Management | Project planning, execution oversight, stakeholder coordination, risk management | Medium | Very High | Leading | Leading | Project Meetings | Daily | Project success, timeline adherence, budget compliance, stakeholder satisfaction | Successful delivery, stakeholder alignment, quality outcomes | project.manager@company.com | Active stakeholder requiring regular engagement
SH-011 | HVAC Contractor | Senior HVAC Contractor | Information Security | Technical Teams | Security Design and Implementation Oversight | Security architecture, threat assessment, compliance inspection, security testing | High | Medium | Supportive | Leading | Security Reviews | Weekly | Security compliance, threat mitigation, data protection, access control | Robust security, compliance adherence, risk mitigation | security.architect@company.com | Active stakeholder requiring regular engagement
SH-012 | Material Supplier | Primary Material Supplier | Human Resources | Business Users | Design Validation Program Development and Delivery | Design Validation design, curriculum development, delivery coordination, competency assessment | Low | High | Supportive | Leading | Design Validation Workshops | Weekly | Design Validation effectiveness, user competency, adoption success, resource requirements | Comprehensive design validation, user readiness, successful adoption | design validation.manager@company.com | Active stakeholder requiring regular engagement
SH-013 | Equipment Operator | Heavy Equipment Operator | Quality Assurance | Project Team | Quality Inspection and Testing Oversight | Testing strategy, quality inspection, defect management, acceptance criteria | Medium | High | Supportive | Leading | Quality Reviews | Weekly | Quality standards, testing coverage, defect resolution, acceptance criteria | High quality deliverables, comprehensive testing, defect-free implementation | quality.assurance.lead@company.com | Active stakeholder requiring regular engagement
SH-014 | Building Inspector | Municipal Building Inspector | Organizational Development | Project Team | Organizational Change and Adoption Support | Change strategy, adoption planning, resistance management, communication coordination | Medium | High | Leading | Leading | Change Workshops | Weekly | User adoption, change resistance, organizational readiness, communication effectiveness | Smooth transition, high adoption, minimal resistance | change.management.specialist@company.com | Active stakeholder requiring regular engagement
SH-015 | Environmental Consultant | Senior Environmental Consultant | Business Analysis | Project Team | Requirements Analysis and Process Cost Efficiency | Requirements gathering, process analysis, solution design, stakeholder liaison | Medium | Very High | Leading | Leading | Requirements Workshops | Daily | Requirements quality compliance, process cost efficiency, stakeholder alignment, solution effectiveness | Clear requirements, optimized processes, stakeholder satisfaction | business.analyst@company.com | Active stakeholder requiring regular engagement

## Influence-Interest Matrix
Construction Project - Stakeholder Influence-Interest Matrix
| Very Low | Low | Medium | High | Very High
Very High |  |  |  | Plumbing Contractor | Site Superintendent
High |  |  | Safety Officer HVAC Contractor | Construction Manager | Architect
Medium |  |  |  | Structural Engineer Quality Inspector Construction Vendor Representative Equipment Operator Building Inspector | Civil Engineer Plumbing Contractor Environmental Consultant
Low |  |  |  | Material Supplier
Very Low
Matrix Legend:
Manage Closely | High Influence, High Interest
Keep Satisfied | High Influence, Low Interest
Keep Informed | Low Influence, High Interest
Monitor | Low Influence, Low Interest

## Engagement Assessment
Construction Project - Stakeholder Engagement Assessment
Assessment Date: July 15, 2025 ¦ Next Review: August 14, 2025
Stakeholder | Current Engagement | Desired Engagement | Gap Analysis | Engagement Strategy | Actions Required | Timeline | Owner | Status
Plumbing Contractor | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Site Superintendent | Leading | Leading | No gap - maintain current level | Empower as change champion | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Construction Manager | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Architect | Leading | Leading | No gap - maintain current level | Empower as change champion | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Structural Engineer | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Civil Engineer | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Safety Officer | Neutral | Leading | Significant gap - move from Neutral to Leading | Engagement and involvement activities | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Quality Inspector | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Construction Vendor Representative | Leading | Leading | No gap - maintain current level | Empower as change champion | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Plumbing Contractor | Leading | Leading | No gap - maintain current level | Empower as change champion | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
HVAC Contractor | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Material Supplier | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Equipment Operator | Supportive | Leading | Minor gap - enhance to leading | Maintain support and leverage advocacy | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Building Inspector | Leading | Leading | No gap - maintain current level | Empower as change champion | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress
Environmental Consultant | Leading | Leading | No gap - maintain current level | Empower as change champion | Regular communication, involvement in decisions, feedback collection | Ongoing throughout project | Plumbing Contractor / Change Lead | In Progress

## Communication Plan
Construction Project - Stakeholder Communication Plan
Plan Date: July 15, 2025 ¦ Review Frequency: Monthly
Stakeholder/Group | Communication Type | Frequency | Method/Channel | Content/Purpose | Owner | Timing | Feedback Mechanism | Success Metrics
Plumbing Contractor | Executive Briefing | Monthly | Executive Briefings | Project progress, decisions, issues, and roi achievement | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Site Superintendent | Executive Briefing | Weekly | Technical Reviews | Project progress, decisions, issues, and technical feasibility | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Construction Manager | Executive Briefing | Monthly | Financial Reports | Project progress, decisions, issues, and budget adherence | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Architect | Technical Review | Daily | Technical Workshops | Project progress, decisions, issues, and design prototype quality compliance | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Structural Engineer | Technical Review | Weekly | Technical Meetings | Project progress, decisions, issues, and system reliability | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Civil Engineer | Business Update | Weekly | Business Workshops | Project progress, decisions, issues, and process efficiency | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Safety Officer | Compliance Report | Monthly | Compliance Reports | Project progress, decisions, issues, and regulatory compliance | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Quality Inspector | Impact Assessment | Monthly | Customer Reports | Project progress, decisions, issues, and customer satisfaction | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Construction Vendor Representative | Partnership Review | Daily | Technical Collaboration | Project progress, decisions, issues, and successful implementation | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Plumbing Contractor | Project Status | Daily | Project Meetings | Project progress, decisions, issues, and project success | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
HVAC Contractor | Technical Review | Weekly | Security Reviews | Project progress, decisions, issues, and security compliance | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Material Supplier | Business Update | Weekly | Design Validation Workshops | Project progress, decisions, issues, and design validation effectiveness | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Equipment Operator | Project Status | Weekly | Quality Reviews | Project progress, decisions, issues, and quality standards | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Building Inspector | Project Status | Weekly | Change Workshops | Project progress, decisions, issues, and user adoption | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
Environmental Consultant | Project Status | Daily | Requirements Workshops | Project progress, decisions, issues, and requirements quality compliance | Plumbing Contractor | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate

## Stakeholder Analysis
Construction Project - Detailed Stakeholder Analysis
Analysis Date: July 15, 2025 ¦ PMI 2025 Standards Compliant
Stakeholder | Power/Influence | Interest Level | Attitude | Impact on Project | Potential Risks | Mitigation Strategies | Opportunities | Key Messages
Plumbing Contractor | Very High - Can significantly impact project decisions and outcomes | High - ROI achievement | Supportive - Generally positive toward project objectives | Critical - Essential for project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, strategic value delivery, clear communication
Site Superintendent | Very High - Can significantly impact project decisions and outcomes | Very High - Technical feasibility | Leading - Generally positive toward project objectives | Critical - Essential for project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, technical excellence, clear communication
Construction Manager | High - Can significantly impact project decisions and outcomes | High - Budget adherence | Supportive - Generally positive toward project objectives | Critical - Essential for project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, budget compliance, clear communication
Architect | High - Can significantly impact project decisions and outcomes | Very High - Design Prototype quality compliance | Leading - Generally positive toward project objectives | Critical - Essential for project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, technical excellence, clear communication
Structural Engineer | Medium - Can significantly impact project decisions and outcomes | High - System reliability | Supportive - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, stable infrastructure, clear communication
Civil Engineer | Medium - Can significantly impact project decisions and outcomes | Very High - Process efficiency | Supportive - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, improved efficiency, clear communication
Safety Officer | High - Can significantly impact project decisions and outcomes | Medium - Regulatory compliance | Neutral - Generally positive toward project objectives | Critical - Essential for project success | Resistance to change, limited support, potential delays | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Conversion to supporter, expertise utilization, network access | Project benefits, full compliance, clear communication
Quality Inspector | Medium - Can significantly impact project decisions and outcomes | High - Customer satisfaction | Supportive - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, enhanced customer experience, clear communication
Construction Vendor Representative | Medium - Can significantly impact project decisions and outcomes | High - Successful implementation | Leading - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, successful construction implementation, clear communication
Plumbing Contractor | Medium - Can significantly impact project decisions and outcomes | Very High - Project success | Leading - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, successful delivery, clear communication
HVAC Contractor | High - Can significantly impact project decisions and outcomes | Medium - Security compliance | Supportive - Generally positive toward project objectives | Critical - Essential for project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, robust security, clear communication
Material Supplier | Low - Can significantly impact project decisions and outcomes | High - Design Validation effectiveness | Supportive - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, comprehensive design validation, clear communication
Equipment Operator | Medium - Can significantly impact project decisions and outcomes | High - Quality standards | Supportive - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, high quality deliverables, clear communication
Building Inspector | Medium - Can significantly impact project decisions and outcomes | High - User adoption | Leading - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, smooth transition, clear communication
Environmental Consultant | Medium - Can significantly impact project decisions and outcomes | Very High - Requirements quality compliance | Leading - Generally positive toward project objectives | Important - Significant contribution to project success | Resource constraints, competing priorities, communication gaps | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, clear requirements, clear communication

## Action Plan
Construction Project - Stakeholder Management Action Plan
Plan Date: July 15, 2025 ¦ Review Frequency: Weekly
Action ID | Stakeholder/Group | Action Description | Objective | Owner | Start Date | Due Date | Status | Progress % | Notes
SA-001 | Plumbing Contractor | Initial stakeholder meeting and relationship building | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-002 | Plumbing Contractor | Regular communication and progress updates | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-003 | Plumbing Contractor | Involvement in key project decisions and reviews | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-004 | Plumbing Contractor | Design Validation and capability development support | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-005 | Plumbing Contractor | Feedback collection and response management | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-006 | Site Superintendent | Initial stakeholder meeting and relationship building | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-007 | Site Superintendent | Regular communication and progress updates | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-008 | Site Superintendent | Involvement in key project decisions and reviews | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-009 | Site Superintendent | Design Validation and capability development support | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-010 | Site Superintendent | Feedback collection and response management | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-011 | Construction Manager | Initial stakeholder meeting and relationship building | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-012 | Construction Manager | Regular communication and progress updates | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-013 | Construction Manager | Involvement in key project decisions and reviews | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-014 | Construction Manager | Design Validation and capability development support | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-015 | Construction Manager | Feedback collection and response management | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-016 | Architect | Initial stakeholder meeting and relationship building | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-017 | Architect | Regular communication and progress updates | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-018 | Architect | Involvement in key project decisions and reviews | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-019 | Architect | Design Validation and capability development support | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-020 | Architect | Feedback collection and response management | Maintain Leading engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-021 | Structural Engineer | Initial stakeholder meeting and relationship building | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-022 | Structural Engineer | Regular communication and progress updates | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-023 | Structural Engineer | Involvement in key project decisions and reviews | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-024 | Structural Engineer | Design Validation and capability development support | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-025 | Structural Engineer | Feedback collection and response management | Maintain Supportive engagement level | Plumbing Contractor | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase