## Open Action Items
IT - OPEN ACTION ITEM LOG
Project: IT RAID Log
Date: July 31, 2025
PMI 2025 Standards Compliant
ACTION ITEM TRACKING
Action_ID | Action_Description | Priority | Status | Owner | Due_Date | Completion_Date | Progress_% | Dependencies | Notes
AI001 | Complete data quality assessment for training datasets | High | In Progress | Chief Technology Officer | 2025-08-30 |  | 25 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI002 | Establish AI ethics committee and governance framework | High | In Progress | IT Managers | 2025-09-04 |  | 32 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI003 | Implement model monitoring and alerting systems | High | In Progress | DevOps Engineers | 2025-09-09 |  | 39 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI004 | Develop comprehensive user training curriculum | High | In Progress | System Administrators | 2025-09-14 |  | 46 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI005 | Create data privacy and security protocols | Medium | In Progress | Ethics Committee | 2025-09-19 |  | 53 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI006 | Finalize vendor contracts and support agreements | Medium | In Progress | Compliance Officers | 2025-09-24 |  | 60 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI007 | Establish performance benchmarks and KPIs | Medium | Not Started | Chief Technology Officer | 2025-09-29 |  | 67 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI008 | Complete regulatory compliance documentation | Medium | Not Started | IT Managers | 2025-10-04 |  | 74 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI009 | Implement change management communication plan | Low | Not Started | DevOps Engineers | 2025-10-09 |  | 81 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success
AI010 | Conduct pilot testing with select user groups | Low | Completed | System Administrators | 2025-10-14 | 2025-07-31 | 100 | Dependent on Cloud Infrastructure Migration milestone completion | Critical action for Information Technology success