## Instructions & User Guide
PRODUCT - NEW PRODUCT LAUNCH AND DEVELOPMENT
Communication Plan
PMI 2025 Standards Compliant
DOCUMENT OVERVIEW
This template outlines the communication strategy for the Core Product Development System Modernization project, ensuring all stakeholders receive timely and relevant information.
KEY FEATURES
• Stakeholder communication matrix
• Communication frequency and methods
• Escalation procedures
• PMI 2025 communication standards
HOW TO USE THIS TEMPLATE
1. Review all tabs to understand the template structure
2. Fill in the yellow highlighted cells with your project-specific information
3. Do not modify formulas or calculated fields
4. Use dropdown menus where provided for consistency
5. Save regularly and maintain version control
6. Export to PDF for stakeholder distribution

## Communication Plan
PRODUCT - NEW PRODUCT LAUNCH AND DEVELOPMENT - COMMUNICATION PLAN
Stakeholder_Group | Communication_Type | Purpose | Frequency | Method | Owner | Distribution_List | Success_Metrics | Notes
Executive Leadership | Status Report | High-level project updates | Monthly | Executive Briefing | Project Manager | VP of Product, Product Director, Operations Director | Attendance, Feedback | Focus on strategic outcomes
Project Team | Team Meeting | Daily coordination | Daily | Standup Meeting | Scrum Master | All team members | Attendance, Action items | 15-minute daily sync
Stakeholders | Newsletter | Project progress updates | Bi-weekly | Email | Communications Lead | All stakeholders | Open rate, Feedback | Include milestones and wins
End Users | Training Announcement | Training schedule and materials | As needed | Email + Portal | Training Manager | All end users | Registration rate | Advance notice required
Vendors | Vendor Meeting | Technical coordination | Weekly | Video Conference | Technical Lead | Vendor team | Issue resolution time | Track action items