## Stakeholder Register
Product Implementation Project - Stakeholder Register
Generated: July 15, 2025 ¦ PMI 2025 Standards Compliant ¦ Classification: Confidential
Stakeholder ID | Name | Title | Organization | Category | Role | Responsibilities | Influence | Interest | Current Engagement | Desired Engagement | Communication Preference | Frequency | Key Concerns | Expectations | Contact Information | Notes
SH-001 | Product Product Training Manager | Product Implementation Manager | Overall Product project leadership and coordination | High | High | Strategic oversight, resource allocation, organizational alignment, executive decision making | Very High | High | Supportive | Leading | Executive Briefings | Monthly | ROI achievement, competitive advantage, organizational transformation | Strategic value delivery, minimal business disruption, clear communication | chief.executive.officer@company.com | Active stakeholder requiring regular engagement
SH-002 | Business Process Owner | Business Process Owner | Business process design and requirements definition | High | High | Technology strategy, architecture approval, technical risk management, vendor relationships | Very High | Very High | Leading | Leading | Technical Reviews | Weekly | Technical feasibility, integration complexity, security and compliance | Technical excellence, scalable architecture, innovation leadership | chief.technology.officer@company.com | Active stakeholder requiring regular engagement
SH-003 | System Administrator | Product System Administrator | Product system configuration and technical administration | High | High | Budget approval, financial performance monitoring, cost control, ROI measurement | High | High | Supportive | Leading | Financial Reports | Monthly | Budget adherence, cost control, financial returns, risk management | Budget compliance, clear financial benefits, transparent reporting | chief.financial.officer@company.com | Active stakeholder requiring regular engagement
SH-004 | Data Migration Specialist | Data Migration Lead | Legacy data extraction, transformation, and loading | Medium | High | Model development, algorithm selection, data strategy, technical implementation | High | Very High | Leading | Leading | Technical Workshops | Daily | Model accuracy, data quality, technical performance, scalability | Technical excellence, advanced capabilities, innovation opportunities | data.science.director@company.com | Active stakeholder requiring regular engagement
SH-005 | Training Coordinator | Product Finance Director | End user training program development and delivery | Medium | High | Infrastructure provisioning, system integration, security implementation, operational support | Medium | High | Supportive | Leading | Technical Meetings | Weekly | System reliability, security compliance, operational impact, resource requirements | Stable infrastructure, clear requirements, adequate resources | it.infrastructure.manager@company.com | Active stakeholder requiring regular engagement
SH-006 | HR Director | Human Resources Director | Organizational change management and user adoption | High | High | Requirements definition, process optimization, user acceptance, change management | Medium | Very High | Supportive | Leading | Business Workshops | Weekly | Process efficiency, user adoption, business value, operational impact | Improved efficiency, user-friendly systems, comprehensive training | business.operations.manager@company.com | Active stakeholder requiring regular engagement
SH-007 | Product Vendor Representative | Vendor Implementation Consultant | Product software configuration and best practices guidance | Medium | High | Compliance validation, regulatory requirements, risk assessment, audit support | High | Medium | Neutral | Leading | Compliance Reports | Monthly | Regulatory compliance, data privacy, audit requirements, risk management | Full compliance, comprehensive documentation, risk mitigation | compliance.officer@company.com | Active stakeholder requiring regular engagement
SH-008 | Executive Sponsor | Senior Executive Sponsor | Requirements gathering and process analysis | Medium | High | Customer impact analysis, experience optimization, feedback collection, satisfaction measurement | Medium | High | Supportive | Leading | Customer Reports | Monthly | Customer satisfaction, service quality, experience improvement, competitive advantage | Enhanced customer experience, improved service delivery, competitive differentiation | customer.experience.director@company.com | Active stakeholder requiring regular engagement
SH-009 | End User Representative | Super User | End user requirements and testing coordination | Medium | High | Platform implementation, technical support, best practices guidance, performance optimization | Medium | High | Leading | Leading | Technical Collaboration | Daily | Successful implementation, customer satisfaction, platform adoption, technical excellence | Successful deployment, positive customer experience, long-term partnership | ai/ml.vendor.representative@company.com | Active stakeholder requiring regular engagement
SH-010 | Training Coordinator | Training Coordinator | Technical infrastructure and system integration | Medium | High | Project planning, execution oversight, stakeholder coordination, risk management | Medium | Very High | Leading | Leading | Project Meetings | Daily | Project success, timeline adherence, budget compliance, stakeholder satisfaction | Successful delivery, stakeholder alignment, quality outcomes | project.manager@company.com | Active stakeholder requiring regular engagement
SH-011 | Quality Assurance Tester | Product QA Specialist | System testing and quality assurance validation | Medium | High | Security architecture, threat assessment, compliance validation, security testing | High | Medium | Supportive | Leading | Security Reviews | Weekly | Security compliance, threat mitigation, data protection, access control | Robust security, compliance adherence, risk mitigation | security.architect@company.com | Active stakeholder requiring regular engagement
SH-012 | Finance Director | Finance Director | Financial module requirements and approval authority | High | Medium | Training design, curriculum development, delivery coordination, competency assessment | Low | High | Supportive | Leading | Training Workshops | Weekly | Training effectiveness, user competency, adoption success, resource requirements | Comprehensive training, user readiness, successful adoption | training.manager@company.com | Active stakeholder requiring regular engagement
SH-013 | Human Resources Director | Human Resources Director | Operations module requirements and process optimization | High | Medium | Testing strategy, quality validation, defect management, acceptance criteria | Medium | High | Supportive | Leading | Quality Reviews | Weekly | Quality standards, testing coverage, defect resolution, acceptance criteria | High quality deliverables, comprehensive testing, defect-free implementation | quality.assurance.lead@company.com | Active stakeholder requiring regular engagement
SH-014 | HR Director | Human Resources Director | HR module requirements and workforce management | Medium | Medium | Change strategy, adoption planning, resistance management, communication coordination | Medium | High | Leading | Leading | Change Workshops | Weekly | User adoption, change resistance, organizational readiness, communication effectiveness | Smooth transition, high adoption, minimal resistance | change.management.specialist@company.com | Active stakeholder requiring regular engagement
SH-015 | Executive Sponsor | Executive Sponsor | Strategic oversight and executive decision making | High | Medium | Requirements gathering, process analysis, solution design, stakeholder liaison | Medium | Very High | Leading | Leading | Requirements Workshops | Daily | Requirements accuracy, process optimization, stakeholder alignment, solution effectiveness | Clear requirements, optimized processes, stakeholder satisfaction | business.analyst@company.com | Active stakeholder requiring regular engagement

## Influence-Interest Matrix
Product Implementation Project - Stakeholder Influence-Interest Matrix
SH-001 | Product Product Training Manager | Product Implementation Manager | Overall Product project leadership and coordination | High | High
SH-002 | Business Process Owner | Business Process Owner | Business process design and requirements definition | High | High
SH-003 | System Administrator | Product System Administrator | Product system configuration and technical administration | High | High
SH-004 | Data Migration Specialist | Data Migration Lead | Legacy data extraction, transformation, and loading | Medium | High
SH-005 | Training Coordinator | Product Finance Director | End user training program development and delivery | Medium | High
SH-006 | HR Director | Human Resources Director | Organizational change management and user adoption | High | High
SH-007 | Product Vendor Representative | Vendor Implementation Consultant | Product software configuration and best practices guidance | Medium | High
SH-008 | Executive Sponsor | Senior Executive Sponsor | Requirements gathering and process analysis | Medium | High
SH-009 | End User Representative | Super User | End user requirements and testing coordination | Medium | High
SH-010 | Training Coordinator | Training Coordinator | Technical infrastructure and system integration | Medium | High
SH-011 | Quality Assurance Tester | Product QA Specialist | System testing and quality assurance validation | Medium | High
SH-012 | Finance Director | Finance Director | Financial module requirements and approval authority | High | Medium
SH-013 | Human Resources Director | Human Resources Director | Operations module requirements and process optimization | High | Medium
SH-014 | HR Director | Human Resources Director | HR module requirements and workforce management | Medium | Medium
SH-015 | Executive Sponsor | Executive Sponsor | Strategic oversight and executive decision making | High | Medium

## Engagement Assessment
Product Implementation Project - Stakeholder Engagement Assessment
Assessment Date: July 15, 2025 ¦ Next Review: August 14, 2025
Stakeholder | Current Engagement | Desired Engagement | Gap Analysis | Engagement Strategy | Actions Required | Timeline | Owner | Status
SH-001 | Product Product Training Manager | Product Implementation Manager | Overall Product project leadership and coordination | High | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-002 | Business Process Owner | Business Process Owner | Business process design and requirements definition | High | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-003 | System Administrator | Product System Administrator | Product system configuration and technical administration | High | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-004 | Data Migration Specialist | Data Migration Lead | Legacy data extraction, transformation, and loading | Medium | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-005 | Training Coordinator | Product Finance Director | End user training program development and delivery | Medium | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-006 | HR Director | Human Resources Director | Organizational change management and user adoption | High | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-007 | Product Vendor Representative | Vendor Implementation Consultant | Product software configuration and best practices guidance | Medium | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-008 | Executive Sponsor | Senior Executive Sponsor | Requirements gathering and process analysis | Medium | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-009 | End User Representative | Super User | End user requirements and testing coordination | Medium | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-010 | Training Coordinator | Training Coordinator | Technical infrastructure and system integration | Medium | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-011 | Quality Assurance Tester | Product QA Specialist | System testing and quality assurance validation | Medium | High | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-012 | Finance Director | Finance Director | Financial module requirements and approval authority | High | Medium | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-013 | Human Resources Director | Human Resources Director | Operations module requirements and process optimization | High | Medium | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-014 | HR Director | Human Resources Director | HR module requirements and workforce management | Medium | Medium | Ongoing throughout project | Product Training Manager / Change Lead | In Progress
SH-015 | Executive Sponsor | Executive Sponsor | Strategic oversight and executive decision making | High | Medium | Ongoing throughout project | Product Training Manager / Change Lead | In Progress

## Communication Plan
Product Implementation Project - Stakeholder Communication Plan
Plan Date: July 15, 2025 ¦ Review Frequency: Monthly
Stakeholder/Group | Communication Type | Frequency | Method/Channel | Content/Purpose | Owner | Timing | Feedback Mechanism | Success Metrics
SH-001 | Product Product Training Manager | Product Implementation Manager | Overall Product project leadership and coordination | High | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-002 | Business Process Owner | Business Process Owner | Business process design and requirements definition | High | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-003 | System Administrator | Product System Administrator | Product system configuration and technical administration | High | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-004 | Data Migration Specialist | Data Migration Lead | Legacy data extraction, transformation, and loading | Medium | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-005 | Training Coordinator | Product Finance Director | End user training program development and delivery | Medium | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-006 | HR Director | Human Resources Director | Organizational change management and user adoption | High | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-007 | Product Vendor Representative | Vendor Implementation Consultant | Product software configuration and best practices guidance | Medium | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-008 | Executive Sponsor | Senior Executive Sponsor | Requirements gathering and process analysis | Medium | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-009 | End User Representative | Super User | End user requirements and testing coordination | Medium | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-010 | Training Coordinator | Training Coordinator | Technical infrastructure and system integration | Medium | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-011 | Quality Assurance Tester | Product QA Specialist | System testing and quality assurance validation | Medium | High | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-012 | Finance Director | Finance Director | Financial module requirements and approval authority | High | Medium | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-013 | Human Resources Director | Human Resources Director | Operations module requirements and process optimization | High | Medium | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-014 | HR Director | Human Resources Director | HR module requirements and workforce management | Medium | Medium | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate
SH-015 | Executive Sponsor | Executive Sponsor | Strategic oversight and executive decision making | High | Medium | As per frequency schedule | Direct feedback, surveys, Q&A sessions | Engagement level, satisfaction score, response rate

## Stakeholder Analysis
Product Implementation Project - Detailed Stakeholder Analysis
Analysis Date: July 15, 2025 ¦ PMI 2025 Standards Compliant
Stakeholder | Power/Influence | Interest Level | Attitude | Impact on Project | Potential Risks | Mitigation Strategies | Opportunities | Key Messages
SH-001 | Product Product Training Manager | Product Implementation Manager | Overall Product project leadership and coordination | High | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, strategic value delivery, clear communication
SH-002 | Business Process Owner | Business Process Owner | Business process design and requirements definition | High | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, technical excellence, clear communication
SH-003 | System Administrator | Product System Administrator | Product system configuration and technical administration | High | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, budget compliance, clear communication
SH-004 | Data Migration Specialist | Data Migration Lead | Legacy data extraction, transformation, and loading | Medium | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, technical excellence, clear communication
SH-005 | Training Coordinator | Product Finance Director | End user training program development and delivery | Medium | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, stable infrastructure, clear communication
SH-006 | HR Director | Human Resources Director | Organizational change management and user adoption | High | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, improved efficiency, clear communication
SH-007 | Product Vendor Representative | Vendor Implementation Consultant | Product software configuration and best practices guidance | Medium | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Conversion to supporter, expertise utilization, network access | Project benefits, full compliance, clear communication
SH-008 | Executive Sponsor | Senior Executive Sponsor | Requirements gathering and process analysis | Medium | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, enhanced customer experience, clear communication
SH-009 | End User Representative | Super User | End user requirements and testing coordination | Medium | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, successful deployment, clear communication
SH-010 | Training Coordinator | Training Coordinator | Technical infrastructure and system integration | Medium | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, successful delivery, clear communication
SH-011 | Quality Assurance Tester | Product QA Specialist | System testing and quality assurance validation | Medium | High | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, robust security, clear communication
SH-012 | Finance Director | Finance Director | Financial module requirements and approval authority | High | Medium | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, comprehensive training, clear communication
SH-013 | Human Resources Director | Human Resources Director | Operations module requirements and process optimization | High | Medium | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, high quality deliverables, clear communication
SH-014 | HR Director | Human Resources Director | HR module requirements and workforce management | Medium | Medium | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, smooth transition, clear communication
SH-015 | Executive Sponsor | Executive Sponsor | Strategic oversight and executive decision making | High | Medium | Regular engagement, clear communication, involvement in decisions, address concerns proactively | Change champion, advocate, expertise contribution, stakeholder influence | Project benefits, clear requirements, clear communication

## Action Plan
Product Implementation Project - Stakeholder Management Action Plan
Plan Date: July 15, 2025 ¦ Review Frequency: Weekly
Action ID | Stakeholder/Group | Action Description | Objective | Owner | Start Date | Due Date | Status | Progress % | Notes
SH-001 | Product Product Training Manager | Product Implementation Manager | Overall Product project leadership and coordination | High | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-002 | Business Process Owner | Business Process Owner | Business process design and requirements definition | High | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-003 | System Administrator | Product System Administrator | Product system configuration and technical administration | High | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-004 | Data Migration Specialist | Data Migration Lead | Legacy data extraction, transformation, and loading | Medium | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-005 | Training Coordinator | Product Finance Director | End user training program development and delivery | Medium | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-006 | HR Director | Human Resources Director | Organizational change management and user adoption | High | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-007 | Product Vendor Representative | Vendor Implementation Consultant | Product software configuration and best practices guidance | Medium | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-008 | Executive Sponsor | Senior Executive Sponsor | Requirements gathering and process analysis | Medium | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-009 | End User Representative | Super User | End user requirements and testing coordination | Medium | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-010 | Training Coordinator | Training Coordinator | Technical infrastructure and system integration | Medium | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-011 | Quality Assurance Tester | Product QA Specialist | System testing and quality assurance validation | Medium | High | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-012 | Finance Director | Finance Director | Financial module requirements and approval authority | High | Medium | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-013 | Human Resources Director | Human Resources Director | Operations module requirements and process optimization | High | Medium | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-014 | HR Director | Human Resources Director | HR module requirements and workforce management | Medium | Medium | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SH-015 | Executive Sponsor | Executive Sponsor | Strategic oversight and executive decision making | High | Medium | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-016 | Data Migration Specialist | Initial stakeholder meeting and relationship building | Maintain Leading engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-017 | Data Migration Specialist | Regular communication and progress updates | Maintain Leading engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-018 | Data Migration Specialist | Involvement in key project decisions and reviews | Maintain Leading engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-019 | Data Migration Specialist | Training and capability development support | Maintain Leading engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-020 | Data Migration Specialist | Feedback collection and response management | Maintain Leading engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-021 | Training Coordinator | Initial stakeholder meeting and relationship building | Maintain Supportive engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-022 | Training Coordinator | Regular communication and progress updates | Maintain Supportive engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-023 | Training Coordinator | Involvement in key project decisions and reviews | Maintain Supportive engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-024 | Training Coordinator | Training and capability development support | Maintain Supportive engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase
SA-025 | Training Coordinator | Feedback collection and response management | Maintain Supportive engagement level | Product Training Manager | 07/15/2025 | 08/14/2025 | Planned | 0% | Scheduled for project initiation phase