## Training Schedule Overview
BUSINESS PROCESS IMPROVEMENT IMPLEMENTATION PROJECT - TRAINING SCHEDULE
2025 PMI Standards Compliant
Project Name: |  | Enterprise BUSINESS PROCESS IMPROVEMENT Training Schedule |  |  | Project Manager: |  | Michael Chen
Training Manager: |  | Emily Davis, CPTM |  |  | Last Updated: |  | 07/16/2025
TRAINING SCHEDULE SUMMARY
Training Module | Target Audience | Participants | Duration | Start Date | End Date | Delivery Method | Status | Completion %
AI/ML Fundamentals (AI-101) | All Users | 850 | 2 hours | 01/15/2026 | 01/31/2026 | E-learning | Not Started | 0%
AI/ML Platform Overview (AI-102) | All Users | 850 | 2 hours | 02/01/2026 | 02/15/2026 | E-learning | Not Started | 0%
Data Analysis for Business (AI-201) | Business Analysts | 45 | 8 hours | 02/15/2026 | 02/28/2026 | Classroom | Not Started | 0%
Advanced ML Techniques (AI-301) | Data Scientists | 25 | 16 hours | 03/01/2026 | 03/15/2026 | Workshop | Not Started | 0%
MLOps for IT Teams (AI-302) | ML Engineers, IT | 35 | 16 hours | 03/15/2026 | 03/31/2026 | Workshop | Not Started | 0%
Model Validation & QA (AI-303) | ML Engineers, QA | 30 | 8 hours | 04/01/2026 | 04/15/2026 | Workshop | Not Started | 0%
Executive Overview (AI-401) | Leadership | 15 | 4 hours | 04/15/2026 | 04/30/2026 | Classroom | Not Started | 0%
Train-the-Trainer (AI-501) | Super Users | 20 | 40 hours | 05/01/2026 | 05/31/2026 | Workshop | Not Started | 0%
TRAINING SCHEDULE STATISTICS
Metric | Value
Total Training Modules | 8
Total Training Hours | 96
Total Participants (All Modules) | 1870
Modules Complete | 0
Modules In Progress | 0
Modules Not Started | 8
Overall Completion Percentage | 0%

## Detailed Training Schedule
DETAILED TRAINING SCHEDULE
Module ID | Module Name | Target Audience | Session ID | Date | Start Time | End Time | Location | Instructor | Max Capacity | Enrolled | Status
AI-101 | AI/ML Fundamentals | All Users | E-101 | 01/15/2026 | N/A | N/A | Online | Self-paced | 850 | 0 | Not Started
AI-102 | AI/ML Platform Overview | All Users | E-102 | 02/01/2026 | N/A | N/A | Online | Self-paced | 850 | 0 | Not Started
AI-201 | Data Analysis for Business | Business Analysts | C-201-1 | 02/15/2026 | 9:00 AM | 5:00 PM | Training Room A | Emily Davis | 15 | 0 | Not Started
AI-201 | Data Analysis for Business | Business Analysts | C-201-2 | 02/16/2026 | 9:00 AM | 5:00 PM | Training Room A | Emily Davis | 15 | 0 | Not Started
AI-201 | Data Analysis for Business | Business Analysts | C-201-3 | 02/17/2026 | 9:00 AM | 5:00 PM | Training Room A | Emily Davis | 15 | 0 | Not Started
AI-301 | Advanced ML Techniques | Data Scientists | W-301-1 | 03/01/2026 | 9:00 AM | 5:00 PM | Tech Lab | Dr. James Wilson | 15 | 0 | Not Started
AI-301 | Advanced ML Techniques | Data Scientists | W-301-2 | 03/02/2026 | 9:00 AM | 5:00 PM | Tech Lab | Dr. James Wilson | 15 | 0 | Not Started
AI-302 | MLOps for IT Teams | ML Engineers, IT | W-302-1 | 03/15/2026 | 9:00 AM | 5:00 PM | Tech Lab | Sarah Johnson | 15 | 0 | Not Started
AI-302 | MLOps for IT Teams | ML Engineers, IT | W-302-2 | 03/16/2026 | 9:00 AM | 5:00 PM | Tech Lab | Sarah Johnson | 15 | 0 | Not Started
AI-303 | Model Validation & QA | ML Engineers, QA | W-303-1 | 04/01/2026 | 9:00 AM | 5:00 PM | Tech Lab | Dr. James Wilson | 15 | 0 | Not Started
AI-303 | Model Validation & QA | ML Engineers, QA | W-303-2 | 04/02/2026 | 9:00 AM | 5:00 PM | Tech Lab | Dr. James Wilson | 15 | 0 | Not Started
AI-401 | Executive Overview | Leadership | C-401-1 | 04/15/2026 | 1:00 PM | 5:00 PM | Executive Briefing Center | Michael Chen | 15 | 0 | Not Started
AI-501 | Train-the-Trainer | Super Users | W-501-1 | 05/01/2026 | 9:00 AM | 5:00 PM | Training Room B | Emily Davis | 10 | 0 | Not Started
AI-501 | Train-the-Trainer | Super Users | W-501-2 | 05/02/2026 | 9:00 AM | 5:00 PM | Training Room B | Emily Davis | 10 | 0 | Not Started
AI-501 | Train-the-Trainer | Super Users | W-501-3 | 05/03/2026 | 9:00 AM | 5:00 PM | Training Room B | Emily Davis | 10 | 0 | Not Started
AI-501 | Train-the-Trainer | Super Users | W-501-4 | 05/04/2026 | 9:00 AM | 5:00 PM | Training Room B | Emily Davis | 10 | 0 | Not Started
AI-501 | Train-the-Trainer | Super Users | W-501-5 | 05/05/2026 | 9:00 AM | 5:00 PM | Training Room B | Emily Davis | 10 | 0 | Not Started

## Instructor Schedule
INSTRUCTOR SCHEDULE
Instructor Name | Module Name | Session ID | Date | Start Time | End Time | Location
Emily Davis | Data Analysis for Business | C-201-1 | 02/15/2026 | 9:00 AM | 5:00 PM | Training Room A
Emily Davis | Data Analysis for Business | C-201-2 | 02/16/2026 | 9:00 AM | 5:00 PM | Training Room A
Emily Davis | Data Analysis for Business | C-201-3 | 02/17/2026 | 9:00 AM | 5:00 PM | Training Room A
Dr. James Wilson | Advanced ML Techniques | W-301-1 | 03/01/2026 | 9:00 AM | 5:00 PM | Tech Lab
Dr. James Wilson | Advanced ML Techniques | W-301-2 | 03/02/2026 | 9:00 AM | 5:00 PM | Tech Lab
Sarah Johnson | MLOps for IT Teams | W-302-1 | 03/15/2026 | 9:00 AM | 5:00 PM | Tech Lab
Sarah Johnson | MLOps for IT Teams | W-302-2 | 03/16/2026 | 9:00 AM | 5:00 PM | Tech Lab
Dr. James Wilson | Model Validation & QA | W-303-1 | 04/01/2026 | 9:00 AM | 5:00 PM | Tech Lab
Dr. James Wilson | Model Validation & QA | W-303-2 | 04/02/2026 | 9:00 AM | 5:00 PM | Tech Lab
Michael Chen | Executive Overview | C-401-1 | 04/15/2026 | 1:00 PM | 5:00 PM | Executive Briefing Center
Emily Davis | Train-the-Trainer | W-501-1 | 05/01/2026 | 9:00 AM | 5:00 PM | Training Room B
Emily Davis | Train-the-Trainer | W-501-2 | 05/02/2026 | 9:00 AM | 5:00 PM | Training Room B
Emily Davis | Train-the-Trainer | W-501-3 | 05/03/2026 | 9:00 AM | 5:00 PM | Training Room B
Emily Davis | Train-the-Trainer | W-501-4 | 05/04/2026 | 9:00 AM | 5:00 PM | Training Room B
Emily Davis | Train-the-Trainer | W-501-5 | 05/05/2026 | 9:00 AM | 5:00 PM | Training Room B

## Facility Schedule
FACILITY SCHEDULE
Location | Module Name | Session ID | Date | Start Time | End Time | Instructor
Training Room A | Data Analysis for Business | C-201-1 | 02/15/2026 | 9:00 AM | 5:00 PM | Emily Davis
Training Room A | Data Analysis for Business | C-201-2 | 02/16/2026 | 9:00 AM | 5:00 PM | Emily Davis
Training Room A | Data Analysis for Business | C-201-3 | 02/17/2026 | 9:00 AM | 5:00 PM | Emily Davis
Tech Lab | Advanced ML Techniques | W-301-1 | 03/01/2026 | 9:00 AM | 5:00 PM | Dr. James Wilson
Tech Lab | Advanced ML Techniques | W-301-2 | 03/02/2026 | 9:00 AM | 5:00 PM | Dr. James Wilson
Tech Lab | MLOps for IT Teams | W-302-1 | 03/15/2026 | 9:00 AM | 5:00 PM | Sarah Johnson
Tech Lab | MLOps for IT Teams | W-302-2 | 03/16/2026 | 9:00 AM | 5:00 PM | Sarah Johnson
Tech Lab | Model Validation & QA | W-303-1 | 04/01/2026 | 9:00 AM | 5:00 PM | Dr. James Wilson
Tech Lab | Model Validation & QA | W-303-2 | 04/02/2026 | 9:00 AM | 5:00 PM | Dr. James Wilson
Executive Briefing Center | Executive Overview | C-401-1 | 04/15/2026 | 1:00 PM | 5:00 PM | Michael Chen
Training Room B | Train-the-Trainer | W-501-1 | 05/01/2026 | 9:00 AM | 5:00 PM | Emily Davis
Training Room B | Train-the-Trainer | W-501-2 | 05/02/2026 | 9:00 AM | 5:00 PM | Emily Davis
Training Room B | Train-the-Trainer | W-501-3 | 05/03/2026 | 9:00 AM | 5:00 PM | Emily Davis
Training Room B | Train-the-Trainer | W-501-4 | 05/04/2026 | 9:00 AM | 5:00 PM | Emily Davis
Training Room B | Train-the-Trainer | W-501-5 | 05/05/2026 | 9:00 AM | 5:00 PM | Emily Davis

## Participant Tracking
PARTICIPANT TRACKING
Employee ID | First Name | Last Name | Department | Role | Module ID | Session ID | Status
EMP001 | John | Smith | Data Science | Data Scientist | AI-101 | E-101 | Not Started
EMP001 | John | Smith | Data Science | Data Scientist | AI-102 | E-102 | Not Started
EMP001 | John | Smith | Data Science | Data Scientist | AI-301 | W-301-1 | Not Started
EMP001 | John | Smith | Data Science | Data Scientist | AI-302 | W-302-1 | Not Started
EMP002 | Sarah | Johnson | IT | ML Engineer | AI-101 | E-101 | Not Started
EMP002 | Sarah | Johnson | IT | ML Engineer | AI-102 | E-102 | Not Started
EMP002 | Sarah | Johnson | IT | ML Engineer | AI-302 | W-302-1 | Not Started
EMP002 | Sarah | Johnson | IT | ML Engineer | AI-303 | W-303-1 | Not Started
EMP003 | Michael | Chen | Executive | CTO | AI-101 | E-101 | Not Started
EMP003 | Michael | Chen | Executive | CTO | AI-102 | E-102 | Not Started
EMP003 | Michael | Chen | Executive | CTO | AI-401 | C-401-1 | Not Started
EMP004 | Emily | Davis | Training | Training Manager | AI-101 | E-101 | Not Started
EMP004 | Emily | Davis | Training | Training Manager | AI-102 | E-102 | Not Started
EMP004 | Emily | Davis | Training | Training Manager | AI-501 | W-501-1 | Not Started
EMP005 | James | Wilson | Data Science | Lead Data Scientist | AI-101 | E-101 | Not Started
EMP005 | James | Wilson | Data Science | Lead Data Scientist | AI-102 | E-102 | Not Started
EMP005 | James | Wilson | Data Science | Lead Data Scientist | AI-301 | W-301-1 | Not Started
EMP005 | James | Wilson | Data Science | Lead Data Scientist | AI-303 | W-303-1 | Not Started
EMP005 | James | Wilson | Data Science | Lead Data Scientist | AI-501 | W-501-1 | Not Started