## Resource Overview
RESOURCE PLAN & STAFFING PLAN
ERP IMPLEMENTATIONS Resource Plan Project
Generated: July 16, 2025
PROJECT INFORMATION
Project Name: | Enterprise AI/ML Implementation
Project Manager: | Sarah Johnson, PMP
Project Duration: | 18 months
Total Budget: | $2,850,000
Team Size: | 25 resources (peak)
Start Date: | January 1, 2025
End Date: | June 30, 2026
RESOURCE SUMMARY BY CATEGORY
Resource Category | Count | Total Hours | Total Cost | % of Budget | Peak Period | Critical Skills | Risk Level
Project Management | 2 | 3600 | $360,000 | 12.6% | Months 1-18 | PMP, Agile, Leadership | Low
Business Analysis | 3 | 4320 | $432,000 | 15.2% | Months 2-8 | Requirements, Process | Medium
Data Science/AI | 5 | 7200 | $900,000 | 31.6% | Months 4-14 | ML, Python, Statistics | High
Software Development | 4 | 5760 | $576,000 | 20.2% | Months 6-16 | Python, APIs, Cloud | Medium
Data Engineering | 3 | 4320 | $432,000 | 15.2% | Months 3-15 | ETL, Databases, Cloud | High
Quality Assurance | 2 | 2880 | $216,000 | 7.6% | Months 8-17 | Testing, Automation | Low
DevOps/Infrastructure | 2 | 2160 | $270,000 | 9.5% | Months 5-18 | Cloud, CI/CD, Security | Medium
Change Management | 2 | 1800 | $180,000 | 6.3% | Months 10-18 | Training, Communication | Low
Subject Matter Experts | 4 | 1440 | $216,000 | 7.6% | Months 1-18 | Domain Knowledge | Medium
TOTALS | 27 | 33480 | $3,582,000 | 125.7%

## Detailed Staffing Plan
DETAILED STAFFING PLAN
Resource Name | Role | Category | Department | Allocation % | Start Date | End Date | Hourly Rate | Total Hours | Total Cost | Skills Required | Experience Level | Location | Manager | Status | Notes
Sarah Johnson | Project Manager | Project Management | PMO | 100% | 2025-01-01 | 2026-06-30 | $100 | 1800 | $180,000 | PMP, Agile, Leadership | Senior | New York | Director PMO | Confirmed | Lead PM
Mike Chen | Scrum Master | Project Management | PMO | 100% | 2025-01-01 | 2026-06-30 | $90 | 1800 | $162,000 | Scrum, Agile, Facilitation | Mid-Level | New York | Sarah Johnson | Confirmed | Agile Coach
Lisa Wang | Senior Business Analyst | Business Analysis | Business | 100% | 2025-02-01 | 2025-08-31 | $85 | 1440 | $122,400 | Requirements, Process Mapping | Senior | Chicago | Business Director | Confirmed | Lead BA
David Kim | Business Analyst | Business Analysis | Business | 75% | 2025-02-01 | 2025-08-31 | $75 | 1080 | $81,000 | Requirements, Documentation | Mid-Level | Chicago | Lisa Wang | Confirmed
Jennifer Liu | Business Analyst | Business Analysis | Business | 75% | 2025-03-01 | 2025-07-31 | $75 | 900 | $67,500 | Process Analysis, Testing | Mid-Level | Remote | Lisa Wang | Pending
Dr. Alex Rodriguez | Lead Data Scientist | Data Science/AI | Technology | 100% | 2025-04-01 | 2026-02-28 | $150 | 1800 | $270,000 | ML, Deep Learning, Python | Expert | San Francisco | CTO | Confirmed | AI Lead
Priya Patel | Senior Data Scientist | Data Science/AI | Technology | 100% | 2025-04-01 | 2026-02-28 | $130 | 1800 | $234,000 | ML, Statistics, R/Python | Senior | San Francisco | Alex Rodriguez | Confirmed
James Wilson | Data Scientist | Data Science/AI | Technology | 100% | 2025-05-01 | 2026-01-31 | $110 | 1440 | $158,400 | ML, Python, Visualization | Mid-Level | Austin | Alex Rodriguez | Pending
Maria Garcia | ML Engineer | Data Science/AI | Technology | 100% | 2025-06-01 | 2026-02-28 | $120 | 1440 | $172,800 | MLOps, Python, Cloud | Senior | Remote | Alex Rodriguez | Pending
Robert Taylor | Junior Data Scientist | Data Science/AI | Technology | 75% | 2025-07-01 | 2025-12-31 | $85 | 720 | $61,200 | Python, Statistics, SQL | Junior | Austin | Alex Rodriguez | Open | Entry Level
Kevin Zhang | Senior Developer | Software Development | Technology | 100% | 2025-06-01 | 2026-04-30 | $110 | 1800 | $198,000 | Python, APIs, Microservices | Senior | Seattle | Tech Lead | Confirmed | Backend Lead
Amanda Brown | Full Stack Developer | Software Development | Technology | 100% | 2025-06-01 | 2026-04-30 | $95 | 1800 | $171,000 | React, Python, Databases | Mid-Level | Seattle | Kevin Zhang | Confirmed
Carlos Martinez | Frontend Developer | Software Development | Technology | 75% | 2025-08-01 | 2026-03-31 | $85 | 1200 | $102,000 | React, JavaScript, UX | Mid-Level | Remote | Kevin Zhang | Pending
Sophie Anderson | API Developer | Software Development | Technology | 75% | 2025-07-01 | 2026-02-28 | $90 | 960 | $86,400 | REST APIs, Python, Testing | Mid-Level | Seattle | Kevin Zhang | Open
Thomas Lee | Senior Data Engineer | Data Engineering | Technology | 100% | 2025-03-01 | 2026-03-31 | $125 | 2160 | $270,000 | ETL, Spark, Cloud Platforms | Senior | Denver | Data Architect | Confirmed | Data Lead
Rachel Green | Data Engineer | Data Engineering | Technology | 100% | 2025-04-01 | 2026-02-28 | $100 | 1800 | $180,000 | SQL, Python, Data Pipelines | Mid-Level | Denver | Thomas Lee | Confirmed
Daniel Park | Cloud Data Engineer | Data Engineering | Technology | 75% | 2025-05-01 | 2025-12-31 | $105 | 1200 | $126,000 | AWS, Databricks, Kafka | Mid-Level | Remote | Thomas Lee | Pending
Emily Davis | QA Lead | Quality Assurance | Technology | 100% | 2025-08-01 | 2026-05-31 | $95 | 1800 | $171,000 | Test Automation, Selenium | Senior | Boston | QA Manager | Confirmed | QA Lead
Michael Johnson | QA Engineer | Quality Assurance | Technology | 75% | 2025-09-01 | 2026-04-30 | $75 | 1080 | $81,000 | Manual Testing, API Testing | Mid-Level | Boston | Emily Davis | Pending
Chris Wilson | DevOps Engineer | DevOps/Infrastructure | Technology | 100% | 2025-05-01 | 2026-06-30 | $115 | 1440 | $165,600 | AWS, Docker, Kubernetes | Senior | Portland | Infrastructure Lead | Confirmed | DevOps Lead
Jessica Miller | Cloud Engineer | DevOps/Infrastructure | Technology | 75% | 2025-06-01 | 2026-05-31 | $100 | 1080 | $108,000 | Cloud Security, CI/CD | Mid-Level | Portland | Chris Wilson | Pending
Mark Thompson | Change Manager | Change Management | HR | 100% | 2025-10-01 | 2026-06-30 | $90 | 1440 | $129,600 | Change Management, Training | Senior | Atlanta | HR Director | Confirmed | Change Lead
Laura White | Training Specialist | Change Management | HR | 50% | 2025-11-01 | 2026-06-30 | $70 | 720 | $50,400 | Training Design, Facilitation | Mid-Level | Atlanta | Mark Thompson | Pending
Dr. Susan Clark | Business SME | Subject Matter Experts | Business | 25% | 2025-01-01 | 2026-06-30 | $150 | 450 | $67,500 | Domain Expertise, Strategy | Expert | New York | Business Director | Confirmed | Strategy SME
John Martinez | Technical SME | Subject Matter Experts | Technology | 25% | 2025-04-01 | 2026-04-30 | $130 | 390 | $50,700 | Architecture, Integration | Expert | San Francisco | CTO | Confirmed | Tech SME
Patricia Lewis | Data SME | Subject Matter Experts | Business | 20% | 2025-03-01 | 2025-12-31 | $120 | 300 | $36,000 | Data Governance, Quality | Expert | Chicago | Data Director | Confirmed | Data SME
Robert Hall | Security SME | Subject Matter Experts | Technology | 20% | 2025-05-01 | 2026-03-31 | $140 | 300 | $42,000 | Cybersecurity, Compliance | Expert | Remote | CISO | Pending | Security SME

## Resource Timeline
RESOURCE ALLOCATION TIMELINE
Resource Name | Role | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06
Sarah Johnson | Project Manager | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Dr. Alex Rodriguez | Lead Data Scientist |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Kevin Zhang | Senior Developer | [5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Thomas Lee | Senior Data Engineer |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Emily Davis | QA Lead | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Chris Wilson | DevOps Engineer |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Mark Thompson | Change Manager | [9 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
LEGEND:
100% Allocation
75% Allocation
50% Allocation

## Skills Matrix
SKILLS MATRIX & COMPETENCY ASSESSMENT
Resource Name | Role | Python/R | Machine Learning | Data Engineering | Cloud Platforms | Project Management | Business Analysis | Testing/QA | DevOps | Leadership | Communication | Overall Rating
Sarah Johnson | Project Manager | 2 | 2 | 1 | 3 | 5 | 4 | 3 | 2 | 5 | 5 | 4.2
Dr. Alex Rodriguez | Lead Data Scientist | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 2 | 4 | 4 | 4.5
Kevin Zhang | Senior Developer | 5 | 3 | 3 | 4 | 2 | 2 | 4 | 3 | 3 | 4 | 3.8
Thomas Lee | Senior Data Engineer | 4 | 3 | 5 | 5 | 2 | 3 | 3 | 4 | 3 | 4 | 4.1
Emily Davis | QA Lead | 3 | 2 | 2 | 3 | 3 | 3 | 5 | 3 | 4 | 4 | 3.6
Chris Wilson | DevOps Engineer | 4 | 2 | 3 | 5 | 2 | 2 | 4 | 5 | 3 | 3 | 3.9
Mark Thompson | Change Manager | 1 | 1 | 1 | 2 | 4 | 4 | 2 | 1 | 5 | 5 | 3.2
SKILL LEVEL LEGEND:
5 = Expert
4 = Advanced
3 = Intermediate
2 = Basic
1 = Beginner

## Cost Analysis
RESOURCE COST ANALYSIS
Cost Category | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 | Q1 2026 | Q2 2026 | Total Cost | % of Total | Budget Status
Project Management | $90,000 | $90,000 | $90,000 | $90,000 | $90,000 | $90,000 | $540,000 | 15.1% | On Budget
Business Analysis | $108,000 | $162,000 | $162,000 | $0 | $0 | $0 | $432,000 | 12.1% | On Budget
Data Science/AI | $0 | $135,000 | $270,000 | $270,000 | $270,000 | $135,000 | $1,080,000 | 30.1% | On Budget
Software Development | $0 | $0 | $144,000 | $216,000 | $216,000 | $144,000 | $720,000 | 20.1% | On Budget
Data Engineering | $90,000 | $135,000 | $180,000 | $180,000 | $135,000 | $90,000 | $810,000 | 22.6% | On Budget
Quality Assurance | $0 | $0 | $54,000 | $81,000 | $81,000 | $54,000 | $270,000 | 7.5% | On Budget
DevOps/Infrastructure | $0 | $67,500 | $90,000 | $90,000 | $90,000 | $90,000 | $427,500 | 11.9% | On Budget
Change Management | $0 | $0 | $0 | $45,000 | $67,500 | $67,500 | $180,000 | 5.0% | On Budget
Subject Matter Experts | $54,000 | $54,000 | $54,000 | $54,000 | $54,000 | $54,000 | $324,000 | 9.0% | On Budget
TOTALS | $342,000 | $643,500 | $1,044,000 | $1,026,000 | $1,003,500 | $724,500 | $4,783,500 | 133.4%
BUDGET VARIANCE ANALYSIS
Approved Budget: | $3,600,000
Planned Cost: | $4,783,500
Variance: | $1,183,500
Variance %: | 32.9% Over
Risk Level: | High - Requires Mitigation

## Resource Risk Assessment
RESOURCE RISK ASSESSMENT
Risk Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Owner | Status
Availability | Key data scientists not available when needed | Medium | High | 6 | Backup resources identified | Sarah Johnson | Active
Skills Gap | Team lacks required ML expertise | Low | High | 4 | Training and external consultants | Alex Rodriguez | Mitigated
Retention | High-demand skills may leave project | Medium | Medium | 4 | Competitive compensation, engagement | HR Manager | Active
Budget | Resource costs exceed approved budget | High | High | 9 | Cost optimization, scope adjustment | Sarah Johnson | Critical
Timeline | Resource ramp-up delays project timeline | Medium | Medium | 4 | Early recruitment, overlap planning | Sarah Johnson | Active
Location | Remote work impacts collaboration | Low | Low | 2 | Collaboration tools, regular meetings | Team Leads | Mitigated
Dependencies | External SMEs not available | Medium | Medium | 4 | Alternative experts identified | Sarah Johnson | Active
Quality | Insufficient QA resources for quality | Low | High | 4 | Additional QA resources, automation | Emily Davis | Mitigated
RISK SCORE LEGEND:
8-9 = Critical Risk
6-7 = High Risk
4-5 = Medium Risk
1-3 = Low Risk