## Assessment Overview
TRAINING NEEDS ASSESSMENT
HEALTHCARE Data Readiness Assessment Project
Generated: July 16, 2025
ASSESSMENT INFORMATION
Project Name: | Enterprise AI/ML Implementation
Assessment Lead: | Emily Davis, CPTM
Assessment Period: | October 15 - December 15, 2025
Assessment Methods: | Surveys, Interviews, Focus Groups, Skills Tests
Target Population: | 850 employees across 5 departments
Assessment Scope: | Technical skills, Business knowledge, Process understanding
Assessment Objectives: | Identify skill gaps, Define training requirements, Establish baseline
ASSESSMENT METHODOLOGY
• Online Skills Survey: Self-assessment of current skills and experience
• Technical Skills Assessment: Hands-on evaluation of technical capabilities
• Stakeholder Interviews: One-on-one discussions with key stakeholders
• Focus Groups: Department-level discussions on training needs
• Job Task Analysis: Review of job roles and required competencies
• Organizational Readiness Assessment: Evaluation of organizational factors
KEY FINDINGS SUMMARY
• 85% of users have no prior experience with AI/ML technologies
• Technical teams require advanced training in MLOps and model deployment
• Business users need focus on data interpretation and insights application
• Executive team requires strategic overview and dashboard interpretation
• Significant knowledge gap in AI ethics and responsible AI practices
• Strong interest in hands-on, practical training approaches
RECOMMENDATIONS
• Develop role-based training curriculum with tailored content
• Implement blended learning approach (e-learning + instructor-led)
• Create AI/ML fundamentals course for all employees
• Develop advanced technical tracks for IT and data science teams
• Establish executive briefing program for leadership
• Implement hands-on labs and practical exercises
• Develop AI ethics and responsible AI module for all users

## Skills Assessment
SKILLS ASSESSMENT MATRIX
Role/Position | Department | Population | Skill Category | Skill Name | Current Level | Required Level | Gap | Priority | Training Approach | Notes
Data Scientist | Analytics | 25 | ML Modeling | Feature Engineering | 3 | 5 |  | High | Technical workshop | Advanced techniques needed
Data Scientist | Analytics | 25 | ML Modeling | Model Selection | 4 | 5 |  | Medium | Technical workshop | Focus on latest algorithms
Data Scientist | Analytics | 25 | MLOps | Model Deployment | 2 | 4 |  | Critical | Hands-on lab | Significant gap identified
Data Scientist | Analytics | 25 | MLOps | Model Monitoring | 2 | 4 |  | High | Technical workshop | Production monitoring focus
Data Scientist | Analytics | 25 | Data | Data Preparation | 4 | 5 |  | Low | Self-paced | Minor refinement needed
ML Engineer | Engineering | 15 | MLOps | CI/CD for ML | 2 | 5 |  | Critical | Technical workshop | Major capability gap
ML Engineer | Engineering | 15 | MLOps | Model Serving | 3 | 5 |  | High | Hands-on lab | Production focus needed
ML Engineer | Engineering | 15 | Infrastructure | Kubernetes | 2 | 4 |  | High | Technical workshop | Container orchestration
ML Engineer | Engineering | 15 | Infrastructure | Cloud Services | 3 | 4 |  | Medium | Hands-on lab | Focus on specific services
ML Engineer | Engineering | 15 | Programming | Python | 4 | 5 |  | Low | Self-paced | Advanced techniques only
Business Analyst | Business | 45 | AI Concepts | ML Fundamentals | 1 | 3 |  | High | Classroom | Basic understanding needed
Business Analyst | Business | 45 | Data | Data Interpretation | 2 | 4 |  | Critical | Hands-on lab | Core job requirement
Business Analyst | Business | 45 | Visualization | Dashboard Usage | 2 | 4 |  | High | Hands-on lab | Daily operational need
Business Analyst | Business | 45 | Business | Use Case Development | 2 | 4 |  | Medium | Workshop | Strategic importance
Business Analyst | Business | 45 | Ethics | Responsible AI | 1 | 3 |  | Medium | E-learning | Compliance requirement
IT Operations | Technology | 35 | MLOps | Platform Administration | 1 | 4 |  | Critical | Technical workshop | Core support function
IT Operations | Technology | 35 | MLOps | Monitoring | 2 | 4 |  | High | Hands-on lab | 24/7 support requirement
IT Operations | Technology | 35 | Security | ML Security | 1 | 4 |  | Critical | Technical workshop | Security vulnerabilities
IT Operations | Technology | 35 | Infrastructure | Scaling | 3 | 4 |  | Medium | Technical workshop | Performance optimization
IT Operations | Technology | 35 | Troubleshooting | Model Debugging | 1 | 3 |  | High | Hands-on lab | Support requirement
Executive | Leadership | 15 | Strategy | AI Strategy | 2 | 4 |  | High | Executive briefing | Strategic decision making
Executive | Leadership | 15 | Business | ROI Analysis | 3 | 4 |  | Medium | Executive briefing | Investment decisions
Executive | Leadership | 15 | Reporting | KPI Monitoring | 2 | 4 |  | High | Hands-on demo | Performance tracking
Executive | Leadership | 15 | Ethics | AI Governance | 2 | 4 |  | Critical | Executive briefing | Regulatory requirement
Executive | Leadership | 15 | AI Concepts | AI Capabilities | 2 | 3 |  | Medium | Executive briefing | Strategic understanding
End User | Various | 730 | AI Concepts | AI Fundamentals | 1 | 2 |  | Medium | E-learning | Basic awareness
End User | Various | 730 | System | Navigation | 0 | 3 |  | Critical | Hands-on lab | Daily usage requirement
End User | Various | 730 | System | Data Input | 0 | 3 |  | Critical | Hands-on lab | Data quality critical
End User | Various | 730 | System | Report Generation | 0 | 3 |  | High | Hands-on lab | Regular reporting need
End User | Various | 730 | Ethics | Responsible Use | 0 | 2 |  | High | E-learning | Compliance requirement

## Organizational Readiness
ORGANIZATIONAL READINESS ASSESSMENT
Assessment Area | Current State | Desired State | Gap | Impact | Recommendations | Priority
Leadership Support | Moderate support with limited understanding | Active championing with clear understanding | Leadership education needed | High | Executive AI briefing program | Critical
Technical Infrastructure | Basic cloud infrastructure in place | Scalable ML-optimized infrastructure | Infrastructure upgrades required | High | Cloud infrastructure enhancement project | High
Data Readiness | Siloed data with quality issues | Integrated, high-quality data lake | Data integration and cleaning | Critical | Data quality initiative | Critical
Skills Availability | Limited AI/ML expertise | Sufficient expertise across key roles | Significant upskilling required | High | Comprehensive training program | Critical
Process Maturity | Ad-hoc processes | Standardized ML lifecycle processes | Process definition and implementation | Medium | MLOps process development | High
Change Readiness | Moderate resistance expected | Enthusiastic adoption | Change management program | High | Robust change management plan | High
Budget Allocation | Initial budget approved | Fully funded implementation | Additional funding may be needed | Medium | Phased funding approach | Medium
Governance Structure | Limited governance | Comprehensive AI governance framework | Governance framework development | High | AI governance committee | High
Tool Availability | Basic development tools | Complete ML development ecosystem | Tool acquisition and integration | Medium | Tool procurement plan | Medium
Knowledge Management | Limited documentation | Comprehensive knowledge base | Knowledge management system | Medium | Knowledge base development | Medium
Regulatory Compliance | Basic compliance understanding | Comprehensive compliance framework | Compliance program development | Critical | AI compliance initiative | Critical
User Readiness | Limited awareness | High awareness and readiness | Awareness and training program | High | User awareness campaign | High

## Training Requirements
TRAINING REQUIREMENTS
Requirement ID | Requirement Category | Requirement Description | Target Audience | Priority | Source | Acceptance Criteria | Notes
TR-001 | Content | AI/ML fundamentals course covering basic concepts, terminology, and use cases | All Users | High | Skills Assessment | 90% of users complete with 80% pass rate | Foundation for all other training
TR-002 | Content | Role-based technical training for data scientists and ML engineers | Technical Teams | Critical | Skills Assessment | 100% of technical staff certified | Core technical capability
TR-003 | Content | Business-focused AI/ML training for analysts and business users | Business Teams | High | Skills Assessment | 85% of business users proficient | Focus on practical application
TR-004 | Content | Executive AI briefing program | Leadership | High | Organizational Readiness | All executives complete briefing | Strategic alignment
TR-005 | Content | AI ethics and responsible AI training | All Users | High | Regulatory Requirements | 100% completion rate | Compliance requirement
TR-006 | Content | MLOps training for IT and operations teams | IT Operations | Critical | Skills Assessment | IT team certified on platform | Operational support
TR-007 | Content | System navigation and basic functions training | End Users | Critical | Skills Assessment | Users demonstrate proficiency | Daily usage requirement
TR-008 | Content | Advanced analytics and reporting training | Analysts | Medium | Skills Assessment | Analysts create custom reports | Advanced capability
TR-009 | Content | AI governance and compliance training | Leadership, Compliance | High | Regulatory Requirements | Governance framework implemented | Regulatory requirement
TR-010 | Content | Data quality and preparation training | Data Teams | High | Skills Assessment | Data quality metrics improved | Foundation for model accuracy
TR-011 | Delivery | Blended learning approach combining e-learning and instructor-led | All Users | High | Focus Groups | Learning effectiveness metrics | Optimized learning approach
TR-012 | Delivery | Hands-on labs and practical exercises | Technical Teams | Critical | Skills Assessment | Practical skills demonstration | Applied learning
TR-013 | Delivery | Just-in-time training delivery | All Users | Medium | Best Practices | Knowledge retention metrics | Timing optimization
TR-014 | Delivery | Mobile-accessible training content | All Users | Medium | User Feedback | Mobile usage metrics | Flexibility for users
TR-015 | Delivery | Train-the-trainer program | Super Users | High | Organizational Readiness | Internal trainers certified | Sustainable capability
TR-016 | Infrastructure | Learning Management System (LMS) configuration | Training Team | High | Technical Requirements | LMS fully operational | Training delivery platform
TR-017 | Infrastructure | Training environment/sandbox system | All Users | Critical | Technical Requirements | Sandbox matches production | Hands-on practice
TR-018 | Infrastructure | Training materials development platform | Training Team | Medium | Technical Requirements | Materials development workflow | Content creation
TR-019 | Evaluation | Skills assessment and certification process | All Users | High | Best Practices | Certification process established | Competency validation
TR-020 | Evaluation | Training effectiveness measurement | Training Team | Medium | Best Practices | Effectiveness metrics defined | Continuous improvement

## Assessment Methods
ASSESSMENT METHODS
Method | Description | Target Audience | Sample Size | Timeline | Responsible | Status
Online Skills Survey | Self-assessment questionnaire covering technical and business skills | All Users | 100% (850) | Oct 15-30, 2025 | Emily Davis | Complete
Technical Skills Assessment | Hands-on technical evaluation for technical roles | Technical Teams | 100% (75) | Nov 1-15, 2025 | Alex Rodriguez | In Progress
Stakeholder Interviews | One-on-one interviews with key stakeholders | Leadership, Key Users | 25 | Oct 20-Nov 10, 2025 | Emily Davis | In Progress
Focus Groups | Department-level discussions on training needs | Department Reps | 10 sessions (50 total) | Nov 5-20, 2025 | Mark Thompson | Scheduled
Job Task Analysis | Detailed analysis of job roles and required competencies | Selected Roles | 12 roles | Oct 25-Nov 30, 2025 | Lisa Wang | In Progress
Organizational Readiness Survey | Assessment of organizational factors affecting implementation | Leadership, Managers | 65 | Nov 1-15, 2025 | John Smith | Scheduled
System Usage Observation | Direct observation of current system usage | Selected End Users | 30 | Nov 10-25, 2025 | Robert Taylor | Scheduled
Documentation Review | Review of existing documentation and training materials | N/A | All available docs | Oct 15-30, 2025 | Jennifer Liu | Complete
Competitor/Industry Analysis | Review of industry standards and best practices | N/A | 5 competitors | Oct 15-Nov 15, 2025 | Sarah Brown | In Progress
Training Pilot Testing | Pilot testing of sample training materials | Mixed Sample | 25 | Dec 1-15, 2025 | Emily Davis | Planned