## Open Action Items
REGULATORY COMPLIANCE AND GOVERNANCE - OPEN ACTION ITEM LOG
Project: Regulatory Compliance
Date: July 31, 2025
PMI 2025 Standards Compliant
ACTION ITEM TRACKING
Action_ID | Action_Description | Priority | Status | Owner | Due_Date | Completion_Date | Progress_% | Dependencies | Notes
AI001 | Establish ongoing regulatory interpretation and legal consultation | High | In Progress | Compliance Officers | 2025-08-30 |  | 25 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI002 | Implement real-time compliance monitoring and alerting systems | High | In Progress | Legal Teams | 2025-09-04 |  | 32 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI003 | Create documentation standards aligned with regulatory requirements | High | In Progress | Auditors | 2025-09-09 |  | 39 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI004 | Develop continuous audit preparation and evidence collection procedures | High | In Progress | Risk Managers | 2025-09-14 |  | 46 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI005 | Execute organization-wide compliance awareness and communication | Medium | In Progress | Business Units | 2025-09-19 |  | 53 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI006 | Deploy role-specific compliance training and certification programs | Medium | In Progress | Regulatory Bodies | 2025-09-24 |  | 60 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI007 | Implement regular risk assessment review and calibration procedures | Medium | Not Started | Compliance Officers | 2025-09-29 |  | 67 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI008 | Complete vendor compliance validation and ongoing monitoring | Medium | Not Started | Legal Teams | 2025-10-04 |  | 74 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI009 | Establish international regulation alignment and expertise consultation | Low | Not Started | Auditors | 2025-10-09 |  | 81 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success
AI010 | Create executive compliance reporting and accountability framework | Low | Completed | Risk Managers | 2025-10-14 | 2025-07-31 | 100 | Dependent on Regulatory Compliance milestone completion | Critical action for Regulatory Compliance and Governance success