## WBS
WBS Code | Task Name | Level | Duration (Days) | Start Date | End Date | Effort (Hours) | Cost ($) | Resource | Status | % Complete | Predecessor | Notes
1.0 | Project Initiation | 1 | 10 | 2024-01-01 |  | 80 | 8000 | PM Team | Not Started | 0 |  | Phase 1
1.1 | Project Charter Development | 2 | 3 | 2024-01-01 |  | 24 | 2400 | Project Manager | Not Started | 0
1.2 | Stakeholder Identification | 2 | 2 | 2024-01-04 |  | 16 | 1600 | Business Analyst | Not Started | 0 | 1.1
1.3 | Initial Risk Assessment | 2 | 3 | 2024-01-06 |  | 24 | 2400 | Risk Manager | Not Started | 0 | 1.2
1.4 | Project Kickoff Meeting | 2 | 1 | 2024-01-09 |  | 8 | 800 | PM Team | Not Started | 0 | 1.3
1.5 | Project Plan Approval | 2 | 1 | 2024-01-10 |  | 8 | 800 | Sponsor | Not Started | 0 | 1.4
2.0 | Planning Phase | 1 | 15 | 2024-01-11 |  | 120 | 12000 | PM Team | Not Started | 0 | 1.0 | Phase 2
2.1 | Detailed Project Planning | 2 | 5 | 2024-01-11 |  | 40 | 4000 | Project Manager | Not Started | 0 | 1.5
2.2 | Resource Planning | 2 | 3 | 2024-01-16 |  | 24 | 2400 | Resource Manager | Not Started | 0 | 2.1
2.3 | Budget Planning | 2 | 3 | 2024-01-19 |  | 24 | 2400 | Finance Team | Not Started | 0 | 2.2
2.4 | Quality Planning | 2 | 2 | 2024-01-22 |  | 16 | 1600 | QA Manager | Not Started | 0 | 2.3
2.5 | Communication Planning | 2 | 2 | 2024-01-24 |  | 16 | 1600 | Communications Lead | Not Started | 0 | 2.4
3.0 | Execution Phase | 1 | 30 | 2024-01-26 |  | 240 | 24000 | Development Team | Not Started | 0 | 2.0 | Phase 3
3.1 | System Design | 2 | 8 | 2024-01-26 |  | 64 | 6400 | System Architect | Not Started | 0 | 2.5
3.2 | Development | 2 | 15 | 2024-02-03 |  | 120 | 12000 | Developers | Not Started | 0 | 3.1
3.3 | Testing | 2 | 5 | 2024-02-18 |  | 40 | 4000 | QA Team | Not Started | 0 | 3.2
3.4 | User Acceptance Testing | 2 | 2 | 2024-02-23 |  | 16 | 1600 | End Users | Not Started | 0 | 3.3
4.0 | Closure Phase | 1 | 5 | 2024-02-25 |  | 40 | 4000 | PM Team | Not Started | 0 | 3.0 | Phase 4
4.1 | Project Documentation | 2 | 2 | 2024-02-25 |  | 16 | 1600 | Technical Writer | Not Started | 0 | 3.4
4.2 | Lessons Learned | 2 | 1 | 2024-02-27 |  | 8 | 800 | PM Team | Not Started | 0 | 4.1
4.3 | Project Closure | 2 | 2 | 2024-02-28 |  | 16 | 1600 | Project Manager | Not Started | 0 | 4.2
PROJECT SUMMARY
Total Tasks:
Total Duration (Days):
Total Effort (Hours):
Total Cost ($):
Overall Progress (%):
Completed Tasks:
In Progress Tasks:

## Instructions
WORK BREAKDOWN STRUCTURE (WBS) INSTRUCTIONS
1. WBS CODE:
Use hierarchical numbering (1.0, 1.1, 1.2, 2.0, etc.)
2. TASK LEVELS:
Level 1: Major phases/deliverables
Level 2: Sub-tasks within phases
Level 3+: Detailed work packages
3. DURATION:
Enter in working days
4. DATES:
End Date automatically calculated from Start Date + Duration
5. EFFORT:
Total hours required for the task
6. COST:
Total cost for the task (labor + materials)
7. PREDECESSOR:
WBS Code of task that must complete before this task starts
8. STATUS OPTIONS:
Not Started, In Progress, Completed, On Hold, Cancelled
9. % COMPLETE:
Enter percentage (0-100) of task completion