## Instructions & User Guide
FINANCE - CORE BANKING SYSTEM MODERNIZATION
Action Item Log
PMI 2025 Standards Compliant
DOCUMENT OVERVIEW
This template tracks all action items, decisions, and follow-ups throughout the Core Banking System Modernization project. It ensures accountability and timely completion of tasks.
KEY FEATURES
• Track action items with owners and due dates
• Priority and status tracking
• Automated aging calculations
• PMI 2025 compliant structure
HOW TO USE THIS TEMPLATE
1. Review all tabs to understand the template structure
2. Fill in the yellow highlighted cells with your project-specific information
3. Do not modify formulas or calculated fields
4. Use dropdown menus where provided for consistency
5. Save regularly and maintain version control
6. Export to PDF for stakeholder distribution

## Action Item Log
FINANCE - CORE BANKING SYSTEM MODERNIZATION
Action_ID | Action_Item | Category | Priority | Owner | Due_Date | Status | Completion_% | Notes | Date_Closed
AI-001 | Complete system requirements documentation | Requirements | High | Business Analyst | 2025-08-15 | In Progress | 75 | On track
AI-002 | Finalize vendor contract terms | Procurement | High | Procurement Manager | 2025-08-10 | Completed | 100 | Contract signed | 2025-08-08
AI-003 | Conduct stakeholder kickoff meeting | Communication | High | Project Manager | 2025-08-05 | Completed | 100 | Meeting held successfully | 2025-08-05
AI-004 | Setup development environment | Technical | Medium | Technical Lead | 2025-08-20 | Not Started | 0 | Waiting for infrastructure
AI-005 | Create training materials outline | Training | Medium | Training Manager | 2025-08-25 | In Progress | 30 | Draft in progress