## Formula Documentation
Finance IMPLEMENTATION WBS - COMPREHENSIVE PROJECT PLAN
PROJECT OVERVIEW:
This Finance Implementation WBS contains 11 comprehensive phases with 150+ detailed tasks,
meeting workflows, budget management, steady-state support, and professional formatting.
PHASES INCLUDED:
1. AI Project Initiation - Charter development, stakeholder management, initial planning
2. AI Budget Planning and Management - Cost estimation, budget controls, tracking
3. AI Solution Design - Requirements analysis, architecture design, documentation
4. AI Compliance and Finance - Ethics review, GDPR compliance, regulatory approvals
5. AI Procurement and Contracting - Vendor selection, infrastructure procurement
6. AI Development and Implementation - Data preparation, model development, integration
7. AI Testing and Validation - Model testing, UAT, security testing, performance validation
8. AI Documentation and Training - Technical documentation, user training, knowledge transfer
9. AI Walkthrough and Handover - Pre-deployment, go-live activities, system handover
10. AI Project Close-out - Administrative closure, lessons learned, final reporting
11. AI Steady-State Support - Warranty period, performance monitoring, ongoing support
COLUMN REFERENCE GUIDE:
A - ID: Unique task identifier
B - WBS_Code: Work Breakdown Structure code
C - Task_Name: Task name with integrated deliverables
D - Task_Type: Phase, Task, Sub-Task, or Milestone
E - Percent_Complete: Task completion percentage (0-100%)
F - Duration: Task duration in days
G - Start_Date: Task start date
H - Finish_Date: Task finish date
I - Predecessors: Tasks that must complete before this task
J - Successors: Tasks that follow this task
K - Resources: Assigned resources
L - Baseline_Start_Date: Original planned start date
M - Baseline_Finish_Date: Original planned finish date
N - Baseline_Duration: Original planned duration
O - Duration_Variance: Actual duration - baseline duration
P - Schedule_Variance: Finish date - baseline finish date
Q - Status: Task status (dropdown)
R - Risk_Level: Risk assessment (Low/Medium/High)
S - Notes: Additional task notes
FORMULAS USED:
Duration Calculation: =H2-G2+1 (Finish Date - Start Date + 1)
Duration Variance: =F2-N2 (Actual Duration - Baseline Duration)
Schedule Variance: =H2-M2 (Finish Date - Baseline Finish Date)
Phase Completion: =AVERAGEIFS(E:E,B:B,"1.*",D:D,"Task")
Milestone Completion: =AVERAGEIFS(E:E,D:D,"Milestone",E:E,">0")
Overall Project: =AVERAGE(Phase_Avg,Milestone_Avg)
STATUS OPTIONS:
- Not Started: Task has not begun
- On Time: Task is progressing as scheduled
- In Progress: Task is currently being worked on
- Complete: Task has been finished
- Delayed: Task is behind schedule
COLOR CODING SYSTEM:
- Blue Background: Phase headers
- Orange Background: Milestones
- Light Blue: Tasks
- Very Light Blue: Sub-tasks
- Green Background: Summary calculations
Finance SPECIFIC FEATURES:
- Data quality and governance workflows
- Model development and validation processes
- Ethics and bias review procedures
- MLOps integration and deployment
- Performance monitoring and model drift detection
- Finance compliance (GDPR, AI Act)
- Stakeholder training on AI systems
CRITICAL SUCCESS FACTORS:
- Data quality and availability
- Stakeholder buy-in and training
- Technical infrastructure readiness
- Model performance validation
- Ethical AI implementation
- Change management and adoption
PMI 2025 COMPLIANCE:
This WBS follows PMI 2025 standards for project management
including proper work breakdown structure, risk management,
stakeholder engagement, and quality assurance processes.

## AI_ML_Implementation_WBS
ID | WBS_Code | Task_Name | Task_Type | Percent_Complete | Duration | Start_Date | Finish_Date | Predecessors | Successors | Resources | Baseline_Start_Date | Baseline_Finish_Date | Baseline_Duration | Duration_Variance | Schedule_Variance | Status | Risk_Level | Notes
1 | 1.0 | AI Project Initiation [Deliverable: Project Initiation Report] | Phase |  |  | 2025-01-01 | 2025-01-20 |  | 18 | Project Manager | 2025-01-01 | 2025-01-20 |  |  |  | In Progress | Medium | Project initiation phase
2 | 1.1 | AI Project Charter Development [Deliverable: Signed Project Charter] | Task | 75% |  | 2025-01-01 | 2025-01-05 |  | 7 | Project Manager | 2025-01-01 | 2025-01-05 |  |  |  | In Progress | Low | Charter development
3 | 1.1.1 | Business Case Analysis [Deliverable: Business Case Document] | Sub-Task | 100% |  | 2025-01-01 | 2025-01-02 |  | 4 | Business Analyst | 2025-01-01 | 2025-01-02 |  |  |  | Complete | Low | Business case complete
4 | 1.1.2 | AI Use Case Definition [Deliverable: Use Case Specifications] | Sub-Task | 75% |  | 2025-01-02 | 2025-01-03 | 3 | 5 | AI Architect | 2025-01-02 | 2025-01-03 |  |  |  | In Progress | Medium | Use cases defined
5 | 1.1.3 | Scope Definition and Objectives [Deliverable: Project Scope Document] | Sub-Task | 50% |  | 2025-01-03 | 2025-01-05 | 4 | 6 | Project Manager | 2025-01-03 | 2025-01-05 |  |  |  | In Progress | Medium | Scope being defined
6 | 1.1.4 | Charter Review Meeting [Deliverable: Meeting Minutes & Approval] | Sub-Task | 25% |  | 2025-01-05 | 2025-01-05 | 5 | 7 | Stakeholders | 2025-01-05 | 2025-01-05 |  |  |  | Not Started | Low | Charter review pending
7 | 1.2 | AI Stakeholder Management [Deliverable: Stakeholder Management Plan] | Task | 50% |  | 2025-01-06 | 2025-01-13 | 6 | 12 | Project Manager | 2025-01-06 | 2025-01-13 |  |  |  | In Progress | Medium | Stakeholder engagement
8 | 1.2.1 | Stakeholder Identification [Deliverable: Stakeholder Register] | Sub-Task | 75% |  | 2025-01-06 | 2025-01-07 | 6 | 9 | Project Manager | 2025-01-06 | 2025-01-07 |  |  |  | In Progress | Low | Stakeholders identified
9 | 1.2.2 | Stakeholder Analysis [Deliverable: Stakeholder Analysis Matrix] | Sub-Task | 50% |  | 2025-01-07 | 2025-01-08 | 8 | 10 | Business Analyst | 2025-01-07 | 2025-01-08 |  |  |  | In Progress | Medium | Analysis in progress
10 | 1.2.3 | Engagement Plan Development [Deliverable: Engagement Strategy] | Sub-Task | 25% |  | 2025-01-08 | 2025-01-09 | 9 | 11 | Communications Lead | 2025-01-08 | 2025-01-09 |  |  |  | Not Started | Medium | Plan development
11 | 1.2.4 | Stakeholder Kickoff Meeting [Deliverable: Kickoff Meeting Minutes] | Sub-Task | 0% |  | 2025-01-10 | 2025-01-11 | 10 | 12 | All Stakeholders | 2025-01-10 | 2025-01-11 |  |  |  | Not Started | Low | Kickoff pending
12 | 1.3 | AI Initial Planning [Deliverable: Initial Project Plan] | Task | 25% |  | 2025-01-14 | 2025-01-20 | 11 | 17 | Project Manager | 2025-01-14 | 2025-01-20 |  |  |  | In Progress | Medium | Initial planning
13 | 1.3.1 | Risk Assessment [Deliverable: Risk Register] | Sub-Task | 50% |  | 2025-01-14 | 2025-01-15 | 11 | 14 | Risk Manager | 2025-01-14 | 2025-01-15 |  |  |  | In Progress | High | Risk assessment
14 | 1.3.2 | Resource Planning [Deliverable: Resource Allocation Plan] | Sub-Task | 25% |  | 2025-01-15 | 2025-01-16 | 13 | 15 | Resource Manager | 2025-01-15 | 2025-01-16 |  |  |  | Not Started | Medium | Resource planning
15 | 1.3.3 | Communication Plan [Deliverable: Communication Strategy] | Sub-Task | 0% |  | 2025-01-16 | 2025-01-17 | 14 | 16 | Communications Lead | 2025-01-16 | 2025-01-17 |  |  |  | Not Started | Low | Communication plan
16 | 1.3.4 | Quality Management Plan [Deliverable: Quality Assurance Plan] | Sub-Task | 0% |  | 2025-01-17 | 2025-01-17 | 15 | 17 | Quality Manager | 2025-01-17 | 2025-01-17 |  |  |  | Not Started | Medium | Quality planning
17 | 1.4 | AI Project Initiation Approval [Deliverable: Signed Initiation Approval] | Milestone | 0% |  | 2025-01-20 | 2025-01-20 | 16 | 18 | Sponsor | 2025-01-20 | 2025-01-20 |  |  |  | Not Started | Low | Approval milestone
18 | 2.0 | AI Budget Planning and Management [Deliverable: Budget Management Report] | Phase |  |  | 2025-01-21 | 2025-02-04 | 17 | 29 | Finance Manager | 2025-01-21 | 2025-02-04 |  |  |  | In Progress | Medium | Budget planning phase
19 | 2.1 | AI Budget Development [Deliverable: Approved Budget Plan] | Task | 60% |  | 2025-01-21 | 2025-01-28 | 17 | 24 | Finance Manager | 2025-01-21 | 2025-01-28 |  |  |  | In Progress | Medium | Budget development
20 | 2.1.1 | Cost Estimation [Deliverable: Cost Estimation Report] | Sub-Task | 75% |  | 2025-01-21 | 2025-01-23 | 17 | 21 | Cost Analyst | 2025-01-21 | 2025-01-23 |  |  |  | In Progress | Medium | Cost estimation
21 | 2.1.2 | Infrastructure Cost Analysis [Deliverable: Infrastructure Cost Report] | Sub-Task | 50% |  | 2025-01-23 | 2025-01-24 | 20 | 22 | Infrastructure Lead | 2025-01-23 | 2025-01-24 |  |  |  | In Progress | High | Infrastructure costs
22 | 2.1.3 | AI Tools and Licensing Costs [Deliverable: Licensing Cost Analysis] | Sub-Task | 25% |  | 2025-01-24 | 2025-01-25 | 21 | 23 | Procurement Lead | 2025-01-24 | 2025-01-25 |  |  |  | Not Started | Medium | Licensing costs
23 | 2.1.4 | Budget Review Meeting [Deliverable: Budget Review Minutes] | Sub-Task | 0% |  | 2025-01-25 | 2025-01-25 | 22 | 24 | Finance Team | 2025-01-25 | 2025-01-25 |  |  |  | Not Started | Low | Budget review
24 | 2.2 | AI Budget Control and Tracking [Deliverable: Budget Control System] | Task | 20% |  | 2025-01-29 | 2025-02-04 | 23 | 28 | Finance Manager | 2025-01-29 | 2025-02-04 |  |  |  | In Progress | Medium | Budget control
25 | 2.2.1 | Budget Baseline Establishment [Deliverable: Budget Baseline Document] | Sub-Task | 50% |  | 2025-01-29 | 2025-01-30 | 23 | 26 | Finance Analyst | 2025-01-29 | 2025-01-30 |  |  |  | In Progress | Low | Baseline setup
26 | 2.2.2 | Budget Monitoring Procedures [Deliverable: Monitoring Procedures Manual] | Sub-Task | 25% |  | 2025-01-30 | 2025-01-31 | 25 | 27 | Finance Manager | 2025-01-30 | 2025-01-31 |  |  |  | Not Started | Medium | Monitoring procedures
27 | 2.2.3 | Change Control Process [Deliverable: Change Control Procedures] | Sub-Task | 0% |  | 2025-01-31 | 2025-02-01 | 26 | 28 | Change Manager | 2025-01-31 | 2025-02-01 |  |  |  | Not Started | Medium | Change control
28 | 2.3 | AI Budget Management Approval [Deliverable: Budget Management Approval] | Milestone | 0% |  | 2025-02-04 | 2025-02-04 | 27 | 29 | Finance Director | 2025-02-04 | 2025-02-04 |  |  |  | Not Started | Low | Budget approval milestone
29 | 3.0 | AI Solution Design [Deliverable: AI Solution Design Document] | Phase |  |  | 2025-02-05 | 2025-02-22 | 28 | 43 | AI Architect | 2025-02-05 | 2025-02-22 |  |  |  | In Progress | High | Solution design phase
30 | 3.1 | AI Requirements Analysis [Deliverable: Requirements Specification] | Task | 60% |  | 2025-02-05 | 2025-02-10 | 28 | 34 | Business Analyst | 2025-02-05 | 2025-02-10 |  |  |  | In Progress | Medium | Requirements analysis
31 | 3.1.1 | Functional Requirements [Deliverable: Functional Requirements Document] | Sub-Task | 75% |  | 2025-02-05 | 2025-02-06 | 28 | 32 | Business Analyst | 2025-02-05 | 2025-02-06 |  |  |  | In Progress | Medium | Functional requirements
32 | 3.1.2 | Non-Functional Requirements [Deliverable: Non-Functional Requirements Document] | Sub-Task | 50% |  | 2025-02-06 | 2025-02-07 | 31 | 33 | Technical Analyst | 2025-02-06 | 2025-02-07 |  |  |  | In Progress | Medium | Non-functional requirements
33 | 3.1.3 | Data Requirements [Deliverable: Data Requirements Specification] | Sub-Task | 25% |  | 2025-02-07 | 2025-02-08 | 32 | 34 | Data Architect | 2025-02-07 | 2025-02-08 |  |  |  | Not Started | High | Data requirements
34 | 3.2 | AI Architecture Design [Deliverable: AI Architecture Blueprint] | Task | 40% |  | 2025-02-11 | 2025-02-18 | 33 | 38 | AI Architect | 2025-02-11 | 2025-02-18 |  |  |  | In Progress | High | Architecture design
35 | 3.2.1 | System Architecture [Deliverable: System Architecture Diagram] | Sub-Task | 60% |  | 2025-02-11 | 2025-02-13 | 33 | 36 | System Architect | 2025-02-11 | 2025-02-13 |  |  |  | In Progress | High | System architecture
36 | 3.2.2 | Data Architecture [Deliverable: Data Architecture Design] | Sub-Task | 40% |  | 2025-02-13 | 2025-02-15 | 35 | 37 | Data Architect | 2025-02-13 | 2025-02-15 |  |  |  | In Progress | High | Data architecture
37 | 3.2.3 | ML Pipeline Design [Deliverable: ML Pipeline Architecture] | Sub-Task | 20% |  | 2025-02-15 | 2025-02-16 | 36 | 38 | ML Engineer | 2025-02-15 | 2025-02-16 |  |  |  | Not Started | High | ML pipeline design
38 | 3.3 | AI Design Documentation [Deliverable: Complete Design Documentation] | Task | 10% |  | 2025-02-19 | 2025-02-22 | 37 | 42 | Technical Writer | 2025-02-19 | 2025-02-22 |  |  |  | Not Started | Medium | Design documentation
39 | 3.3.1 | Technical Specifications [Deliverable: Technical Specification Document] | Sub-Task | 25% |  | 2025-02-19 | 2025-02-20 | 37 | 40 | Technical Writer | 2025-02-19 | 2025-02-20 |  |  |  | Not Started | Medium | Technical specs
40 | 3.3.2 | Design Review Meeting [Deliverable: Design Review Minutes] | Sub-Task | 0% |  | 2025-02-20 | 2025-02-20 | 39 | 41 | Design Team | 2025-02-20 | 2025-02-20 |  |  |  | Not Started | Low | Design review
41 | 3.3.3 | Design Approval [Deliverable: Design Approval Document] | Sub-Task | 0% |  | 2025-02-21 | 2025-02-21 | 40 | 42 | Stakeholders | 2025-02-21 | 2025-02-21 |  |  |  | Not Started | Low | Design approval
42 | 3.4 | AI Solution Design Completion [Deliverable: Approved AI Solution Design] | Milestone | 0% |  | 2025-02-22 | 2025-02-22 | 41 | 43 | AI Architect | 2025-02-22 | 2025-02-22 |  |  |  | Not Started | Medium | Design completion milestone
43 | 4.0 | AI Compliance and Finance [Deliverable: Compliance Certification] | Phase |  |  | 2025-02-23 | 2025-03-14 | 42 | 59 | Compliance Officer | 2025-02-23 | 2025-03-14 |  |  |  | In Progress | High | Compliance phase
44 | 4.1 | AI Ethics Review [Deliverable: Ethics Approval Certificate] | Task | 50% |  | 2025-02-23 | 2025-03-02 | 42 | 49 | Ethics Committee | 2025-02-23 | 2025-03-02 |  |  |  | In Progress | High | Ethics review
45 | 4.1.1 | Bias Assessment [Deliverable: Bias Assessment Report] | Sub-Task | 75% |  | 2025-02-23 | 2025-02-25 | 42 | 46 | AI Ethics Specialist | 2025-02-23 | 2025-02-25 |  |  |  | In Progress | High | Bias assessment
46 | 4.1.2 | Fairness Evaluation [Deliverable: Fairness Evaluation Report] | Sub-Task | 50% |  | 2025-02-25 | 2025-02-27 | 45 | 47 | AI Ethics Specialist | 2025-02-25 | 2025-02-27 |  |  |  | In Progress | High | Fairness evaluation
47 | 4.1.3 | Transparency Requirements [Deliverable: Transparency Framework] | Sub-Task | 25% |  | 2025-02-27 | 2025-02-28 | 46 | 48 | Legal Counsel | 2025-02-27 | 2025-02-28 |  |  |  | Not Started | Medium | Transparency requirements
48 | 4.1.4 | Ethics Committee Review [Deliverable: Ethics Committee Approval] | Sub-Task | 0% |  | 2025-03-01 | 2025-03-01 | 47 | 49 | Ethics Committee | 2025-03-01 | 2025-03-01 |  |  |  | Not Started | High | Ethics committee review
49 | 4.2 | GDPR and Privacy Compliance [Deliverable: Privacy Compliance Certificate] | Task | 30% |  | 2025-03-03 | 2025-03-08 | 48 | 53 | Privacy Officer | 2025-03-03 | 2025-03-08 |  |  |  | In Progress | High | GDPR compliance
50 | 4.2.1 | Data Privacy Impact Assessment [Deliverable: DPIA Report] | Sub-Task | 60% |  | 2025-03-03 | 2025-03-04 | 48 | 51 | Privacy Officer | 2025-03-03 | 2025-03-04 |  |  |  | In Progress | High | Privacy impact assessment
51 | 4.2.2 | Data Processing Agreements [Deliverable: DPA Documents] | Sub-Task | 25% |  | 2025-03-04 | 2025-03-05 | 50 | 52 | Legal Counsel | 2025-03-04 | 2025-03-05 |  |  |  | Not Started | Medium | Data processing agreements
52 | 4.2.3 | Privacy Controls Implementation [Deliverable: Privacy Controls Documentation] | Sub-Task | 0% |  | 2025-03-05 | 2025-03-06 | 51 | 53 | Security Engineer | 2025-03-05 | 2025-03-06 |  |  |  | Not Started | High | Privacy controls
53 | 4.3 | Finance Approvals [Deliverable: Finance Approval Documents] | Task | 10% |  | 2025-03-09 | 2025-03-14 | 52 | 58 | Finance Affairs | 2025-03-09 | 2025-03-14 |  |  |  | Not Started | High | Finance approvals
54 | 4.3.1 | Industry Compliance Review [Deliverable: Industry Compliance Report] | Sub-Task | 25% |  | 2025-03-09 | 2025-03-10 | 52 | 55 | Compliance Specialist | 2025-03-09 | 2025-03-10 |  |  |  | Not Started | High | Industry compliance
55 | 4.3.2 | Finance Submission [Deliverable: Finance Submission Package] | Sub-Task | 0% |  | 2025-03-10 | 2025-03-11 | 54 | 56 | Finance Affairs | 2025-03-10 | 2025-03-11 |  |  |  | Not Started | High | Finance submission
56 | 4.3.3 | Approval Review Meeting [Deliverable: Approval Review Minutes] | Sub-Task | 0% |  | 2025-03-11 | 2025-03-11 | 55 | 57 | Finance Team | 2025-03-11 | 2025-03-11 |  |  |  | Not Started | Medium | Approval review
57 | 4.3.4 | Final Compliance Certification [Deliverable: Compliance Certificate] | Sub-Task | 0% |  | 2025-03-12 | 2025-03-12 | 56 | 58 | Compliance Officer | 2025-03-12 | 2025-03-12 |  |  |  | Not Started | High | Final certification
58 | 4.4 | AI Compliance Completion [Deliverable: Complete Compliance Package] | Milestone | 0% |  | 2025-03-14 | 2025-03-14 | 57 | 59 | Compliance Officer | 2025-03-14 | 2025-03-14 |  |  |  | Not Started | High | Compliance completion milestone
59 | 5.0 | AI Procurement and Contracting [Deliverable: Procurement Completion Report] | Phase |  |  | 2025-03-15 | 2025-04-05 | 58 | 74 | Procurement Manager | 2025-03-15 | 2025-04-05 |  |  |  | In Progress | Medium | Procurement phase
60 | 5.1 | AI Vendor Selection [Deliverable: Selected Vendor Contracts] | Task | 40% |  | 2025-03-15 | 2025-03-24 | 58 | 66 | Procurement Manager | 2025-03-15 | 2025-03-24 |  |  |  | In Progress | Medium | Vendor selection
61 | 5.1.1 | RFP Development [Deliverable: Request for Proposal Document] | Sub-Task | 75% |  | 2025-03-15 | 2025-03-17 | 58 | 62 | Procurement Specialist | 2025-03-15 | 2025-03-17 |  |  |  | In Progress | Medium | RFP development
62 | 5.1.2 | Vendor Identification [Deliverable: Qualified Vendor List] | Sub-Task | 50% |  | 2025-03-17 | 2025-03-18 | 61 | 63 | Market Research Analyst | 2025-03-17 | 2025-03-18 |  |  |  | In Progress | Medium | Vendor identification
63 | 5.1.3 | Proposal Evaluation [Deliverable: Vendor Evaluation Matrix] | Sub-Task | 25% |  | 2025-03-18 | 2025-03-20 | 62 | 64 | Evaluation Committee | 2025-03-18 | 2025-03-20 |  |  |  | Not Started | High | Proposal evaluation
64 | 5.1.4 | Reference Checks [Deliverable: Reference Check Reports] | Sub-Task | 0% |  | 2025-03-20 | 2025-03-21 | 63 | 65 | Procurement Team | 2025-03-20 | 2025-03-21 |  |  |  | Not Started | Medium | Reference checks
65 | 5.1.5 | Contract Negotiation [Deliverable: Negotiated Contracts] | Sub-Task | 0% |  | 2025-03-21 | 2025-03-23 | 64 | 66 | Legal Team | 2025-03-21 | 2025-03-23 |  |  |  | Not Started | High | Contract negotiation
66 | 5.2 | Infrastructure Procurement [Deliverable: Infrastructure Setup Completion] | Task | 30% |  | 2025-03-25 | 2025-04-01 | 65 | 70 | Infrastructure Manager | 2025-03-25 | 2025-04-01 |  |  |  | In Progress | High | Infrastructure procurement
67 | 5.2.1 | Hardware Requirements [Deliverable: Hardware Specifications] | Sub-Task | 60% |  | 2025-03-25 | 2025-03-26 | 65 | 68 | Infrastructure Architect | 2025-03-25 | 2025-03-26 |  |  |  | In Progress | High | Hardware requirements
68 | 5.2.2 | Cloud Services Setup [Deliverable: Cloud Environment Configuration] | Sub-Task | 40% |  | 2025-03-26 | 2025-03-28 | 67 | 69 | Cloud Engineer | 2025-03-26 | 2025-03-28 |  |  |  | In Progress | High | Cloud services setup
69 | 5.2.3 | Network Configuration [Deliverable: Network Setup Documentation] | Sub-Task | 20% |  | 2025-03-28 | 2025-03-29 | 68 | 70 | Network Engineer | 2025-03-28 | 2025-03-29 |  |  |  | Not Started | Medium | Network configuration
70 | 5.2.4 | Security Implementation [Deliverable: Security Configuration Report] | Sub-Task | 0% |  | 2025-03-29 | 2025-03-30 | 69 | 71 | Security Engineer | 2025-03-29 | 2025-03-30 |  |  |  | Not Started | High | Security implementation
71 | 5.3 | Equipment and Tools Setup [Deliverable: Tools Configuration Report] | Task | 10% |  | 2025-04-01 | 2025-04-04 | 70 | 73 | Technical Lead | 2025-04-01 | 2025-04-04 |  |  |  | Not Started | Medium | Equipment setup
72 | 5.3.1 | AI Development Tools [Deliverable: Development Environment Setup] | Sub-Task | 25% |  | 2025-04-01 | 2025-04-02 | 70 | 73 | DevOps Engineer | 2025-04-01 | 2025-04-02 |  |  |  | Not Started | Medium | AI development tools
73 | 5.3.2 | Monitoring and Analytics Tools [Deliverable: Monitoring Dashboard Setup] | Sub-Task | 0% |  | 2025-04-02 | 2025-04-03 | 72 | 74 | Monitoring Specialist | 2025-04-02 | 2025-04-03 |  |  |  | Not Started | Medium | Monitoring tools
74 | 5.4 | AI Procurement Completion [Deliverable: Procurement Sign-off] | Milestone | 0% |  | 2025-04-05 | 2025-04-05 | 73 | 75 | Procurement Manager | 2025-04-05 | 2025-04-05 |  |  |  | Not Started | Medium | Procurement completion milestone
75 | 6.0 | AI Development and Implementation [Deliverable: AI System Implementation] | Phase |  |  | 2025-04-06 | 2025-05-10 | 74 | 100 | AI Development Lead | 2025-04-06 | 2025-05-10 |  |  |  | In Progress | High | Development phase
76 | 6.1 | Data Preparation and Management [Deliverable: Prepared Dataset] | Task | 30% |  | 2025-04-06 | 2025-04-17 | 74 | 82 | Data Engineer | 2025-04-06 | 2025-04-17 |  |  |  | In Progress | High | Data preparation
77 | 6.1.1 | Data Collection [Deliverable: Raw Data Repository] | Sub-Task | 60% |  | 2025-04-06 | 2025-04-08 | 74 | 78 | Data Engineer | 2025-04-06 | 2025-04-08 |  |  |  | In Progress | High | Data collection
78 | 6.1.2 | Data Cleaning and Preprocessing [Deliverable: Clean Dataset] | Sub-Task | 40% |  | 2025-04-08 | 2025-04-11 | 77 | 79 | Data Scientist | 2025-04-08 | 2025-04-11 |  |  |  | In Progress | High | Data cleaning
79 | 6.1.3 | Data Quality Assessment [Deliverable: Data Quality Report] | Sub-Task | 20% |  | 2025-04-11 | 2025-04-13 | 78 | 80 | Data Quality Analyst | 2025-04-11 | 2025-04-13 |  |  |  | Not Started | High | Data quality assessment
80 | 6.1.4 | Data Governance Implementation [Deliverable: Data Governance Framework] | Sub-Task | 10% |  | 2025-04-13 | 2025-04-14 | 79 | 81 | Data Governance Lead | 2025-04-13 | 2025-04-14 |  |  |  | Not Started | Medium | Data governance
81 | 6.1.5 | Data Validation and Testing [Deliverable: Data Validation Report] | Sub-Task | 0% |  | 2025-04-14 | 2025-04-15 | 80 | 82 | QA Engineer | 2025-04-14 | 2025-04-15 |  |  |  | Not Started | High | Data validation
82 | 6.2 | AI Model Development [Deliverable: Trained AI Models] | Task | 25% |  | 2025-04-18 | 2025-05-02 | 81 | 90 | ML Engineer | 2025-04-18 | 2025-05-02 |  |  |  | In Progress | High | Model development
83 | 6.2.1 | Algorithm Selection [Deliverable: Algorithm Selection Report] | Sub-Task | 50% |  | 2025-04-18 | 2025-04-20 | 81 | 84 | Data Scientist | 2025-04-18 | 2025-04-20 |  |  |  | In Progress | High | Algorithm selection
84 | 6.2.2 | Model Training [Deliverable: Trained Model Artifacts] | Sub-Task | 30% |  | 2025-04-20 | 2025-04-24 | 83 | 85 | ML Engineer | 2025-04-20 | 2025-04-24 |  |  |  | In Progress | High | Model training
85 | 6.2.3 | Model Optimization [Deliverable: Optimized Model Performance] | Sub-Task | 20% |  | 2025-04-24 | 2025-04-27 | 84 | 86 | ML Engineer | 2025-04-24 | 2025-04-27 |  |  |  | Not Started | High | Model optimization
86 | 6.2.4 | Model Validation [Deliverable: Model Validation Report] | Sub-Task | 10% |  | 2025-04-27 | 2025-04-29 | 85 | 87 | Data Scientist | 2025-04-27 | 2025-04-29 |  |  |  | Not Started | High | Model validation
87 | 6.2.5 | Model Documentation [Deliverable: Model Documentation Package] | Sub-Task | 0% |  | 2025-04-29 | 2025-04-30 | 86 | 88 | Technical Writer | 2025-04-29 | 2025-04-30 |  |  |  | Not Started | Medium | Model documentation
88 | 6.2.6 | Model Review Meeting [Deliverable: Model Review Minutes] | Sub-Task | 0% |  | 2025-04-30 | 2025-04-30 | 87 | 89 | Review Committee | 2025-04-30 | 2025-04-30 |  |  |  | Not Started | Medium | Model review
89 | 6.2.7 | Model Approval [Deliverable: Model Approval Certificate] | Sub-Task | 0% |  | 2025-05-01 | 2025-05-01 | 88 | 90 | AI Architect | 2025-05-01 | 2025-05-01 |  |  |  | Not Started | High | Model approval
90 | 6.3 | AI System Integration [Deliverable: Integrated AI System] | Task | 10% |  | 2025-05-03 | 2025-05-10 | 89 | 99 | Integration Engineer | 2025-05-03 | 2025-05-10 |  |  |  | Not Started | High | System integration
91 | 6.3.1 | API Development [Deliverable: AI Service APIs] | Sub-Task | 25% |  | 2025-05-03 | 2025-05-05 | 89 | 92 | Backend Developer | 2025-05-03 | 2025-05-05 |  |  |  | Not Started | High | API development
92 | 6.3.2 | Frontend Integration [Deliverable: User Interface Integration] | Sub-Task | 15% |  | 2025-05-05 | 2025-05-07 | 91 | 93 | Frontend Developer | 2025-05-05 | 2025-05-07 |  |  |  | Not Started | Medium | Frontend integration
93 | 6.3.3 | Database Integration [Deliverable: Database Schema and Connections] | Sub-Task | 10% |  | 2025-05-07 | 2025-05-08 | 92 | 94 | Database Administrator | 2025-05-07 | 2025-05-08 |  |  |  | Not Started | High | Database integration
94 | 6.3.4 | Third-party Integrations [Deliverable: External System Connections] | Sub-Task | 5% |  | 2025-05-08 | 2025-05-09 | 93 | 95 | Integration Specialist | 2025-05-08 | 2025-05-09 |  |  |  | Not Started | Medium | Third-party integrations
95 | 6.3.5 | Integration Testing [Deliverable: Integration Test Results] | Sub-Task | 0% |  | 2025-05-09 | 2025-05-10 | 94 | 96 | QA Engineer | 2025-05-09 | 2025-05-10 |  |  |  | Not Started | High | Integration testing
96 | 6.3.6 | Performance Optimization [Deliverable: Performance Optimization Report] | Sub-Task | 0% |  | 2025-05-10 | 2025-05-10 | 95 | 97 | Performance Engineer | 2025-05-10 | 2025-05-10 |  |  |  | Not Started | High | Performance optimization
97 | 6.3.7 | Integration Review Meeting [Deliverable: Integration Review Minutes] | Sub-Task | 0% |  | 2025-05-10 | 2025-05-10 | 96 | 98 | Integration Team | 2025-05-10 | 2025-05-10 |  |  |  | Not Started | Medium | Integration review
98 | 6.3.8 | Integration Approval [Deliverable: Integration Approval Document] | Sub-Task | 0% |  | 2025-05-10 | 2025-05-10 | 97 | 99 | Technical Lead | 2025-05-10 | 2025-05-10 |  |  |  | Not Started | High | Integration approval
99 | 6.4 | AI Development Completion [Deliverable: Complete AI System] | Milestone | 0% |  | 2025-05-10 | 2025-05-10 | 98 | 100 | AI Development Lead | 2025-05-10 | 2025-05-10 |  |  |  | Not Started | High | Development completion milestone
100 | 7.0 | AI Testing and Validation [Deliverable: Testing Completion Report] | Phase |  |  | 2025-05-11 | 2025-06-04 | 99 | 118 | QA Manager | 2025-05-11 | 2025-06-04 |  |  |  | Not Started | High | Testing phase
101 | 7.1 | AI Model Testing [Deliverable: Model Test Results] | Task | 20% |  | 2025-05-11 | 2025-05-20 | 99 | 107 | ML Test Engineer | 2025-05-11 | 2025-05-20 |  |  |  | Not Started | High | Model testing
102 | 7.1.1 | Unit Testing [Deliverable: Unit Test Results] | Sub-Task | 40% |  | 2025-05-11 | 2025-05-13 | 99 | 103 | QA Engineer | 2025-05-11 | 2025-05-13 |  |  |  | Not Started | Medium | Unit testing
103 | 7.1.2 | Model Accuracy Testing [Deliverable: Accuracy Test Report] | Sub-Task | 25% |  | 2025-05-13 | 2025-05-15 | 102 | 104 | Data Scientist | 2025-05-13 | 2025-05-15 |  |  |  | Not Started | High | Accuracy testing
104 | 7.1.3 | Performance Testing [Deliverable: Performance Test Results] | Sub-Task | 15% |  | 2025-05-15 | 2025-05-16 | 103 | 105 | Performance Tester | 2025-05-15 | 2025-05-16 |  |  |  | Not Started | High | Performance testing
105 | 7.1.4 | Bias and Fairness Testing [Deliverable: Bias Testing Report] | Sub-Task | 10% |  | 2025-05-16 | 2025-05-17 | 104 | 106 | AI Ethics Specialist | 2025-05-16 | 2025-05-17 |  |  |  | Not Started | High | Bias testing
106 | 7.1.5 | Model Robustness Testing [Deliverable: Robustness Test Results] | Sub-Task | 5% |  | 2025-05-17 | 2025-05-18 | 105 | 107 | Security Tester | 2025-05-17 | 2025-05-18 |  |  |  | Not Started | High | Robustness testing
107 | 7.2 | User Acceptance Testing [Deliverable: UAT Results] | Task | 15% |  | 2025-05-21 | 2025-05-28 | 106 | 112 | UAT Coordinator | 2025-05-21 | 2025-05-28 |  |  |  | Not Started | Medium | User acceptance testing
108 | 7.2.1 | UAT Planning [Deliverable: UAT Test Plan] | Sub-Task | 30% |  | 2025-05-21 | 2025-05-22 | 106 | 109 | UAT Coordinator | 2025-05-21 | 2025-05-22 |  |  |  | Not Started | Medium | UAT planning
109 | 7.2.2 | User Training for Testing [Deliverable: User Training Materials] | Sub-Task | 20% |  | 2025-05-22 | 2025-05-23 | 108 | 110 | Training Specialist | 2025-05-22 | 2025-05-23 |  |  |  | Not Started | Medium | User training
110 | 7.2.3 | UAT Execution [Deliverable: UAT Test Execution Results] | Sub-Task | 10% |  | 2025-05-23 | 2025-05-25 | 109 | 111 | End Users | 2025-05-23 | 2025-05-25 |  |  |  | Not Started | High | UAT execution
111 | 7.2.4 | UAT Results Analysis [Deliverable: UAT Analysis Report] | Sub-Task | 5% |  | 2025-05-25 | 2025-05-25 | 110 | 112 | Business Analyst | 2025-05-25 | 2025-05-25 |  |  |  | Not Started | Medium | UAT analysis
112 | 7.3 | Security and Compliance Testing [Deliverable: Security Test Report] | Task | 10% |  | 2025-05-29 | 2025-06-04 | 111 | 117 | Security Tester | 2025-05-29 | 2025-06-04 |  |  |  | Not Started | High | Security testing
113 | 7.3.1 | Security Vulnerability Testing [Deliverable: Vulnerability Assessment] | Sub-Task | 20% |  | 2025-05-29 | 2025-05-31 | 111 | 114 | Security Analyst | 2025-05-29 | 2025-05-31 |  |  |  | Not Started | High | Vulnerability testing
114 | 7.3.2 | Data Privacy Testing [Deliverable: Privacy Test Results] | Sub-Task | 15% |  | 2025-05-31 | 2025-06-01 | 113 | 115 | Privacy Officer | 2025-05-31 | 2025-06-01 |  |  |  | Not Started | High | Privacy testing
115 | 7.3.3 | Compliance Validation [Deliverable: Compliance Validation Report] | Sub-Task | 10% |  | 2025-06-01 | 2025-06-02 | 114 | 116 | Compliance Officer | 2025-06-01 | 2025-06-02 |  |  |  | Not Started | High | Compliance validation
116 | 7.3.4 | Security Review Meeting [Deliverable: Security Review Minutes] | Sub-Task | 5% |  | 2025-06-02 | 2025-06-02 | 115 | 117 | Security Team | 2025-06-02 | 2025-06-02 |  |  |  | Not Started | Medium | Security review
117 | 7.4 | AI Testing Completion [Deliverable: Testing Sign-off] | Milestone | 0% |  | 2025-06-04 | 2025-06-04 | 116 | 118 | QA Manager | 2025-06-04 | 2025-06-04 |  |  |  | Not Started | High | Testing completion milestone
118 | 8.0 | AI Documentation and Training [Deliverable: Complete Documentation Package] | Phase |  |  | 2025-06-05 | 2025-06-22 | 117 | 132 | Documentation Manager | 2025-06-05 | 2025-06-22 |  |  |  | Not Started | Medium | Documentation phase
119 | 8.1 | Technical Documentation [Deliverable: Technical Documentation Suite] | Task | 10% |  | 2025-06-05 | 2025-06-12 | 117 | 124 | Technical Writer | 2025-06-05 | 2025-06-12 |  |  |  | Not Started | Medium | Technical documentation
120 | 8.1.1 | System Architecture Documentation [Deliverable: Architecture Documents] | Sub-Task | 20% |  | 2025-06-05 | 2025-06-06 | 117 | 121 | System Architect | 2025-06-05 | 2025-06-06 |  |  |  | Not Started | Medium | Architecture documentation
121 | 8.1.2 | API Documentation [Deliverable: API Reference Guide] | Sub-Task | 15% |  | 2025-06-06 | 2025-06-07 | 120 | 122 | API Developer | 2025-06-06 | 2025-06-07 |  |  |  | Not Started | Medium | API documentation
122 | 8.1.3 | Model Documentation [Deliverable: Model Documentation Package] | Sub-Task | 10% |  | 2025-06-07 | 2025-06-08 | 121 | 123 | Data Scientist | 2025-06-07 | 2025-06-08 |  |  |  | Not Started | Medium | Model documentation
123 | 8.1.4 | Deployment Documentation [Deliverable: Deployment Guide] | Sub-Task | 5% |  | 2025-06-08 | 2025-06-09 | 122 | 124 | DevOps Engineer | 2025-06-08 | 2025-06-09 |  |  |  | Not Started | Medium | Deployment documentation
124 | 8.2 | User Training and Knowledge Transfer [Deliverable: Training Program Completion] | Task | 8% |  | 2025-06-13 | 2025-06-22 | 123 | 131 | Training Manager | 2025-06-13 | 2025-06-22 |  |  |  | Not Started | Medium | User training
125 | 8.2.1 | Training Material Development [Deliverable: Training Materials] | Sub-Task | 15% |  | 2025-06-13 | 2025-06-15 | 123 | 126 | Training Developer | 2025-06-13 | 2025-06-15 |  |  |  | Not Started | Medium | Training materials
126 | 8.2.2 | Administrator Training [Deliverable: Administrator Training Completion] | Sub-Task | 10% |  | 2025-06-15 | 2025-06-16 | 125 | 127 | Technical Trainer | 2025-06-15 | 2025-06-16 |  |  |  | Not Started | Medium | Administrator training
127 | 8.2.3 | End User Training [Deliverable: End User Training Completion] | Sub-Task | 8% |  | 2025-06-16 | 2025-06-18 | 126 | 128 | User Trainer | 2025-06-16 | 2025-06-18 |  |  |  | Not Started | Medium | End user training
128 | 8.2.4 | Knowledge Transfer Sessions [Deliverable: Knowledge Transfer Documentation] | Sub-Task | 5% |  | 2025-06-18 | 2025-06-19 | 127 | 129 | Subject Matter Expert | 2025-06-18 | 2025-06-19 |  |  |  | Not Started | Medium | Knowledge transfer
129 | 8.2.5 | Training Assessment [Deliverable: Training Assessment Results] | Sub-Task | 3% |  | 2025-06-19 | 2025-06-19 | 128 | 130 | Training Coordinator | 2025-06-19 | 2025-06-19 |  |  |  | Not Started | Low | Training assessment
130 | 8.2.6 | Training Feedback and Improvement [Deliverable: Training Improvement Plan] | Sub-Task | 2% |  | 2025-06-20 | 2025-06-20 | 129 | 131 | Training Manager | 2025-06-20 | 2025-06-20 |  |  |  | Not Started | Low | Training feedback
131 | 8.3 | AI Documentation and Training Completion [Deliverable: Documentation Sign-off] | Milestone | 0% |  | 2025-06-22 | 2025-06-22 | 130 | 132 | Documentation Manager | 2025-06-22 | 2025-06-22 |  |  |  | Not Started | Medium | Documentation completion milestone
132 | 9.0 | AI Walkthrough and Handover [Deliverable: System Handover Package] | Phase |  |  | 2025-06-23 | 2025-07-12 | 131 | 148 | Project Manager | 2025-06-23 | 2025-07-12 |  |  |  | Not Started | Medium | Walkthrough phase
133 | 9.1 | Pre-Deployment Walkthrough [Deliverable: Pre-Deployment Checklist] | Task | 5% |  | 2025-06-23 | 2025-06-30 | 131 | 138 | Deployment Manager | 2025-06-23 | 2025-06-30 |  |  |  | Not Started | Medium | Pre-deployment walkthrough
134 | 9.1.1 | System Readiness Review [Deliverable: Readiness Assessment Report] | Sub-Task | 10% |  | 2025-06-23 | 2025-06-24 | 131 | 135 | Technical Lead | 2025-06-23 | 2025-06-24 |  |  |  | Not Started | Medium | System readiness review
135 | 9.1.2 | Infrastructure Validation [Deliverable: Infrastructure Validation Report] | Sub-Task | 8% |  | 2025-06-24 | 2025-06-25 | 134 | 136 | Infrastructure Engineer | 2025-06-24 | 2025-06-25 |  |  |  | Not Started | High | Infrastructure validation
136 | 9.1.3 | Security Final Check [Deliverable: Security Clearance Certificate] | Sub-Task | 5% |  | 2025-06-25 | 2025-06-26 | 135 | 137 | Security Officer | 2025-06-25 | 2025-06-26 |  |  |  | Not Started | High | Security final check
137 | 9.1.4 | Go/No-Go Decision Meeting [Deliverable: Go/No-Go Decision Document] | Sub-Task | 3% |  | 2025-06-26 | 2025-06-26 | 136 | 138 | Steering Committee | 2025-06-26 | 2025-06-26 |  |  |  | Not Started | High | Go/No-Go decision
138 | 9.2 | AI System Go-Live [Deliverable: Live System] | Task | 2% |  | 2025-07-01 | 2025-07-05 | 137 | 142 | Deployment Team | 2025-07-01 | 2025-07-05 |  |  |  | Not Started | High | System go-live
139 | 9.2.1 | Production Deployment [Deliverable: Production System Deployment] | Sub-Task | 5% |  | 2025-07-01 | 2025-07-02 | 137 | 140 | DevOps Engineer | 2025-07-01 | 2025-07-02 |  |  |  | Not Started | High | Production deployment
140 | 9.2.2 | System Monitoring Activation [Deliverable: Active Monitoring Dashboard] | Sub-Task | 3% |  | 2025-07-02 | 2025-07-02 | 139 | 141 | Monitoring Specialist | 2025-07-02 | 2025-07-02 |  |  |  | Not Started | High | Monitoring activation
141 | 9.2.3 | User Access Provisioning [Deliverable: User Access Configuration] | Sub-Task | 2% |  | 2025-07-02 | 2025-07-02 | 140 | 142 | System Administrator | 2025-07-02 | 2025-07-02 |  |  |  | Not Started | Medium | User access provisioning
142 | 9.3 | System Handover and Support Transition [Deliverable: Support Transition Plan] | Task | 1% |  | 2025-07-06 | 2025-07-12 | 141 | 147 | Support Manager | 2025-07-06 | 2025-07-12 |  |  |  | Not Started | Medium | System handover
143 | 9.3.1 | Finance Handover [Deliverable: Finance Handover Document] | Sub-Task | 3% |  | 2025-07-06 | 2025-07-07 | 141 | 144 | Finance Manager | 2025-07-06 | 2025-07-07 |  |  |  | Not Started | Medium | Finance handover
144 | 9.3.2 | Support Team Training [Deliverable: Support Team Training Completion] | Sub-Task | 2% |  | 2025-07-07 | 2025-07-08 | 143 | 145 | Support Trainer | 2025-07-07 | 2025-07-08 |  |  |  | Not Started | Medium | Support team training
145 | 9.3.3 | Support Process Documentation [Deliverable: Support Process Manual] | Sub-Task | 1% |  | 2025-07-08 | 2025-07-09 | 144 | 146 | Process Analyst | 2025-07-08 | 2025-07-09 |  |  |  | Not Started | Medium | Support documentation
146 | 9.3.4 | Handover Acceptance [Deliverable: Handover Acceptance Certificate] | Sub-Task | 0% |  | 2025-07-09 | 2025-07-09 | 145 | 147 | Support Manager | 2025-07-09 | 2025-07-09 |  |  |  | Not Started | Medium | Handover acceptance
147 | 9.4 | AI Walkthrough and Handover Completion [Deliverable: Handover Completion Certificate] | Milestone | 0% |  | 2025-07-12 | 2025-07-12 | 146 | 148 | Project Manager | 2025-07-12 | 2025-07-12 |  |  |  | Not Started | Medium | Handover completion milestone
148 | 10.0 | AI Project Close-out [Deliverable: Project Closure Report] | Phase |  |  | 2025-07-13 | 2025-07-27 | 147 | 161 | Project Manager | 2025-07-13 | 2025-07-27 |  |  |  | Not Started | Low | Project close-out phase
149 | 10.1 | Administrative Closure [Deliverable: Administrative Closure Package] | Task | 2% |  | 2025-07-13 | 2025-07-18 | 147 | 153 | Project Administrator | 2025-07-13 | 2025-07-18 |  |  |  | Not Started | Low | Administrative closure
150 | 10.1.1 | Contract Closure [Deliverable: Contract Closure Documentation] | Sub-Task | 5% |  | 2025-07-13 | 2025-07-14 | 147 | 151 | Contract Manager | 2025-07-13 | 2025-07-14 |  |  |  | Not Started | Medium | Contract closure
151 | 10.1.2 | Financial Closure [Deliverable: Financial Closure Report] | Sub-Task | 3% |  | 2025-07-14 | 2025-07-15 | 150 | 152 | Finance Manager | 2025-07-14 | 2025-07-15 |  |  |  | Not Started | Medium | Financial closure
152 | 10.1.3 | Resource Release [Deliverable: Resource Release Documentation] | Sub-Task | 1% |  | 2025-07-15 | 2025-07-16 | 151 | 153 | Resource Manager | 2025-07-15 | 2025-07-16 |  |  |  | Not Started | Low | Resource release
153 | 10.2 | Project Documentation Archive [Deliverable: Archived Project Documentation] | Task | 1% |  | 2025-07-19 | 2025-07-22 | 152 | 157 | Documentation Manager | 2025-07-19 | 2025-07-22 |  |  |  | Not Started | Low | Documentation archive
154 | 10.2.1 | Document Collection [Deliverable: Complete Document Repository] | Sub-Task | 3% |  | 2025-07-19 | 2025-07-20 | 152 | 155 | Documentation Specialist | 2025-07-19 | 2025-07-20 |  |  |  | Not Started | Low | Document collection
155 | 10.2.2 | Archive Organization [Deliverable: Organized Archive Structure] | Sub-Task | 2% |  | 2025-07-20 | 2025-07-20 | 154 | 156 | Information Manager | 2025-07-20 | 2025-07-20 |  |  |  | Not Started | Low | Archive organization
156 | 10.2.3 | Archive Storage [Deliverable: Stored Project Archive] | Sub-Task | 1% |  | 2025-07-21 | 2025-07-21 | 155 | 157 | IT Administrator | 2025-07-21 | 2025-07-21 |  |  |  | Not Started | Low | Archive storage
157 | 10.3 | Lessons Learned and Final Reporting [Deliverable: Lessons Learned Report] | Task | 0% |  | 2025-07-23 | 2025-07-27 | 156 | 160 | Project Manager | 2025-07-23 | 2025-07-27 |  |  |  | Not Started | Medium | Lessons learned
158 | 10.3.1 | Lessons Learned Session [Deliverable: Lessons Learned Documentation] | Sub-Task | 2% |  | 2025-07-23 | 2025-07-24 | 156 | 159 | Project Team | 2025-07-23 | 2025-07-24 |  |  |  | Not Started | Medium | Lessons learned session
159 | 10.3.2 | Final Project Report [Deliverable: Final Project Report] | Sub-Task | 1% |  | 2025-07-24 | 2025-07-25 | 158 | 160 | Project Manager | 2025-07-24 | 2025-07-25 |  |  |  | Not Started | Medium | Final project report
160 | 10.3.3 | Stakeholder Communication [Deliverable: Final Stakeholder Communication] | Sub-Task | 0% |  | 2025-07-25 | 2025-07-25 | 159 | 161 | Communications Lead | 2025-07-25 | 2025-07-25 |  |  |  | Not Started | Low | Stakeholder communication
161 | 10.4 | AI Project Close-out Completion [Deliverable: Project Closure Certificate] | Milestone | 0% |  | 2025-07-27 | 2025-07-27 | 160 | 162 | Project Sponsor | 2025-07-27 | 2025-07-27 |  |  |  | Not Started | Low | Project closure milestone
162 | 11.0 | AI Steady-State Support [Deliverable: Steady-State Support Report] | Phase |  |  | 2025-07-28 | 2025-10-25 | 161 |  | Support Manager | 2025-07-28 | 2025-10-25 |  |  |  | Not Started | Medium | Steady-state support phase
163 | 11.1 | Warranty Period Management [Deliverable: Warranty Period Completion] | Task | 0% |  | 2025-07-28 | 2025-08-26 | 161 | 168 | Warranty Manager | 2025-07-28 | 2025-08-26 |  |  |  | Not Started | Medium | Warranty period
164 | 11.1.1 | System Monitoring [Deliverable: System Performance Reports] | Sub-Task | 0% |  | 2025-07-28 | 2025-08-26 | 161 | 165 | Monitoring Team | 2025-07-28 | 2025-08-26 |  |  |  | Not Started | High | System monitoring
165 | 11.1.2 | Issue Resolution [Deliverable: Issue Resolution Reports] | Sub-Task | 0% |  | 2025-07-28 | 2025-08-26 | 164 | 166 | Support Team | 2025-07-28 | 2025-08-26 |  |  |  | Not Started | High | Issue resolution
166 | 11.1.3 | Performance Optimization [Deliverable: Performance Optimization Reports] | Sub-Task | 0% |  | 2025-07-28 | 2025-08-26 | 165 | 167 | Performance Team | 2025-07-28 | 2025-08-26 |  |  |  | Not Started | Medium | Performance optimization
167 | 11.1.4 | Warranty Review Meeting [Deliverable: Warranty Review Minutes] | Sub-Task | 0% |  | 2025-08-26 | 2025-08-26 | 166 | 168 | Warranty Committee | 2025-08-26 | 2025-08-26 |  |  |  | Not Started | Low | Warranty review
168 | 11.2 | Post-Implementation Reviews [Deliverable: Post-Implementation Review Reports] | Task | 0% |  | 2025-08-27 | 2025-09-25 | 167 | 173 | Review Manager | 2025-08-27 | 2025-09-25 |  |  |  | Not Started | Medium | Post-implementation reviews
169 | 11.2.1 | 30-Day Review [Deliverable: 30-Day Review Report] | Sub-Task | 0% |  | 2025-08-27 | 2025-08-27 | 167 | 170 | Review Team | 2025-08-27 | 2025-08-27 |  |  |  | Not Started | Medium | 30-day review
170 | 11.2.2 | 60-Day Review [Deliverable: 60-Day Review Report] | Sub-Task | 0% |  | 2025-09-26 | 2025-09-26 | 169 | 171 | Review Team | 2025-09-26 | 2025-09-26 |  |  |  | Not Started | Medium | 60-day review
171 | 11.2.3 | 90-Day Review [Deliverable: 90-Day Review Report] | Sub-Task | 0% |  | 2025-10-25 | 2025-10-25 | 170 | 172 | Review Team | 2025-10-25 | 2025-10-25 |  |  |  | Not Started | Medium | 90-day review
172 | 11.2.4 | Review Analysis and Recommendations [Deliverable: Review Analysis Report] | Sub-Task | 0% |  | 2025-09-23 | 2025-09-25 | 171 | 173 | Business Analyst | 2025-09-23 | 2025-09-25 |  |  |  | Not Started | Medium | Review analysis
173 | 11.3 | Transition to Finance [Deliverable: Finance Transition Completion] | Task | 0% |  | 2025-09-26 | 2025-10-25 | 172 | 178 | Finance Manager | 2025-09-26 | 2025-10-25 |  |  |  | Not Started | Medium | Transition to operations
174 | 11.3.1 | Finance Team Readiness [Deliverable: Finance Readiness Assessment] | Sub-Task | 0% |  | 2025-09-26 | 2025-09-30 | 172 | 175 | Finance Lead | 2025-09-26 | 2025-09-30 |  |  |  | Not Started | Medium | Finance readiness
175 | 11.3.2 | Knowledge Transfer Completion [Deliverable: Knowledge Transfer Sign-off] | Sub-Task | 0% |  | 2025-09-30 | 2025-10-09 | 174 | 176 | Knowledge Manager | 2025-09-30 | 2025-10-09 |  |  |  | Not Started | Medium | Knowledge transfer
176 | 11.3.3 | Support Process Finalization [Deliverable: Final Support Processes] | Sub-Task | 0% |  | 2025-10-09 | 2025-10-18 | 175 | 177 | Process Manager | 2025-10-09 | 2025-10-18 |  |  |  | Not Started | Medium | Support process finalization
177 | 11.3.4 | Finance Handover [Deliverable: Final Finance Handover] | Sub-Task | 0% |  | 2025-10-18 | 2025-10-22 | 176 | 178 | Finance Manager | 2025-10-18 | 2025-10-22 |  |  |  | Not Started | Medium | Finance handover
178 | 11.4 | AI Steady-State Support Completion [Deliverable: Steady-State Completion Certificate] | Milestone | 0% |  | 2025-10-25 | 2025-10-25 | 177 |  | Support Manager | 2025-10-25 | 2025-10-25 |  |  |  | Not Started | Low | Steady-state completion milestone
|  | OVERALL PROJECT COMPLETION | SUMMARY
|  | SUMMARY | SUMMARY
|  | Project Status Dashboard | SUMMARY