## Engagement Overview
STAKEHOLDER ENGAGEMENT PLAN
PRODUCT Stakeholder Engagement Plan Project
Generated: July 16, 2025
PROJECT INFORMATION
Project Name: | Enterprise Cloud Infrastructure Migration
Stakeholder Manager: | Jennifer Martinez, PMP
Total Stakeholders: | 45 identified stakeholders
Stakeholder Categories: | 8 primary stakeholder groups
Engagement Duration: | 18 months (Jan 2025 - Jun 2026)
Engagement Budget: | $95,000 (3.3% of project budget)
Engagement Frequency: | Daily to Quarterly based on stakeholder
STAKEHOLDER ENGAGEMENT OBJECTIVES
1. Maintain active support from key stakeholders throughout project lifecycle
2. Ensure timely stakeholder input and decision-making for project success
3. Build stakeholder confidence and trust in IT transformation initiative
4. Minimize stakeholder resistance and maximize adoption readiness
5. Establish sustainable stakeholder relationships for future initiatives
6. Create transparent communication channels for feedback and concerns
ENGAGEMENT PRINCIPLES
• Inclusive: Engage all affected stakeholders with appropriate level of involvement
• Transparent: Provide honest, timely, and accurate information about project status
• Respectful: Value stakeholder time, expertise, and perspectives in all interactions
• Responsive: Address stakeholder concerns and feedback promptly and effectively
• Consistent: Maintain regular engagement patterns and reliable communication
• Value-Focused: Emphasize benefits and value creation for each stakeholder group

## Stakeholder Analysis
STAKEHOLDER ANALYSIS MATRIX
Stakeholder Name | Role/Title | Organization | Interest Level | Influence Level | Attitude | Impact on Project | Project Impact on Them | Engagement Strategy | Key Concerns | Success Criteria | Preferred Communication | Frequency | Owner
John Smith | CEO | Executive | High | High | Supportive | High | High | Manage Closely | ROI and timeline | Business success | Executive briefing | Monthly | Sarah Johnson
Maria Garcia | CTO | Technology | High | High | Champion | High | High | Manage Closely | Technical feasibility | Innovation leadership | Technical review | Bi-weekly | Alex Rodriguez
David Chen | CFO | Finance | Medium | High | Neutral | High | Medium | Keep Satisfied | Budget control | Cost management | Financial report | Monthly | Sarah Johnson
Lisa Wang | CHRO | HR | Medium | Medium | Supportive | Medium | High | Keep Informed | Employee impact | Change success | HR meeting | Bi-weekly | Mark Thompson
Robert Taylor | Business Director | Operations | High | Medium | Supportive | Medium | High | Keep Informed | Business continuity | Operational efficiency | Business review | Weekly | Lisa Wang
Jennifer Liu | Data Director | Analytics | High | Medium | Champion | High | High | Keep Informed | Data quality | Analytics capability | Data meeting | Weekly | Thomas Lee
Michael Johnson | IT Director | Technology | Medium | Medium | Neutral | Medium | Medium | Keep Informed | Infrastructure impact | System stability | IT review | Bi-weekly | Chris Wilson
Sarah Brown | Compliance Officer | Legal | Medium | Medium | Cautious | Medium | Medium | Keep Informed | Regulatory compliance | Risk mitigation | Compliance review | Monthly | Sarah Johnson
Kevin Zhang | Tech Lead | Technology | High | Low | Champion | Low | High | Monitor | Technical execution | Career development | Team meeting | Weekly | Alex Rodriguez
Amanda Davis | End User Rep | Business | High | Low | Cautious | Low | High | Monitor | Usability concerns | Job security | User session | Bi-weekly | Mark Thompson
Dr. Susan Clark | Board Member | Governance | Medium | High | Neutral | High | Low | Keep Satisfied | Strategic alignment | Governance oversight | Board report | Quarterly | CEO
Tom Wilson | Union Rep | Labor | Medium | Medium | Resistant | Medium | High | Keep Informed | Job displacement | Worker protection | Union meeting | Monthly | CHRO
Rachel Green | Customer Rep | External | Low | Low | Neutral | Low | Medium | Monitor | Service quality | Customer satisfaction | Customer update | Quarterly | Customer Success
James Miller | Vendor Partner | External | Medium | Low | Supportive | Low | Medium | Monitor | Partnership impact | Business opportunity | Vendor meeting | Monthly | Procurement
Patricia Lewis | Regulator | External | Low | High | Neutral | High | Low | Keep Satisfied | Compliance adherence | Regulatory oversight | Regulatory report | Quarterly | Compliance Officer

## Engagement Activities
STAKEHOLDER ENGAGEMENT ACTIVITIES
Activity ID | Activity Name | Target Stakeholders | Objective | Method | Frequency | Start Date | End Date | Owner | Status | Budget | Notes
SE-001 | Executive Steering Committee | C-Suite | Strategic oversight | Monthly meeting | Monthly | 2025-01-01 | 2026-06-30 | Sarah Johnson | Active | $12,000 | Strategic decisions
SE-002 | Project Kickoff Event | All Stakeholders | Project launch | Town hall | One-time | 2025-01-15 | 2025-01-15 | Communications | Completed | $8,000 | Project introduction
SE-003 | Technical Advisory Board | Technical Leaders | Technical guidance | Bi-weekly meeting | Bi-weekly | 2025-02-01 | 2026-04-30 | Alex Rodriguez | Active | $15,000 | Technical decisions
SE-004 | Business User Sessions | End Users | Requirements gathering | Workshop | Monthly | 2025-02-15 | 2025-06-30 | Business Analyst | Active | $10,000 | User input
SE-005 | Change Champion Network | Champions | Change advocacy | Monthly meeting | Monthly | 2025-03-01 | 2026-06-30 | Mark Thompson | Active | $8,000 | Change support
SE-006 | Vendor Partner Reviews | Key Vendors | Partnership alignment | Quarterly review | Quarterly | 2025-03-15 | 2026-06-30 | Procurement | Active | $5,000 | Vendor coordination
SE-007 | Regulatory Briefings | Compliance/Legal | Compliance assurance | Quarterly briefing | Quarterly | 2025-04-01 | 2026-06-30 | Compliance Officer | Active | $6,000 | Regulatory updates
SE-008 | Customer Advisory Panel | Key Customers | Customer perspective | Quarterly session | Quarterly | 2025-04-15 | 2026-03-31 | Customer Success | Planned | $7,000 | Customer feedback
SE-009 | Union Consultation | Labor Representatives | Worker concerns | Monthly meeting | Monthly | 2025-05-01 | 2026-06-30 | HR Manager | Planned | $4,000 | Labor relations
SE-010 | Board Reporting | Board of Directors | Governance reporting | Quarterly report | Quarterly | 2025-01-01 | 2026-06-30 | CEO | Active | $8,000 | Board oversight
SE-011 | All-Hands Updates | All Employees | Company-wide updates | Quarterly meeting | Quarterly | 2025-01-01 | 2026-06-30 | CEO | Active | $12,000 | Company communication
SE-012 | Feedback Surveys | All Stakeholders | Sentiment tracking | Survey | Quarterly | 2025-03-01 | 2026-06-30 | Communications | Active | $5,000 | Feedback collection

## Engagement Metrics
STAKEHOLDER ENGAGEMENT METRICS
Metric Category | Metric Name | Target | Current | Trend | Measurement Method | Frequency | Owner | Status | Action Required
Participation | Meeting Attendance | 90% | 88% | Stable | Meeting records | Weekly | Meeting Owners | Yellow | Improve scheduling
Satisfaction | User Satisfaction Score | 4.0/5 | 4.2/5 | Improving | Quarterly survey | Quarterly | Engagement Manager | Green | None
Communication | Response Rate | 80% | 75% | Declining | Communication tracking | Monthly | Communications | Yellow | Follow-up process
Engagement | Active Participation | 70% | 72% | Improving | Participation tracking | Monthly | Engagement Manager | Green | None
Support | Stakeholder Support Level | 4.0/5 | 3.8/5 | Stable | Support assessment | Quarterly | Project Manager | Yellow | Address concerns
Feedback | Feedback Quality | 4.0/5 | 4.1/5 | Improving | Feedback analysis | Monthly | Business Analyst | Green | None
Influence | Influencer Engagement | 95% | 93% | Stable | Influencer tracking | Monthly | Engagement Manager | Green | None
Resistance | Resistance Level | < 20% | 18% | Improving | Resistance assessment | Monthly | Change Manager | Green | None
Escalation | Issue Escalation Rate | < 10% | 8% | Stable | Issue tracking | Weekly | Project Manager | Green | None
Commitment | Commitment Level | 4.0/5 | 3.9/5 | Stable | Commitment survey | Quarterly | Engagement Manager | Yellow | Reinforce value