## Instructions & User Guide
PRODUCT - NEW PRODUCT LAUNCH AND DEVELOPMENT
Procurement Plan
PMI 2025 Standards Compliant
DOCUMENT OVERVIEW
This template manages all procurement activities for the Core Product Development System Modernization project, ensuring timely acquisition of goods and services.
KEY FEATURES
• Procurement item tracking
• Vendor management
• Budget and timeline monitoring
• PMI 2025 procurement standards
HOW TO USE THIS TEMPLATE
1. Review all tabs to understand the template structure
2. Fill in the yellow highlighted cells with your project-specific information
3. Do not modify formulas or calculated fields
4. Use dropdown menus where provided for consistency
5. Save regularly and maintain version control
6. Export to PDF for stakeholder distribution

## Procurement Plan
PRODUCT - NEW PRODUCT LAUNCH AND DEVELOPMENT - PROCUREMENT PLAN
Procurement_ID | Item_Description | Category | Vendor | Estimated_Cost | Actual_Cost | Required_Date | Delivery_Date | Status | Owner | Notes
PR-001 | Core Product Development Platform License | Software | Vendor A | 2500000 | 2450000 | 2025-08-01 | 2025-07-28 | Delivered | Procurement Manager | Negotiated 2% discount
PR-002 | Cloud Infrastructure Services | Infrastructure | AWS | 500000 | 0 | 2025-09-01 |  | In Progress | IT Manager | Annual contract
PR-003 | Security Assessment Services | Consulting | Security Firm B | 150000 | 0 | 2025-08-15 |  | Pending | Security Officer | RFP in review
PR-004 | Training Development Services | Training | Training Co C | 75000 | 0 | 2025-10-01 |  | Not Started | Training Manager | Awaiting budget approval