## Budget Summary
Product Development IMPLEMENTATION PROJECT - TRProductNING BUDGET ESTIMATES
2025 PMI Standards Compliant
Project Name: |  | Enterprise Product Development Implementation
Training Manager: |  | Emily Davis, CPTM
Budget Period: |  | January 2026 - December 2026
Last Updated: |  | 07/16/2025
TRProductNING BUDGET SUMMARY
Category | Estimated Budget | Actual Expenses | Remaining Budget | % Used
Personnel | $125,000.00 | $0.00
Materials & Supplies | $45,000.00 | $0.00
Facilities | $30,000.00 | $0.00
Technology & Equipment | $75,000.00 | $0.00
External Services | $85,000.00 | $0.00
Travel & Accommodations | $25,000.00 | $0.00
Contingency (10%) | $38,500.00 | $0.00
TOTAL
BUDGET METRICS
Total Training Budget
Training Cost per Employee |  | Based on 850 employees
Average Cost per Training Hour |  | Based on 1,870 total training hours
Budget Utilization |  | Percentage of budget used
Budget Variance |  | Remaining budget
BUDGET STATUS

## Personnel Budget
PERSONNEL BUDGET
Role | Hourly Rate | Estimated Hours | Total Cost | Actual Hours | Actual Cost | Variance
Training Manager | $75.00 | 480 |  | 0
Instructional Designer | $65.00 | 640 |  | 0
Technical SME - Data Science | $85.00 | 160 |  | 0
Technical SME - Product Engineering | $85.00 | 160 |  | 0
Technical SME - IT Operations | $75.00 | 120 |  | 0
Instructor - Technical | $70.00 | 320 |  | 0
Instructor - Business | $65.00 | 240 |  | 0
Training Coordinator | $45.00 | 320 |  | 0
LMS Administrator | $55.00 | 160 |  | 0
TOTAL

## Materials & Supplies
MATERIALS & SUPPLIES BUDGET
Item | Unit Cost | Quantity | Total Cost | Actual Quantity | Actual Cost | Variance
Participant Workbooks | $25.00 | 850 |  | 0
Instructor Guides | $45.00 | 15 |  | 0
Digital Content Licenses | $15.00 | 850 |  | 0
Training Lab Equipment | $1,500.00 | 10 |  | 0
Reference Materials | $35.00 | 100 |  | 0
Training Software Licenses | $75.00 | 50 |  | 0
Office Supplies | $500.00 | 1 |  | 0
Printing & Reproduction | $2,500.00 | 1 |  | 0
Certificates & Awards | $10.00 | 850 |  | 0
TOTAL

## External Services
EXTERNAL SERVICES BUDGET
Service | Unit Cost | Quantity | Total Cost | Actual Quantity | Actual Cost | Variance
E-learning Development | $15,000.00 | 2 |  | 0
Technical Training Vendor | $25,000.00 | 1 |  | 0
LMS Implementation | $20,000.00 | 1 |  | 0
External Instructors | $2,500.00 | 5 |  | 0
Training Evaluation Consultant | $7,500.00 | 1 |  | 0
Video Production Services | $5,000.00 | 2 |  | 0
TOTAL

## Course Budget
COURSE BUDGET BREAKDOWN
Course | Development Cost | Delivery Cost | Materials Cost | Total Cost | Cost per Participant | ROI Category
Product Development Fundamentals (Product-101) | $15,000.00 | $5,000.00 | $21,250.00 |  |  | Strategic
Product Development Platform Overview (Product-102) | $15,000.00 | $5,000.00 | $12,750.00 |  |  | Strategic
Data Analysis for Business (Product-201) | $8,000.00 | $7,500.00 | $1,125.00 |  |  | Business
Advanced Product Techniques (Product-301) | $12,000.00 | $10,000.00 | $625.00 |  |  | Technical
ProductOps for IT Teams (Product-302) | $12,000.00 | $10,000.00 | $875.00 |  |  | Technical
Model Validation & QA (Product-303) | $8,000.00 | $5,000.00 | $750.00 |  |  | Technical
Executive Overview (Product-401) | $5,000.00 | $2,500.00 | $375.00 |  |  | Strategic
Train-the-Trainer (Product-501) | $10,000.00 | $15,000.00 | $500.00 |  |  | Operational
TOTAL

## Budget Timeline
BUDGET TIMELINE (2026)
Budget Category | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Personnel | 10000 | 10000 | 15000 | 15000 | 15000 | 15000 | 10000 | 10000 | 10000 | 5000 | 5000 | 5000
Materials & Supplies | 15000 | 10000 | 5000 | 5000 | 2500 | 2500 | 1000 | 1000 | 1000 | 1000 | 500 | 500
Facilities | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Technology & Equipment | 25000 | 25000 | 5000 | 5000 | 2500 | 2500 | 2500 | 2500 | 1000 | 1000 | 1000 | 2000
External Services | 20000 | 20000 | 15000 | 10000 | 5000 | 5000 | 2500 | 2500 | 1000 | 1000 | 1000 | 2000
Travel & Accommodations | 1000 | 2000 | 3000 | 3000 | 3000 | 3000 | 2000 | 2000 | 2000 | 1000 | 1000 | 2000
Contingency | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500
Monthly Total
Cumulative Total