## Change Management Overview
CHANGE MANAGEMENT PLAN
CONSULTING Change Management Plan Project
Generated: July 16, 2025
PROJECT INFORMATION
Project Name: | Enterprise AI/ML Implementation
Change Manager: | Mark Thompson, CCMP
Change Methodology: | Prosci ADKAR Model
Affected Population: | 850 employees across 5 departments
Change Complexity: | High - Technology and Process Change
Change Duration: | 18 months (Jan 2025 - Jun 2026)
Change Budget: | $180,000 (6.3% of project budget)
CHANGE MANAGEMENT OBJECTIVES
1. Achieve 95% user adoption of new AI/ML systems within 6 months of go-live
2. Minimize business disruption during transition to new technology platform
3. Build organizational capability and confidence in AI/ML technologies
4. Establish sustainable change management practices for future initiatives
5. Ensure all affected employees receive appropriate training and support
6. Create positive stakeholder sentiment and enthusiasm for AI/ML transformation
CHANGE MANAGEMENT STRATEGY
• ADKAR Model: Focus on Awareness, Desire, Knowledge, Ability, and Reinforcement
• Stakeholder-Centric: Tailored approach based on stakeholder impact and influence
• Communication-Heavy: Multi-channel communication strategy with feedback loops
• Training-Intensive: Comprehensive training program with hands-on practice
• Support-Focused: Dedicated support resources during transition period
• Measurement-Driven: Regular assessment of change readiness and adoption

## Change Impact Assessment
CHANGE IMPACT ASSESSMENT
Stakeholder Group | Department | Population | Change Type | Impact Level | Current State | Future State | Readiness Level | Resistance Risk | Change Champion | Support Required | Priority
Data Scientists | Analytics | 25 | Technology | High | Manual processes | AI/ML automation | High | Low | Dr. Alex Rodriguez | Advanced training | High
Business Analysts | Business | 45 | Process | High | Traditional analysis | AI-powered insights | Medium | Medium | Lisa Wang | Process training | High
IT Operations | Technology | 35 | Technology | Medium | Legacy systems | Cloud-native platform | Medium | Medium | Chris Wilson | Technical training | Medium
End Users | Operations | 200 | Technology | Medium | Current systems | New AI interface | Low | High | Robert Taylor | User training | High
Management | Executive | 15 | Strategic | High | Traditional decisions | Data-driven decisions | High | Low | CEO | Executive briefings | Critical
Finance Team | Finance | 30 | Process | Medium | Manual reporting | Automated analytics | Medium | Medium | CFO | Process training | Medium
HR Team | Human Resources | 25 | Process | Low | Current processes | Enhanced analytics | Medium | Low | CHRO | Basic training | Low
Sales Team | Sales | 150 | Technology | Medium | CRM system | AI-enhanced CRM | Low | High | Sales Director | Sales training | High
Customer Service | Support | 120 | Technology | High | Manual support | AI-assisted support | Low | High | Support Manager | Intensive training | High
Quality Assurance | Technology | 35 | Process | Medium | Manual testing | AI-powered testing | Medium | Medium | Emily Davis | QA training | Medium
Compliance Team | Legal | 20 | Process | Medium | Manual compliance | Automated monitoring | Medium | Medium | Compliance Officer | Compliance training | Medium
External Partners | External | 100 | Technology | Low | Current interfaces | API integration | Low | Medium | Partnership Manager | Partner enablement | Low

## Change Activities
CHANGE MANAGEMENT ACTIVITIES
Activity ID | Activity Name | ADKAR Element | Target Audience | Start Date | End Date | Owner | Status | Completion % | Budget | Notes
CM-001 | Stakeholder Analysis | Awareness | All Stakeholders | 2025-01-15 | 2025-02-15 | Mark Thompson | Completed | 100% | $5,000 | Baseline assessment
CM-002 | Communication Strategy | Awareness | All Stakeholders | 2025-02-01 | 2025-02-28 | Communications Lead | Completed | 100% | $8,000 | Multi-channel approach
CM-003 | Executive Sponsorship | Awareness | Leadership | 2025-01-01 | 2025-12-31 | CEO | In Progress | 75% | $10,000 | Ongoing leadership
CM-004 | Change Champion Network | Desire | Champions | 2025-03-01 | 2025-04-30 | Mark Thompson | In Progress | 60% | $15,000 | 50 champions identified
CM-005 | Resistance Management | Desire | High Resistance Groups | 2025-04-01 | 2025-10-31 | Change Team | Planned | 0% | $12,000 | Targeted interventions
CM-006 | Training Needs Analysis | Knowledge | All Users | 2025-03-15 | 2025-04-15 | Training Manager | In Progress | 80% | $8,000 | Skills gap assessment
CM-007 | Training Program Development | Knowledge | All Users | 2025-04-15 | 2025-06-30 | Training Team | Planned | 0% | $25,000 | Multi-modal training
CM-008 | Training Delivery | Knowledge | All Users | 2025-07-01 | 2025-11-30 | Training Team | Planned | 0% | $35,000 | Phased rollout
CM-009 | Coaching and Support | Ability | End Users | 2025-09-01 | 2026-03-31 | Support Team | Planned | 0% | $20,000 | On-the-job support
CM-010 | Performance Monitoring | Reinforcement | All Users | 2025-12-01 | 2026-06-30 | Analytics Team | Planned | 0% | $10,000 | Adoption metrics
CM-011 | Recognition Program | Reinforcement | Early Adopters | 2026-01-01 | 2026-06-30 | HR Team | Planned | 0% | $15,000 | Incentive program
CM-012 | Continuous Improvement | Reinforcement | All Stakeholders | 2026-01-01 | 2026-12-31 | Change Team | Planned | 0% | $12,000 | Feedback integration