## Open Action Items
ENTERPRISE RESOURCE PLANNING IMPLEMENTATION - OPEN ACTION ITEM LOG
Project: ERP Implementation
Date: July 31, 2025
PMI 2025 Standards Compliant
ACTION ITEM TRACKING
Action_ID | Action_Description | Priority | Status | Owner | Due_Date | Completion_Date | Progress_% | Dependencies | Notes
AI001 | Complete business process standardization and documentation | High | In Progress | ERP Project Manager | 2025-08-30 |  | 25 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI002 | Execute comprehensive data cleansing and validation procedures | High | In Progress | Business Process Owners | 2025-09-04 |  | 32 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI003 | Deploy user training program with hands-on practice sessions | High | In Progress | IT Architects | 2025-09-09 |  | 39 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI004 | Implement continuous change management communication strategy | High | In Progress | End Users | 2025-09-14 |  | 46 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI005 | Establish dedicated integration testing environment and procedures | Medium | In Progress | Change Managers | 2025-09-19 |  | 53 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI006 | Ensure executive sponsorship visibility through regular updates | Medium | In Progress | Executive Sponsors | 2025-09-24 |  | 60 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI007 | Finalize customization decisions with long-term impact assessment | Medium | Not Started | ERP Project Manager | 2025-09-29 |  | 67 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI008 | Prepare 24/7 go-live support team and escalation procedures | Medium | Not Started | Business Process Owners | 2025-10-04 |  | 74 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI009 | Complete performance testing with realistic scenarios | Low | Not Started | IT Architects | 2025-10-09 |  | 81 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success
AI010 | Plan post-implementation optimization and continuous improvement | Low | Completed | End Users | 2025-10-14 | 2025-07-31 | 100 | Dependent on ERP Implementation milestone completion | Critical action for Enterprise Resource Planning Implementation success