## Communications Overview
COMMUNICATIONS MANAGEMENT PLAN
EDUCATION Communication Plan Project
Generated: July 16, 2025
PROJECT INFORMATION
Project Name: | Enterprise AI/ML Implementation
Project Manager: | Sarah Johnson, PMP
Communications Lead: | Jennifer Martinez
Project Duration: | 18 months
Stakeholder Count: | 45 stakeholders
Communication Channels: | 8 primary channels
Reporting Frequency: | Weekly, Monthly, Quarterly
COMMUNICATION OBJECTIVES
1. Ensure all stakeholders receive timely, accurate, and relevant project information
2. Maintain transparent communication about project progress, risks, and issues
3. Facilitate effective decision-making through structured reporting and escalation
4. Build stakeholder confidence and support through consistent engagement
5. Enable seamless knowledge transfer and change management activities
6. Establish feedback mechanisms for continuous communication improvement
COMMUNICATION PRINCIPLES
• Transparency: Open and honest communication about project status
• Timeliness: Information delivered when stakeholders need it
• Relevance: Content tailored to audience needs and interests
• Consistency: Standardized formats and messaging across channels
• Two-way: Encourage feedback and dialogue, not just broadcasting
• Accessibility: Multiple channels to accommodate different preferences

## Stakeholder Communications
STAKEHOLDER COMMUNICATIONS MATRIX
Stakeholder Name | Role/Title | Department | Interest Level | Influence Level | Communication Needs | Preferred Method | Frequency | Key Messages | Responsible Person | Status | Notes
John Smith | CEO | Executive | High | High | Strategic updates, ROI | Executive briefing | Monthly | Business value, progress | Sarah Johnson | Active | Key decision maker
Maria Garcia | CTO | Technology | High | High | Technical progress, risks | Technical review | Bi-weekly | Architecture, implementation | Alex Rodriguez | Active | Technical sponsor
David Chen | CFO | Finance | Medium | High | Budget, costs, ROI | Financial report | Monthly | Cost control, benefits | Sarah Johnson | Active | Budget approver
Lisa Wang | CHRO | HR | Medium | Medium | Change impact, training | Status meeting | Bi-weekly | People impact, readiness | Mark Thompson | Active | Change sponsor
Robert Taylor | Business Director | Operations | High | Medium | Business impact, timeline | Business review | Weekly | Operational readiness | Lisa Wang | Active | End user champion
Jennifer Liu | Data Director | Analytics | High | Medium | Data strategy, quality | Technical meeting | Weekly | Data governance, quality | Thomas Lee | Active | Data owner
Michael Johnson | IT Director | Technology | Medium | Medium | Infrastructure, security | IT review | Bi-weekly | Technical readiness | Chris Wilson | Active | Infrastructure lead
Sarah Brown | Compliance Officer | Legal | Medium | Medium | Regulatory compliance | Compliance review | Monthly | Risk mitigation, compliance | Sarah Johnson | Active | Risk oversight
Kevin Zhang | Project Team | Technology | High | Low | Task assignments, progress | Team standup | Daily | Sprint progress, blockers | Mike Chen | Active | Development team
Amanda Davis | End Users | Business | High | Low | Training, system changes | User communication | Bi-weekly | System benefits, training | Mark Thompson | Active | User representatives

## Communication Schedule
COMMUNICATION SCHEDULE & CALENDAR
Communication Type | Audience | Purpose | Method | Frequency | Day/Date | Time | Duration | Owner | Participants | Status
Executive Briefing | C-Suite | Strategic updates | Presentation | Monthly | 1st Monday | 9:00 AM | 60 min | Sarah Johnson | CEO, CTO, CFO | Scheduled
Steering Committee | Project Board | Governance oversight | Meeting | Bi-weekly | Tuesdays | 2:00 PM | 90 min | Sarah Johnson | Steering Committee | Scheduled
Technical Review | Technical Team | Technical progress | Meeting | Weekly | Thursdays | 10:00 AM | 60 min | Alex Rodriguez | Tech Leads | Scheduled
Team Standup | Project Team | Daily coordination | Standup | Daily | Mon-Fri | 9:00 AM | 15 min | Mike Chen | Development Team | Scheduled
Status Report | All Stakeholders | Progress update | Email/Portal | Weekly | Fridays | 5:00 PM | N/A | Sarah Johnson | All Stakeholders | Scheduled
Risk Review | Risk Committee | Risk management | Meeting | Bi-weekly | Wednesdays | 3:00 PM | 45 min | Sarah Johnson | Risk Owners | Scheduled
User Communication | End Users | Change readiness | Newsletter | Bi-weekly | Fridays | 12:00 PM | N/A | Mark Thompson | End Users | Scheduled
Vendor Updates | Vendors | Vendor coordination | Call | Weekly | Mondays | 11:00 AM | 30 min | Procurement Lead | Key Vendors | Scheduled
Quality Review | QA Team | Quality assurance | Meeting | Weekly | Wednesdays | 1:00 PM | 45 min | Emily Davis | QA Team | Scheduled
Change Board | Change Committee | Change approval | Meeting | Weekly | Tuesdays | 4:00 PM | 60 min | Sarah Johnson | Change Board | Scheduled

## Communication Templates
COMMUNICATION TEMPLATES & STANDARDS
Template Name | Purpose | Audience | Format | Frequency | Owner | Approval Required | Distribution Method
Weekly Status Report | Progress communication | All Stakeholders | Email/PDF | Weekly | Sarah Johnson | No | Email + Portal
Executive Dashboard | High-level metrics | Executives | PowerPoint | Monthly | Sarah Johnson | Yes | Presentation
Technical Update | Technical progress | Technical Team | Document | Bi-weekly | Alex Rodriguez | No | Email
Risk Register Update | Risk communication | Risk Committee | Excel | Bi-weekly | Risk Manager | Yes | Email + Meeting
Change Notice | Change communication | Affected Stakeholders | Form | As needed | Change Manager | Yes | Email + Portal
User Newsletter | End user engagement | End Users | Newsletter | Bi-weekly | Mark Thompson | No | Email + Intranet
Vendor Communication | Vendor coordination | Vendors | Email | Weekly | Procurement Lead | No | Email
Issue Escalation | Issue communication | Management | Email/Call | As needed | Project Manager | No | Email + Call
Milestone Report | Achievement communication | All Stakeholders | Report | Monthly | Sarah Johnson | Yes | Email + Portal
Lessons Learned | Knowledge sharing | Project Team | Document | Quarterly | Sarah Johnson | No | Meeting + Portal

## Communication Metrics
COMMUNICATION EFFECTIVENESS METRICS
Metric Category | Metric Name | Target | Current | Variance | Trend | Measurement Method | Frequency | Owner | Action Required
Engagement | Email Open Rate | 85% | 78% | -7% | Declining | Email Analytics | Weekly | Comm Lead | Improve subject lines
Engagement | Meeting Attendance | 90% | 92% | +2% | Stable | Meeting Records | Weekly | Meeting Owners | None
Satisfaction | Communication Survey | 4.0/5 | 3.8/5 | -0.2 | Declining | Quarterly Survey | Quarterly | Comm Lead | Address feedback
Timeliness | Report Delivery | 100% | 95% | -5% | Stable | Delivery Tracking | Weekly | Report Owners | Process improvement
Quality | Information Accuracy | 98% | 96% | -2% | Stable | Feedback Analysis | Monthly | Content Owners | Review process
Reach | Stakeholder Coverage | 100% | 98% | -2% | Stable | Distribution Lists | Monthly | Comm Lead | Update lists
Feedback | Response Rate | 70% | 65% | -5% | Declining | Response Tracking | Monthly | Comm Lead | Encourage participation
Escalation | Issue Resolution Time | 24 hrs | 18 hrs | +6 hrs | Improving | Issue Tracking | Weekly | Project Manager | None
Knowledge | Information Retention | 80% | 75% | -5% | Stable | Knowledge Tests | Quarterly | Training Lead | Reinforce key messages
Channel | Channel Effectiveness | 4.0/5 | 4.2/5 | +0.2 | Improving | Channel Survey | Quarterly | Comm Lead | None

## Escalation Matrix
COMMUNICATION ESCALATION MATRIX
Issue Type | Severity Level | Initial Contact | Escalation Level 1 | Escalation Level 2 | Escalation Level 3 | Timeframe | Communication Method
Technical Issue | Low | Tech Lead | Project Manager | CTO | CEO | 24-48 hours | Email + Meeting
Technical Issue | Medium | Tech Lead | Project Manager | CTO | CEO | 4-8 hours | Email + Call
Technical Issue | High | Project Manager | CTO | CEO | Board | 1-2 hours | Call + Meeting
Budget Variance | Low | Project Manager | Finance Director | CFO | CEO | 24 hours | Email + Report
Budget Variance | Medium | Project Manager | CFO | CEO | Board | 4 hours | Call + Meeting
Budget Variance | High | CFO | CEO | Board | Audit Committee | 1 hour | Emergency Meeting
Schedule Delay | Low | Project Manager | Sponsor | Steering Committee | Executive Team | 24 hours | Email + Update
Schedule Delay | Medium | Project Manager | Steering Committee | Executive Team | Board | 8 hours | Meeting + Report
Schedule Delay | High | Sponsor | Executive Team | Board | Chairman | 2 hours | Emergency Meeting
Quality Issue | Low | QA Lead | Project Manager | Quality Director | CTO | 24 hours | Email + Report
Quality Issue | Medium | Project Manager | Quality Director | CTO | CEO | 4 hours | Call + Meeting
Quality Issue | High | Quality Director | CTO | CEO | Board | 1 hour | Emergency Meeting
Stakeholder Conflict | Low | Project Manager | Sponsor | HR Director | Executive Team | 48 hours | Meeting + Mediation
Stakeholder Conflict | Medium | Sponsor | HR Director | Executive Team | CEO | 8 hours | Facilitated Meeting
Stakeholder Conflict | High | HR Director | CEO | Board | External Mediator | 2 hours | Executive Session