## Formula Documentation
GOVERNMENT IMPLEMENTATION WBS - COMPREHENSIVE PROJECT PLAN
PROJECT OVERVIEW:
This GOVERNMENT WBS WBS contains 11 comprehensive phases with 178 detailed tasks,
meeting workflows, budget management, steady-state support, and professional formatting.
PHASES INCLUDED:
1. Government Project Initiation - Charter development, stakeholder management, initial planning
2. Government Budget Planning and Management - Cost estimation, budget controls, tracking
3. AI/ML Design and Planning - Requirements analysis, system design, documentation
4. AI/ML Compliance and Regulatory - Compliance frameworks, regulatory approvals
5. AI/ML Procurement and Contracting - Vendor selection, procurement, equipment
6. AI/ML Implementation - Installation, configuration, integration, testing
7. AI/ML Testing and Validation - System testing, performance validation, acceptance
8. AI/ML Documentation and Training - Technical documentation, user training
9. AI/ML Walkthrough and Handover - Deployment preparation, system handover
10. AI/ML Project Close-out - Administrative closure, lessons learned, final reporting
11. AI/ML Steady-State Support - Production support, maintenance, continuous improvement
AI/ML SPECIFIC FEATURES:
- Process analysis and reengineering - Workflow optimization and automation - Performance metrics and KPI implementation - Change management and training - Quality assurance and control - Continuous improvement processes - AI/ML excellence initiatives
PMI 2025 COMPLIANCE:
This WBS follows PMI 2025 standards for project management

## Operational_Implementation_WBS
ID | WBS_Code | Task_Name | Task_Type | Percent_Complete | Duration | Start_Date | Finish_Date | Predecessors | Successors | Resources | Baseline_Start_Date | Baseline_Finish_Date | Baseline_Duration | Duration_Variance | Schedule_Variance | Status | Risk_Level | Notes
1 | 1.0 | AI/ML Project Initiation [Deliverable: Project Initiation Report] | Phase |  |  | 2025-01-01 | 2025-01-20 |  | 18 | Project Manager | 2025-01-01 | 2025-01-20 |  |  |  | In Progress | Medium | Project initiation phase
2 | 1.1 | AI/ML Project Charter Development [Deliverable: Signed Project Charter] | Task | 75% |  | 2025-01-01 | 2025-01-05 |  | 7 | Project Manager | 2025-01-01 | 2025-01-05 |  |  |  | In Progress | Low | Charter development
3 | 1.1.1 | Business Case Analysis [Deliverable: Business Case Document] | Sub-Task | 100% |  | 2025-01-01 | 2025-01-02 |  | 4 | Business Analyst | 2025-01-01 | 2025-01-02 |  |  |  | Complete | Low | Business case complete
4 | 1.1.2 | AI/ML Requirements Definition [Deliverable: Requirements Document] | Sub-Task | 75% |  | 2025-01-02 | 2025-01-03 | 3 | 5 | AI/ML Analyst | 2025-01-02 | 2025-01-03 |  |  |  | In Progress | Medium | Requirements defined
5 | 1.1.3 | Scope Definition and Objectives [Deliverable: Project Scope Document] | Sub-Task | 50% |  | 2025-01-03 | 2025-01-04 | 4 | 6 | Project Manager | 2025-01-03 | 2025-01-04 |  |  |  | In Progress | Medium | Scope being defined
6 | 1.1.4 | Charter Review Meeting [Deliverable: Meeting Minutes & Approval] | Sub-Task | 25% |  | 2025-01-05 | 2025-01-05 | 5 | 7 | Stakeholders | 2025-01-05 | 2025-01-05 |  |  |  | Not Started | Low | Charter review pending
7 | 1.2 | AI/ML Stakeholder Management [Deliverable: Stakeholder Management Plan] | Task | 50% |  | 2025-01-06 | 2025-01-13 | 6 | 12 | Project Manager | 2025-01-06 | 2025-01-13 |  |  |  | In Progress | Medium | Stakeholder engagement
8 | 1.2.1 | Stakeholder Identification [Deliverable: Stakeholder Register] | Sub-Task | 75% |  | 2025-01-06 | 2025-01-07 | 6 | 9 | Project Manager | 2025-01-06 | 2025-01-07 |  |  |  | In Progress | Low | Stakeholders identified
9 | 1.2.2 | Stakeholder Analysis [Deliverable: Stakeholder Analysis Matrix] | Sub-Task | 50% |  | 2025-01-07 | 2025-01-08 | 8 | 10 | Business Analyst | 2025-01-07 | 2025-01-08 |  |  |  | In Progress | Medium | Analysis in progress
10 | 1.2.3 | Engagement Plan Development [Deliverable: Engagement Strategy] | Sub-Task | 25% |  | 2025-01-08 | 2025-01-09 | 9 | 11 | Communications Lead | 2025-01-08 | 2025-01-09 |  |  |  | Not Started | Medium | Plan development
11 | 1.2.4 | Stakeholder Kickoff Meeting [Deliverable: Kickoff Meeting Minutes] | Sub-Task | 0% |  | 2025-01-10 | 2025-01-11 | 10 | 12 | All Stakeholders | 2025-01-10 | 2025-01-11 |  |  |  | Not Started | Low | Kickoff pending
12 | 1.3 | AI/ML Initial Planning [Deliverable: Initial Project Plan] | Task | 25% |  | 2025-01-14 | 2025-01-20 | 11 | 17 | Project Manager | 2025-01-14 | 2025-01-20 |  |  |  | In Progress | Medium | Initial planning
13 | 1.3.1 | Risk Assessment [Deliverable: Risk Register] | Sub-Task | 50% |  | 2025-01-14 | 2025-01-15 | 11 | 14 | Risk Manager | 2025-01-14 | 2025-01-15 |  |  |  | In Progress | High | Risk assessment
14 | 1.3.2 | Resource Planning [Deliverable: Resource Allocation Plan] | Sub-Task | 25% |  | 2025-01-15 | 2025-01-16 | 13 | 15 | Resource Manager | 2025-01-15 | 2025-01-16 |  |  |  | Not Started | Medium | Resource planning
15 | 1.3.3 | Communication Plan [Deliverable: Communication Strategy] | Sub-Task | 0% |  | 2025-01-16 | 2025-01-17 | 14 | 16 | Communications Lead | 2025-01-16 | 2025-01-17 |  |  |  | Not Started | Low | Communication plan
16 | 1.3.4 | Quality Management Plan [Deliverable: Quality Assurance Plan] | Sub-Task | 0% |  | 2025-01-17 | 2025-01-17 | 15 | 17 | Quality Manager | 2025-01-17 | 2025-01-17 |  |  |  | Not Started | Medium | Quality planning
17 | 1.4 | AI/ML Project Initiation Approval [Deliverable: Signed Initiation Approval] | Milestone | 0% |  | 2025-01-20 | 2025-01-20 | 16 | 18 | Sponsor | 2025-01-20 | 2025-01-20 |  |  |  | Not Started | Low | Approval milestone
18 | 2.0 | AI/ML Budget Planning and Management [Deliverable: Budget Management Report] | Phase |  |  | 2025-01-21 | 2025-02-04 | 17 | 29 | Finance Manager | 2025-01-21 | 2025-02-04 |  |  |  | In Progress | Medium | Budget planning phase
19 | 2.1 | AI/ML Budget Development [Deliverable: Approved Budget Plan] | Task | 60% |  | 2025-01-21 | 2025-01-28 | 17 | 24 | Finance Manager | 2025-01-21 | 2025-01-28 |  |  |  | In Progress | Medium | Budget development
20 | 2.1.1 | Cost Estimation [Deliverable: Cost Estimation Report] | Sub-Task | 75% |  | 2025-01-21 | 2025-01-23 | 17 | 21 | Cost Analyst | 2025-01-21 | 2025-01-23 |  |  |  | In Progress | Medium | Cost estimation
21 | 2.1.2 | AI/ML Equipment Costs [Deliverable: Equipment Cost Report] | Sub-Task | 50% |  | 2025-01-23 | 2025-01-24 | 20 | 22 | AI/ML Procurement Lead | 2025-01-23 | 2025-01-24 |  |  |  | In Progress | High | Equipment costs
22 | 2.1.3 | Implementation and Training Costs [Deliverable: Implementation Cost Analysis] | Sub-Task | 25% |  | 2025-01-24 | 2025-01-25 | 21 | 23 | Training Manager | 2025-01-24 | 2025-01-25 |  |  |  | Not Started | Medium | Implementation costs
23 | 2.1.4 | Budget Review Meeting [Deliverable: Budget Review Minutes] | Sub-Task | 0% |  | 2025-01-25 | 2025-01-25 | 22 | 24 | Finance Team | 2025-01-25 | 2025-01-25 |  |  |  | Not Started | Low | Budget review
24 | 2.2 | AI/ML Budget Control and Tracking [Deliverable: Budget Control System] | Task | 20% |  | 2025-01-29 | 2025-02-04 | 23 | 28 | Finance Manager | 2025-01-29 | 2025-02-04 |  |  |  | In Progress | Medium | Budget control
25 | 2.2.1 | Budget Baseline Establishment [Deliverable: Budget Baseline Document] | Sub-Task | 50% |  | 2025-01-29 | 2025-01-30 | 23 | 26 | Finance Analyst | 2025-01-29 | 2025-01-30 |  |  |  | In Progress | Low | Baseline setup
26 | 2.2.2 | Budget Monitoring Procedures [Deliverable: Monitoring Procedures Manual] | Sub-Task | 25% |  | 2025-01-30 | 2025-01-31 | 25 | 27 | Finance Manager | 2025-01-30 | 2025-01-31 |  |  |  | Not Started | Medium | Monitoring procedures
27 | 2.2.3 | Change Control Process [Deliverable: Change Control Procedures] | Sub-Task | 0% |  | 2025-01-31 | 2025-02-01 | 26 | 28 | Change Manager | 2025-01-31 | 2025-02-01 |  |  |  | Not Started | Medium | Change control
28 | 2.3 | AI/ML Budget Management Approval [Deliverable: Budget Management Approval] | Milestone | 0% |  | 2025-02-04 | 2025-02-04 | 27 | 29 | Finance Director | 2025-02-04 | 2025-02-04 |  |  |  | Not Started | Low | Budget approval milestone
29 | 3.0 | AI/ML Design and Planning [Deliverable: Design Package] | Phase |  |  | 2025-02-05 | 2025-03-01 | 28 | 43 | AI/ML Solution Architect | 2025-02-05 | 2025-03-01 |  |  |  | In Progress | High | Design phase
30 | 3.1 | AI/ML Requirements Analysis [Deliverable: Requirements Specification] | Task | 60% |  | 2025-02-05 | 2025-02-14 | 28 | 35 | Business Analyst | 2025-02-05 | 2025-02-14 |  |  |  | In Progress | Medium | Requirements analysis
31 | 3.1.1 | Functional Requirements [Deliverable: Functional Requirements Document] | Sub-Task | 75% |  | 2025-02-05 | 2025-02-08 | 28 | 32 | Business Analyst | 2025-02-05 | 2025-02-08 |  |  |  | In Progress | Medium | Functional requirements
32 | 3.1.2 | Non-Functional Requirements [Deliverable: Non-Functional Requirements Document] | Sub-Task | 50% |  | 2025-02-08 | 2025-02-10 | 31 | 33 | Technical Architect | 2025-02-08 | 2025-02-10 |  |  |  | In Progress | High | Non-functional requirements
33 | 3.1.3 | Requirements Validation [Deliverable: Validated Requirements] | Sub-Task | 25% |  | 2025-02-10 | 2025-02-12 | 32 | 34 | Quality Analyst | 2025-02-10 | 2025-02-12 |  |  |  | Not Started | Medium | Requirements validation
34 | 3.1.4 | Requirements Approval Meeting [Deliverable: Approved Requirements] | Sub-Task | 0% |  | 2025-02-14 | 2025-02-14 | 33 | 35 | Stakeholders | 2025-02-14 | 2025-02-14 |  |  |  | Not Started | Low | Requirements approval
35 | 3.2 | AI/ML System Design [Deliverable: System Design Document] | Task | 30% |  | 2025-02-15 | 2025-02-26 | 34 | 40 | Solution Architect | 2025-02-15 | 2025-02-26 |  |  |  | In Progress | High | System design
36 | 3.2.1 | Architecture Design [Deliverable: Architecture Blueprint] | Sub-Task | 50% |  | 2025-02-15 | 2025-02-19 | 34 | 37 | Solution Architect | 2025-02-15 | 2025-02-19 |  |  |  | In Progress | High | Architecture design
37 | 3.2.2 | Interface Design [Deliverable: Interface Specifications] | Sub-Task | 25% |  | 2025-02-19 | 2025-02-22 | 36 | 38 | UI/UX Designer | 2025-02-19 | 2025-02-22 |  |  |  | Not Started | Medium | Interface design
38 | 3.2.3 | Security Design [Deliverable: Security Architecture] | Sub-Task | 0% |  | 2025-02-22 | 2025-02-24 | 37 | 39 | Security Architect | 2025-02-22 | 2025-02-24 |  |  |  | Not Started | High | Security design
39 | 3.2.4 | Design Review Meeting [Deliverable: Approved Design] | Sub-Task | 0% |  | 2025-02-26 | 2025-02-26 | 38 | 40 | Design Team | 2025-02-26 | 2025-02-26 |  |  |  | Not Started | Medium | Design review
40 | 3.3 | AI/ML Documentation [Deliverable: Design Documentation Package] | Task | 10% |  | 2025-02-27 | 2025-03-01 | 39 | 42 | Technical Writer | 2025-02-27 | 2025-03-01 |  |  |  | Not Started | Low | Documentation
41 | 3.3.1 | Technical Documentation [Deliverable: Technical Specifications] | Sub-Task | 0% |  | 2025-02-27 | 2025-02-28 | 39 | 42 | Technical Writer | 2025-02-27 | 2025-02-28 |  |  |  | Not Started | Low | Technical docs
42 | 3.4 | AI/ML Design Approval [Deliverable: Signed Design Approval] | Milestone | 0% |  | 2025-03-01 | 2025-03-01 | 41 | 43 | Design Authority | 2025-03-01 | 2025-03-01 |  |  |  | Not Started | Medium | Design approval milestone
43 | 4.0 | AI/ML Compliance and Regulatory [Deliverable: Compliance Report] | Phase |  |  | 2025-03-02 | 2025-03-17 | 42 | 59 | Compliance Officer | 2025-03-02 | 2025-03-17 |  |  |  | Not Started | High | Compliance phase
44 | 4.1 | AI/ML Compliance Assessment [Deliverable: Compliance Assessment Report] | Task | 40% |  | 2025-03-02 | 2025-03-07 | 42 | 50 | Compliance Officer | 2025-03-02 | 2025-03-07 |  |  |  | Not Started | High | Compliance assessment
45 | 4.1.1 | Regulatory Framework Review [Deliverable: Framework Assessment] | Sub-Task | 50% |  | 2025-03-02 | 2025-03-03 | 42 | 46 | Compliance Analyst | 2025-03-02 | 2025-03-03 |  |  |  | Not Started | High | Framework review
46 | 4.1.2 | Gap Analysis [Deliverable: Gap Analysis Report] | Sub-Task | 25% |  | 2025-03-03 | 2025-03-04 | 45 | 47 | Compliance Analyst | 2025-03-03 | 2025-03-04 |  |  |  | Not Started | High | Gap analysis
47 | 4.1.3 | Compliance Plan Development [Deliverable: Compliance Plan] | Sub-Task | 0% |  | 2025-03-04 | 2025-03-05 | 46 | 48 | Compliance Manager | 2025-03-04 | 2025-03-05 |  |  |  | Not Started | Medium | Compliance planning
48 | 4.1.4 | Internal Review Meeting [Deliverable: Internal Review Report] | Sub-Task | 0% |  | 2025-03-06 | 2025-03-06 | 47 | 49 | Internal Team | 2025-03-06 | 2025-03-06 |  |  |  | Not Started | Medium | Internal review
49 | 4.1.5 | Stakeholder Review Meeting [Deliverable: Stakeholder Feedback] | Sub-Task | 0% |  | 2025-03-07 | 2025-03-07 | 48 | 50 | Stakeholders | 2025-03-07 | 2025-03-07 |  |  |  | Not Started | Low | Stakeholder review
50 | 4.2 | AI/ML Regulatory Approvals [Deliverable: Regulatory Approval Documents] | Task | 20% |  | 2025-03-08 | 2025-03-15 | 49 | 57 | Regulatory Manager | 2025-03-08 | 2025-03-15 |  |  |  | Not Started | Medium | Regulatory approvals
51 | 4.2.1 | Regulatory Submission Preparation [Deliverable: Submission Package] | Sub-Task | 25% |  | 2025-03-08 | 2025-03-10 | 49 | 52 | Regulatory Specialist | 2025-03-08 | 2025-03-10 |  |  |  | Not Started | Medium | Submission prep
52 | 4.2.2 | Regulatory Authority Engagement [Deliverable: Authority Correspondence] | Sub-Task | 0% |  | 2025-03-10 | 2025-03-12 | 51 | 53 | Regulatory Manager | 2025-03-10 | 2025-03-12 |  |  |  | Not Started | High | Authority engagement
53 | 4.2.3 | Technical Review [Deliverable: Technical Review Report] | Sub-Task | 0% |  | 2025-03-12 | 2025-03-13 | 52 | 54 | Technical Team | 2025-03-12 | 2025-03-13 |  |  |  | Not Started | Medium | Technical review
54 | 4.2.4 | Quality Review [Deliverable: Quality Assurance Report] | Sub-Task | 0% |  | 2025-03-13 | 2025-03-14 | 53 | 55 | Quality Team | 2025-03-13 | 2025-03-14 |  |  |  | Not Started | Medium | Quality review
55 | 4.2.5 | Final Approval Meeting [Deliverable: Final Approval Document] | Sub-Task | 0% |  | 2025-03-15 | 2025-03-15 | 54 | 56 | Approval Authority | 2025-03-15 | 2025-03-15 |  |  |  | Not Started | High | Final approval
56 | 4.3 | AI/ML Compliance Documentation [Deliverable: Compliance Documentation] | Task | 10% |  | 2025-03-16 | 2025-03-17 | 55 | 58 | Documentation Team | 2025-03-16 | 2025-03-17 |  |  |  | Not Started | Low | Compliance documentation
57 | 4.3.1 | Process Documentation [Deliverable: Process Documentation] | Sub-Task | 0% |  | 2025-03-16 | 2025-03-16 | 55 | 58 | Process Analyst | 2025-03-16 | 2025-03-16 |  |  |  | Not Started | Low | Process docs
58 | 4.4 | AI/ML Compliance Approval [Deliverable: Signed Compliance Approval] | Milestone | 0% |  | 2025-03-17 | 2025-03-17 | 57 | 59 | Compliance Authority | 2025-03-17 | 2025-03-17 |  |  |  | Not Started | Medium | Compliance approval milestone
59 | 5.0 | AI/ML Procurement and Contracting [Deliverable: Procurement Package] | Phase |  |  | 2025-03-18 | 2025-04-01 | 58 | 74 | Procurement Manager | 2025-03-18 | 2025-04-01 |  |  |  | Not Started | Medium | Procurement phase
60 | 5.1 | AI/ML Vendor Selection [Deliverable: Selected Vendor List] | Task | 30% |  | 2025-03-18 | 2025-03-24 | 58 | 67 | Procurement Manager | 2025-03-18 | 2025-03-24 |  |  |  | Not Started | Medium | Vendor selection
61 | 5.1.1 | Vendor Research [Deliverable: Vendor Research Report] | Sub-Task | 40% |  | 2025-03-18 | 2025-03-19 | 58 | 62 | Procurement Analyst | 2025-03-18 | 2025-03-19 |  |  |  | Not Started | Low | Vendor research
62 | 5.1.2 | RFP Development [Deliverable: Request for Proposal] | Sub-Task | 20% |  | 2025-03-19 | 2025-03-20 | 61 | 63 | Procurement Specialist | 2025-03-19 | 2025-03-20 |  |  |  | Not Started | Medium | RFP development
63 | 5.1.3 | Vendor Evaluation [Deliverable: Vendor Evaluation Matrix] | Sub-Task | 0% |  | 2025-03-20 | 2025-03-22 | 62 | 64 | Evaluation Team | 2025-03-20 | 2025-03-22 |  |  |  | Not Started | High | Vendor evaluation
64 | 5.1.4 | Vendor Selection Meeting [Deliverable: Vendor Selection Decision] | Sub-Task | 0% |  | 2025-03-23 | 2025-03-23 | 63 | 65 | Selection Committee | 2025-03-23 | 2025-03-23 |  |  |  | Not Started | Medium | Vendor selection
65 | 5.1.5 | Contract Negotiation [Deliverable: Negotiated Contract Terms] | Sub-Task | 0% |  | 2025-03-24 | 2025-03-24 | 64 | 66 | Legal Team | 2025-03-24 | 2025-03-24 |  |  |  | Not Started | High | Contract negotiation
66 | 5.1.6 | Contract Finalization Meeting [Deliverable: Signed Contracts] | Sub-Task | 0% |  | 2025-03-24 | 2025-03-24 | 65 | 67 | Contract Team | 2025-03-24 | 2025-03-24 |  |  |  | Not Started | Medium | Contract finalization
67 | 5.2 | AI/ML Equipment Procurement [Deliverable: Procured Equipment] | Task | 10% |  | 2025-03-25 | 2025-03-30 | 66 | 72 | Equipment Manager | 2025-03-25 | 2025-03-30 |  |  |  | Not Started | High | Equipment procurement
68 | 5.2.1 | Equipment Specification [Deliverable: Equipment Specifications] | Sub-Task | 20% |  | 2025-03-25 | 2025-03-26 | 66 | 69 | Technical Specialist | 2025-03-25 | 2025-03-26 |  |  |  | Not Started | Medium | Equipment specs
69 | 5.2.2 | Purchase Order Processing [Deliverable: Purchase Orders] | Sub-Task | 0% |  | 2025-03-26 | 2025-03-27 | 68 | 70 | Procurement Officer | 2025-03-26 | 2025-03-27 |  |  |  | Not Started | Medium | Purchase orders
70 | 5.2.3 | Delivery Coordination [Deliverable: Delivery Schedule] | Sub-Task | 0% |  | 2025-03-27 | 2025-03-28 | 69 | 71 | Logistics Coordinator | 2025-03-27 | 2025-03-28 |  |  |  | Not Started | High | Delivery coordination
71 | 5.2.4 | Equipment Inspection [Deliverable: Inspection Report] | Sub-Task | 0% |  | 2025-03-29 | 2025-03-29 | 70 | 72 | Quality Inspector | 2025-03-29 | 2025-03-29 |  |  |  | Not Started | Medium | Equipment inspection
72 | 5.3 | AI/ML Procurement Documentation [Deliverable: Procurement Documentation] | Task | 0% |  | 2025-03-31 | 2025-04-01 | 71 | 73 | Documentation Team | 2025-03-31 | 2025-04-01 |  |  |  | Not Started | Low | Procurement documentation
73 | 5.4 | AI/ML Procurement Completion [Deliverable: Procurement Completion Certificate] | Milestone | 0% |  | 2025-04-01 | 2025-04-01 | 72 | 74 | Procurement Authority | 2025-04-01 | 2025-04-01 |  |  |  | Not Started | Low | Procurement completion milestone
74 | 6.0 | AI/ML Implementation [Deliverable: Implemented System] | Phase |  |  | 2025-04-02 | 2025-05-01 | 73 | 99 | Implementation Manager | 2025-04-02 | 2025-05-01 |  |  |  | Not Started | High | Implementation phase
75 | 6.1 | AI/ML Installation and Setup [Deliverable: Installed System] | Task | 15% |  | 2025-04-02 | 2025-04-11 | 73 | 85 | Installation Team | 2025-04-02 | 2025-04-11 |  |  |  | Not Started | High | Installation and setup
76 | 6.1.1 | Site Preparation [Deliverable: Prepared Site] | Sub-Task | 20% |  | 2025-04-02 | 2025-04-03 | 73 | 77 | Site Manager | 2025-04-02 | 2025-04-03 |  |  |  | Not Started | Medium | Site preparation
77 | 6.1.2 | Equipment Installation [Deliverable: Installed Equipment] | Sub-Task | 10% |  | 2025-04-03 | 2025-04-06 | 76 | 78 | Installation Technician | 2025-04-03 | 2025-04-06 |  |  |  | Not Started | High | Equipment installation
78 | 6.1.3 | System Configuration [Deliverable: Configured System] | Sub-Task | 5% |  | 2025-04-06 | 2025-04-08 | 77 | 79 | Configuration Specialist | 2025-04-06 | 2025-04-08 |  |  |  | Not Started | High | System configuration
79 | 6.1.4 | Initial Testing [Deliverable: Initial Test Results] | Sub-Task | 0% |  | 2025-04-08 | 2025-04-09 | 78 | 80 | Test Engineer | 2025-04-08 | 2025-04-09 |  |  |  | Not Started | Medium | Initial testing
80 | 6.1.5 | Installation Review Meeting [Deliverable: Installation Review Report] | Sub-Task | 0% |  | 2025-04-10 | 2025-04-10 | 79 | 81 | Installation Team | 2025-04-10 | 2025-04-10 |  |  |  | Not Started | Low | Installation review
81 | 6.1.6 | Installation Approval Meeting [Deliverable: Installation Approval] | Sub-Task | 0% |  | 2025-04-11 | 2025-04-11 | 80 | 82 | Project Manager | 2025-04-11 | 2025-04-11 |  |  |  | Not Started | Medium | Installation approval
82 | 6.2 | AI/ML Integration and Configuration [Deliverable: Integrated System] | Task | 5% |  | 2025-04-12 | 2025-04-23 | 81 | 93 | Integration Lead | 2025-04-12 | 2025-04-23 |  |  |  | Not Started | High | Integration and configuration
83 | 6.2.1 | System Integration [Deliverable: Integrated Components] | Sub-Task | 10% |  | 2025-04-12 | 2025-04-15 | 81 | 84 | Integration Engineer | 2025-04-12 | 2025-04-15 |  |  |  | Not Started | High | System integration
84 | 6.2.2 | Data Migration [Deliverable: Migrated Data] | Sub-Task | 5% |  | 2025-04-15 | 2025-04-17 | 83 | 85 | Data Specialist | 2025-04-15 | 2025-04-17 |  |  |  | Not Started | High | Data migration
85 | 6.2.3 | Performance Optimization [Deliverable: Optimized System] | Sub-Task | 0% |  | 2025-04-17 | 2025-04-19 | 84 | 86 | Performance Engineer | 2025-04-17 | 2025-04-19 |  |  |  | Not Started | Medium | Performance optimization
86 | 6.2.4 | Security Implementation [Deliverable: Secured System] | Sub-Task | 0% |  | 2025-04-19 | 2025-04-20 | 85 | 87 | Security Engineer | 2025-04-19 | 2025-04-20 |  |  |  | Not Started | High | Security implementation
87 | 6.2.5 | Integration Testing [Deliverable: Integration Test Results] | Sub-Task | 0% |  | 2025-04-20 | 2025-04-21 | 86 | 88 | Test Engineer | 2025-04-20 | 2025-04-21 |  |  |  | Not Started | Medium | Integration testing
88 | 6.2.6 | Integration Review Meeting [Deliverable: Integration Review Report] | Sub-Task | 0% |  | 2025-04-22 | 2025-04-22 | 87 | 89 | Integration Team | 2025-04-22 | 2025-04-22 |  |  |  | Not Started | Low | Integration review
89 | 6.2.7 | Integration Approval Meeting [Deliverable: Integration Approval] | Sub-Task | 0% |  | 2025-04-23 | 2025-04-23 | 88 | 90 | Technical Authority | 2025-04-23 | 2025-04-23 |  |  |  | Not Started | Medium | Integration approval
90 | 6.3 | AI/ML Final Implementation [Deliverable: Final Implementation Report] | Task | 0% |  | 2025-04-24 | 2025-05-01 | 89 | 97 | Implementation Manager | 2025-04-24 | 2025-05-01 |  |  |  | Not Started | Medium | Final implementation
91 | 6.3.1 | Final Configuration [Deliverable: Final Configuration] | Sub-Task | 0% |  | 2025-04-24 | 2025-04-25 | 89 | 92 | Configuration Manager | 2025-04-24 | 2025-04-25 |  |  |  | Not Started | Medium | Final configuration
92 | 6.3.2 | System Validation [Deliverable: Validation Report] | Sub-Task | 0% |  | 2025-04-25 | 2025-04-27 | 91 | 93 | Validation Engineer | 2025-04-25 | 2025-04-27 |  |  |  | Not Started | High | System validation
93 | 6.3.3 | Implementation Documentation [Deliverable: Implementation Documentation] | Sub-Task | 0% |  | 2025-04-27 | 2025-04-28 | 92 | 94 | Technical Writer | 2025-04-27 | 2025-04-28 |  |  |  | Not Started | Low | Implementation docs
94 | 6.3.4 | Final Review Meeting [Deliverable: Final Review Report] | Sub-Task | 0% |  | 2025-04-29 | 2025-04-29 | 93 | 95 | Review Team | 2025-04-29 | 2025-04-29 |  |  |  | Not Started | Medium | Final review
95 | 6.3.5 | Implementation Approval Meeting [Deliverable: Implementation Approval] | Sub-Task | 0% |  | 2025-04-30 | 2025-04-30 | 94 | 96 | Implementation Authority | 2025-04-30 | 2025-04-30 |  |  |  | Not Started | High | Implementation approval
96 | 6.4 | AI/ML Implementation Completion [Deliverable: Implementation Completion Certificate] | Milestone | 0% |  | 2025-05-01 | 2025-05-01 | 95 | 97 | Project Sponsor | 2025-05-01 | 2025-05-01 |  |  |  | Not Started | Low | Implementation completion milestone
97 | 7.0 | AI/ML Testing and Validation [Deliverable: Testing Report] | Phase |  |  | 2025-05-02 | 2025-05-21 | 96 | 115 | Test Manager | 2025-05-02 | 2025-05-21 |  |  |  | Not Started | High | Testing phase
98 | 7.1 | AI/ML System Testing [Deliverable: System Test Results] | Task | 0% |  | 2025-05-02 | 2025-05-09 | 96 | 106 | Test Manager | 2025-05-02 | 2025-05-09 |  |  |  | Not Started | High | System testing
99 | 7.1.1 | Unit Testing [Deliverable: Unit Test Results] | Sub-Task | 0% |  | 2025-05-02 | 2025-05-03 | 96 | 100 | Test Engineer | 2025-05-02 | 2025-05-03 |  |  |  | Not Started | Medium | Unit testing
100 | 7.1.2 | Integration Testing [Deliverable: Integration Test Results] | Sub-Task | 0% |  | 2025-05-03 | 2025-05-05 | 99 | 101 | Integration Tester | 2025-05-03 | 2025-05-05 |  |  |  | Not Started | High | Integration testing
101 | 7.1.3 | Performance Testing [Deliverable: Performance Test Results] | Sub-Task | 0% |  | 2025-05-05 | 2025-05-06 | 100 | 102 | Performance Tester | 2025-05-05 | 2025-05-06 |  |  |  | Not Started | High | Performance testing
102 | 7.1.4 | Security Testing [Deliverable: Security Test Results] | Sub-Task | 0% |  | 2025-05-06 | 2025-05-07 | 101 | 103 | Security Tester | 2025-05-06 | 2025-05-07 |  |  |  | Not Started | High | Security testing
103 | 7.1.5 | System Test Review Meeting [Deliverable: Test Review Report] | Sub-Task | 0% |  | 2025-05-08 | 2025-05-08 | 102 | 104 | Test Team | 2025-05-08 | 2025-05-08 |  |  |  | Not Started | Medium | Test review
104 | 7.1.6 | System Test Approval Meeting [Deliverable: Test Approval] | Sub-Task | 0% |  | 2025-05-09 | 2025-05-09 | 103 | 105 | Test Authority | 2025-05-09 | 2025-05-09 |  |  |  | Not Started | Medium | Test approval
105 | 7.2 | AI/ML User Acceptance Testing [Deliverable: UAT Results] | Task | 0% |  | 2025-05-10 | 2025-05-15 | 104 | 111 | UAT Manager | 2025-05-10 | 2025-05-15 |  |  |  | Not Started | High | User acceptance testing
106 | 7.2.1 | UAT Planning [Deliverable: UAT Plan] | Sub-Task | 0% |  | 2025-05-10 | 2025-05-10 | 104 | 107 | UAT Coordinator | 2025-05-10 | 2025-05-10 |  |  |  | Not Started | Medium | UAT planning
107 | 7.2.2 | UAT Execution [Deliverable: UAT Test Results] | Sub-Task | 0% |  | 2025-05-10 | 2025-05-12 | 106 | 108 | End Users | 2025-05-10 | 2025-05-12 |  |  |  | Not Started | High | UAT execution
108 | 7.2.3 | UAT Issue Resolution [Deliverable: Resolved Issues] | Sub-Task | 0% |  | 2025-05-12 | 2025-05-13 | 107 | 109 | Development Team | 2025-05-12 | 2025-05-13 |  |  |  | Not Started | High | Issue resolution
109 | 7.2.4 | UAT Review Meeting [Deliverable: UAT Review Report] | Sub-Task | 0% |  | 2025-05-14 | 2025-05-14 | 108 | 110 | UAT Team | 2025-05-14 | 2025-05-14 |  |  |  | Not Started | Medium | UAT review
110 | 7.2.5 | UAT Approval Meeting [Deliverable: UAT Approval] | Sub-Task | 0% |  | 2025-05-15 | 2025-05-15 | 109 | 111 | Business Users | 2025-05-15 | 2025-05-15 |  |  |  | Not Started | High | UAT approval
111 | 7.3 | AI/ML Final Validation [Deliverable: Final Validation Report] | Task | 0% |  | 2025-05-16 | 2025-05-21 | 110 | 114 | Validation Manager | 2025-05-16 | 2025-05-21 |  |  |  | Not Started | High | Final validation
112 | 7.3.1 | End-to-End Testing [Deliverable: E2E Test Results] | Sub-Task | 0% |  | 2025-05-16 | 2025-05-18 | 110 | 113 | E2E Tester | 2025-05-16 | 2025-05-18 |  |  |  | Not Started | High | End-to-end testing
113 | 7.3.2 | Final Validation Review Meeting [Deliverable: Validation Review Report] | Sub-Task | 0% |  | 2025-05-19 | 2025-05-19 | 112 | 114 | Validation Team | 2025-05-19 | 2025-05-19 |  |  |  | Not Started | Medium | Validation review
114 | 7.4 | AI/ML Testing Completion [Deliverable: Testing Completion Certificate] | Milestone | 0% |  | 2025-05-21 | 2025-05-21 | 113 | 115 | Test Authority | 2025-05-21 | 2025-05-21 |  |  |  | Not Started | Low | Testing completion milestone
115 | 8.0 | AI/ML Documentation and Training [Deliverable: Documentation and Training Package] | Phase |  |  | 2025-05-22 | 2025-06-05 | 114 | 129 | Training Manager | 2025-05-22 | 2025-06-05 |  |  |  | Not Started | Medium | Documentation and training phase
116 | 8.1 | AI/ML Technical Documentation [Deliverable: Technical Documentation Package] | Task | 0% |  | 2025-05-22 | 2025-05-27 | 114 | 122 | Technical Writer | 2025-05-22 | 2025-05-27 |  |  |  | Not Started | Medium | Technical documentation
117 | 8.1.1 | User Manuals [Deliverable: User Manual Documentation] | Sub-Task | 0% |  | 2025-05-22 | 2025-05-23 | 114 | 118 | Technical Writer | 2025-05-22 | 2025-05-23 |  |  |  | Not Started | Low | User manuals
118 | 8.1.2 | Administrator Guides [Deliverable: Administrator Guide Documentation] | Sub-Task | 0% |  | 2025-05-23 | 2025-05-24 | 117 | 119 | Technical Writer | 2025-05-23 | 2025-05-24 |  |  |  | Not Started | Medium | Administrator guides
119 | 8.1.3 | Troubleshooting Guides [Deliverable: Troubleshooting Documentation] | Sub-Task | 0% |  | 2025-05-24 | 2025-05-25 | 118 | 120 | Support Specialist | 2025-05-24 | 2025-05-25 |  |  |  | Not Started | Medium | Troubleshooting guides
120 | 8.1.4 | Documentation Review Meeting [Deliverable: Documentation Review Report] | Sub-Task | 0% |  | 2025-05-26 | 2025-05-26 | 119 | 121 | Documentation Team | 2025-05-26 | 2025-05-26 |  |  |  | Not Started | Low | Documentation review
121 | 8.1.5 | Documentation Approval Meeting [Deliverable: Documentation Approval] | Sub-Task | 0% |  | 2025-05-27 | 2025-05-27 | 120 | 122 | Documentation Authority | 2025-05-27 | 2025-05-27 |  |  |  | Not Started | Medium | Documentation approval
122 | 8.2 | AI/ML User Training [Deliverable: Trained Users] | Task | 0% |  | 2025-05-28 | 2025-06-04 | 121 | 128 | Training Manager | 2025-05-28 | 2025-06-04 |  |  |  | Not Started | High | User training
123 | 8.2.1 | Training Material Development [Deliverable: Training Materials] | Sub-Task | 0% |  | 2025-05-28 | 2025-05-29 | 121 | 124 | Training Developer | 2025-05-28 | 2025-05-29 |  |  |  | Not Started | Medium | Training materials
124 | 8.2.2 | Training Delivery [Deliverable: Training Sessions] | Sub-Task | 0% |  | 2025-05-29 | 2025-06-01 | 123 | 125 | Training Instructor | 2025-05-29 | 2025-06-01 |  |  |  | Not Started | High | Training delivery
125 | 8.2.3 | Training Assessment [Deliverable: Training Assessment Results] | Sub-Task | 0% |  | 2025-06-01 | 2025-06-02 | 124 | 126 | Training Assessor | 2025-06-01 | 2025-06-02 |  |  |  | Not Started | Medium | Training assessment
126 | 8.2.4 | Training Review Meeting [Deliverable: Training Review Report] | Sub-Task | 0% |  | 2025-06-03 | 2025-06-03 | 125 | 127 | Training Team | 2025-06-03 | 2025-06-03 |  |  |  | Not Started | Low | Training review
127 | 8.2.5 | Training Completion Meeting [Deliverable: Training Completion Certificate] | Sub-Task | 0% |  | 2025-06-04 | 2025-06-04 | 126 | 128 | Training Authority | 2025-06-04 | 2025-06-04 |  |  |  | Not Started | Medium | Training completion
128 | 8.3 | AI/ML Documentation and Training Completion [Deliverable: Documentation and Training Completion Certificate] | Milestone | 0% |  | 2025-06-05 | 2025-06-05 | 127 | 129 | Training Authority | 2025-06-05 | 2025-06-05 |  |  |  | Not Started | Low | Documentation and training completion milestone
129 | 9.0 | AI/ML Walkthrough and Handover [Deliverable: Handover Package] | Phase |  |  | 2025-06-06 | 2025-06-23 | 128 | 145 | Deployment Manager | 2025-06-06 | 2025-06-23 |  |  |  | Not Started | Medium | Walkthrough and handover phase
130 | 9.1 | AI/ML Pre-Deployment Activities [Deliverable: Pre-Deployment Checklist] | Task | 0% |  | 2025-06-06 | 2025-06-11 | 128 | 136 | Deployment Manager | 2025-06-06 | 2025-06-11 |  |  |  | Not Started | High | Pre-deployment activities
131 | 9.1.1 | Deployment Planning [Deliverable: Deployment Plan] | Sub-Task | 0% |  | 2025-06-06 | 2025-06-07 | 128 | 132 | Deployment Planner | 2025-06-06 | 2025-06-07 |  |  |  | Not Started | Medium | Deployment planning
132 | 9.1.2 | Go-Live Preparation [Deliverable: Go-Live Checklist] | Sub-Task | 0% |  | 2025-06-07 | 2025-06-08 | 131 | 133 | Go-Live Coordinator | 2025-06-07 | 2025-06-08 |  |  |  | Not Started | High | Go-live preparation
133 | 9.1.3 | Rollback Planning [Deliverable: Rollback Plan] | Sub-Task | 0% |  | 2025-06-08 | 2025-06-09 | 132 | 134 | Risk Manager | 2025-06-08 | 2025-06-09 |  |  |  | Not Started | High | Rollback planning
134 | 9.1.4 | Pre-Deployment Review Meeting [Deliverable: Pre-Deployment Review Report] | Sub-Task | 0% |  | 2025-06-10 | 2025-06-10 | 133 | 135 | Deployment Team | 2025-06-10 | 2025-06-10 |  |  |  | Not Started | Medium | Pre-deployment review
135 | 9.1.5 | Pre-Deployment Approval Meeting [Deliverable: Pre-Deployment Approval] | Sub-Task | 0% |  | 2025-06-11 | 2025-06-11 | 134 | 136 | Deployment Authority | 2025-06-11 | 2025-06-11 |  |  |  | Not Started | High | Pre-deployment approval
136 | 9.2 | AI/ML Go-Live Activities [Deliverable: Go-Live Report] | Task | 0% |  | 2025-06-12 | 2025-06-16 | 135 | 141 | Go-Live Manager | 2025-06-12 | 2025-06-16 |  |  |  | Not Started | High | Go-live activities
137 | 9.2.1 | System Deployment [Deliverable: Deployed System] | Sub-Task | 0% |  | 2025-06-12 | 2025-06-12 | 135 | 138 | Deployment Engineer | 2025-06-12 | 2025-06-12 |  |  |  | Not Started | High | System deployment
138 | 9.2.2 | Go-Live Monitoring [Deliverable: Go-Live Monitoring Report] | Sub-Task | 0% |  | 2025-06-12 | 2025-06-14 | 137 | 139 | Monitoring Team | 2025-06-12 | 2025-06-14 |  |  |  | Not Started | High | Go-live monitoring
139 | 9.2.3 | Issue Resolution [Deliverable: Resolved Issues] | Sub-Task | 0% |  | 2025-06-14 | 2025-06-15 | 138 | 140 | Support Team | 2025-06-14 | 2025-06-15 |  |  |  | Not Started | High | Issue resolution
140 | 9.2.4 | Go-Live Review Meeting [Deliverable: Go-Live Review Report] | Sub-Task | 0% |  | 2025-06-16 | 2025-06-16 | 139 | 141 | Go-Live Team | 2025-06-16 | 2025-06-16 |  |  |  | Not Started | Medium | Go-live review
141 | 9.3 | AI/ML System Handover [Deliverable: System Handover Package] | Task | 0% |  | 2025-06-17 | 2025-06-23 | 140 | 144 | Handover Manager | 2025-06-17 | 2025-06-23 |  |  |  | Not Started | Medium | System handover
142 | 9.3.1 | Handover Documentation [Deliverable: Handover Documentation Package] | Sub-Task | 0% |  | 2025-06-17 | 2025-06-18 | 140 | 143 | Documentation Team | 2025-06-17 | 2025-06-18 |  |  |  | Not Started | Medium | Handover documentation
143 | 9.3.2 | Knowledge Transfer [Deliverable: Knowledge Transfer Sessions] | Sub-Task | 0% |  | 2025-06-18 | 2025-06-20 | 142 | 144 | Knowledge Transfer Team | 2025-06-18 | 2025-06-20 |  |  |  | Not Started | High | Knowledge transfer
144 | 9.3.3 | Handover Approval Meeting [Deliverable: Handover Approval] | Sub-Task | 0% |  | 2025-06-22 | 2025-06-22 | 143 | 145 | Handover Authority | 2025-06-22 | 2025-06-22 |  |  |  | Not Started | High | Handover approval
144 | 9.4 | AI/ML Handover Completion [Deliverable: Handover Completion Certificate] | Milestone | 0% |  | 2025-06-23 | 2025-06-23 | 143 | 145 | Project Sponsor | 2025-06-23 | 2025-06-23 |  |  |  | Not Started | Low | Handover completion milestone
145 | 10.0 | AI/ML Project Close-out [Deliverable: Project Close-out Report] | Phase |  |  | 2025-06-24 | 2025-07-05 | 144 | 158 | Project Manager | 2025-06-24 | 2025-07-05 |  |  |  | Not Started | Low | Project close-out phase
146 | 10.1 | AI/ML Administrative Closure [Deliverable: Administrative Closure Package] | Task | 0% |  | 2025-06-24 | 2025-06-28 | 144 | 151 | Project Manager | 2025-06-24 | 2025-06-28 |  |  |  | Not Started | Medium | Administrative closure
147 | 10.1.1 | Contract Closure [Deliverable: Closed Contracts] | Sub-Task | 0% |  | 2025-06-24 | 2025-06-25 | 144 | 148 | Contract Manager | 2025-06-24 | 2025-06-25 |  |  |  | Not Started | Medium | Contract closure
148 | 10.1.2 | Financial Closure [Deliverable: Financial Closure Report] | Sub-Task | 0% |  | 2025-06-25 | 2025-06-26 | 147 | 149 | Finance Manager | 2025-06-25 | 2025-06-26 |  |  |  | Not Started | Medium | Financial closure
149 | 10.1.3 | Resource Release [Deliverable: Resource Release Documentation] | Sub-Task | 0% |  | 2025-06-27 | 2025-06-27 | 148 | 150 | Resource Manager | 2025-06-27 | 2025-06-27 |  |  |  | Not Started | Low | Resource release
150 | 10.1.4 | Administrative Review Meeting [Deliverable: Administrative Review Report] | Sub-Task | 0% |  | 2025-06-28 | 2025-06-28 | 149 | 151 | Administrative Team | 2025-06-28 | 2025-06-28 |  |  |  | Not Started | Low | Administrative review
151 | 10.2 | AI/ML Lessons Learned [Deliverable: Lessons Learned Report] | Task | 0% |  | 2025-06-29 | 2025-07-02 | 150 | 155 | Project Manager | 2025-06-29 | 2025-07-02 |  |  |  | Not Started | Medium | Lessons learned
152 | 10.2.1 | Lessons Learned Collection [Deliverable: Lessons Learned Database] | Sub-Task | 0% |  | 2025-06-29 | 2025-06-30 | 150 | 153 | Project Analyst | 2025-06-29 | 2025-06-30 |  |  |  | Not Started | Medium | Lessons collection
153 | 10.2.2 | Best Practices Documentation [Deliverable: Best Practices Guide] | Sub-Task | 0% |  | 2025-06-30 | 2025-07-01 | 152 | 154 | Knowledge Manager | 2025-06-30 | 2025-07-01 |  |  |  | Not Started | Low | Best practices
154 | 10.2.3 | Lessons Learned Review Meeting [Deliverable: Lessons Learned Review Report] | Sub-Task | 0% |  | 2025-07-02 | 2025-07-02 | 153 | 155 | Project Team | 2025-07-02 | 2025-07-02 |  |  |  | Not Started | Low | Lessons review
155 | 10.3 | AI/ML Final Reporting [Deliverable: Final Project Report] | Task | 0% |  | 2025-07-03 | 2025-07-05 | 154 | 157 | Project Manager | 2025-07-03 | 2025-07-05 |  |  |  | Not Started | Medium | Final reporting
156 | 10.3.1 | Final Report Preparation [Deliverable: Final Project Report] | Sub-Task | 0% |  | 2025-07-03 | 2025-07-04 | 154 | 157 | Project Manager | 2025-07-03 | 2025-07-04 |  |  |  | Not Started | Medium | Final report
157 | 10.4 | AI/ML Project Closure [Deliverable: Project Closure Certificate] | Milestone | 0% |  | 2025-07-05 | 2025-07-05 | 156 | 158 | Project Sponsor | 2025-07-05 | 2025-07-05 |  |  |  | Not Started | Low | Project closure milestone
158 | 11.0 | AI/ML Steady-State Support [Deliverable: Steady-State Support Plan] | Phase |  |  | 2025-07-06 | 2025-10-03 | 157 |  | Support Manager | 2025-07-06 | 2025-10-03 |  |  |  | Not Started | Low | Steady-state support phase
159 | 11.1 | AI/ML Production Support [Deliverable: Production Support Services] | Task | 0% |  | 2025-07-06 | 2025-08-04 | 157 | 165 | Support Manager | 2025-07-06 | 2025-08-04 |  |  |  | Not Started | Medium | Production support
160 | 11.1.1 | 24/7 Monitoring [Deliverable: Monitoring Reports] | Sub-Task | 0% |  | 2025-07-06 | 2025-08-04 | 157 | 161 | Monitoring Team | 2025-07-06 | 2025-08-04 |  |  |  | Not Started | High | 24/7 monitoring
161 | 11.1.2 | Incident Management [Deliverable: Incident Reports] | Sub-Task | 0% |  | 2025-07-06 | 2025-08-04 | 160 | 162 | Incident Team | 2025-07-06 | 2025-08-04 |  |  |  | Not Started | High | Incident management
162 | 11.1.3 | Performance Monitoring [Deliverable: Performance Reports] | Sub-Task | 0% |  | 2025-07-06 | 2025-08-04 | 161 | 163 | Performance Team | 2025-07-06 | 2025-08-04 |  |  |  | Not Started | Medium | Performance monitoring
163 | 11.1.4 | User Support [Deliverable: User Support Services] | Sub-Task | 0% |  | 2025-07-06 | 2025-08-04 | 162 | 164 | Help Desk | 2025-07-06 | 2025-08-04 |  |  |  | Not Started | Medium | User support
164 | 11.1.5 | Monthly Support Review Meeting [Deliverable: Monthly Support Reports] | Sub-Task | 0% |  | 2025-07-06 | 2025-08-04 | 163 | 165 | Support Team | 2025-07-06 | 2025-08-04 |  |  |  | Not Started | Low | Monthly reviews
165 | 11.2 | AI/ML Maintenance and Updates [Deliverable: Maintenance Services] | Task | 0% |  | 2025-08-05 | 2025-09-03 | 164 | 170 | Maintenance Manager | 2025-08-05 | 2025-09-03 |  |  |  | Not Started | Medium | Maintenance and updates
166 | 11.2.1 | Preventive Maintenance [Deliverable: Maintenance Reports] | Sub-Task | 0% |  | 2025-08-05 | 2025-09-03 | 164 | 167 | Maintenance Team | 2025-08-05 | 2025-09-03 |  |  |  | Not Started | Medium | Preventive maintenance
167 | 11.2.2 | System Updates [Deliverable: Updated System] | Sub-Task | 0% |  | 2025-08-05 | 2025-09-03 | 166 | 168 | Update Team | 2025-08-05 | 2025-09-03 |  |  |  | Not Started | High | System updates
168 | 11.2.3 | Security Updates [Deliverable: Security Patches] | Sub-Task | 0% |  | 2025-08-05 | 2025-09-03 | 167 | 169 | Security Team | 2025-08-05 | 2025-09-03 |  |  |  | Not Started | High | Security updates
169 | 11.2.4 | Maintenance Review Meeting [Deliverable: Maintenance Review Reports] | Sub-Task | 0% |  | 2025-08-05 | 2025-09-03 | 168 | 170 | Maintenance Team | 2025-08-05 | 2025-09-03 |  |  |  | Not Started | Low | Maintenance reviews
170 | 11.3 | AI/ML Continuous Improvement [Deliverable: Improvement Initiatives] | Task | 0% |  | 2025-09-04 | 2025-10-03 | 169 | 174 | Improvement Manager | 2025-09-04 | 2025-10-03 |  |  |  | Not Started | Low | Continuous improvement
171 | 11.3.1 | Performance Analysis [Deliverable: Performance Analysis Reports] | Sub-Task | 0% |  | 2025-09-04 | 2025-10-03 | 169 | 172 | Performance Analyst | 2025-09-04 | 2025-10-03 |  |  |  | Not Started | Medium | Performance analysis
172 | 11.3.2 | Improvement Recommendations [Deliverable: Improvement Recommendations] | Sub-Task | 0% |  | 2025-09-04 | 2025-10-03 | 171 | 173 | Improvement Analyst | 2025-09-04 | 2025-10-03 |  |  |  | Not Started | Low | Improvement recommendations
173 | 11.3.3 | Improvement Implementation [Deliverable: Implemented Improvements] | Sub-Task | 0% |  | 2025-09-04 | 2025-10-03 | 172 | 174 | Improvement Team | 2025-09-04 | 2025-10-03 |  |  |  | Not Started | Medium | Improvement implementation
174 | 11.4 | AI/ML Steady-State Establishment [Deliverable: Steady-State Establishment Certificate] | Milestone | 0% |  | 2025-10-03 | 2025-10-03 | 173 |  | Project Sponsor | 2025-10-03 | 2025-10-03 |  |  |  | Not Started | Low | Steady-state establishment milestone
|  | OVERALL PROJECT COMPLETION | SUMMARY
|  | SUMMARY | SUMMARY
|  | Project Status Dashboard | SUMMARY