## Open Action Items
SOFTWARE DEVELOPMENT AND ENGINEERING - OPEN ACTION ITEM LOG
Project: Software Development
Date: July 31, 2025
PMI 2025 Standards Compliant
ACTION ITEM TRACKING
Action_ID | Action_Description | Priority | Status | Owner | Due_Date | Completion_Date | Progress_% | Dependencies | Notes
AI001 | Establish comprehensive requirements management and change control | High | In Progress | Software Architects | 2025-08-30 |  | 25 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI002 | Complete technical architecture design and review procedures | High | In Progress | Developers | 2025-09-04 |  | 32 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI003 | Implement quality assurance processes throughout development lifecycle | High | In Progress | QA Engineers | 2025-09-09 |  | 39 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI004 | Deploy continuous security assessment and improvement procedures | High | In Progress | DevOps Engineers | 2025-09-14 |  | 46 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI005 | Execute performance optimization during architecture and development | Medium | In Progress | Product Owners | 2025-09-19 |  | 53 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI006 | Establish user feedback collection and integration procedures | Medium | In Progress | End Users | 2025-09-24 |  | 60 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI007 | Create documentation standards and maintenance procedures | Medium | Not Started | Software Architects | 2025-09-29 |  | 67 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI008 | Implement DevOps practices and automation pipelines | Medium | Not Started | Developers | 2025-10-04 |  | 74 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI009 | Deploy testing automation and continuous integration procedures | Low | Not Started | QA Engineers | 2025-10-09 |  | 81 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success
AI010 | Establish post-deployment monitoring and improvement processes | Low | Completed | DevOps Engineers | 2025-10-14 | 2025-07-31 | 100 | Dependent on Software Development milestone completion | Critical action for Software Development and Engineering success