## Procurement Overview
PROCUREMENT MANAGEMENT PLAN
SOFTWARE Procurement Plan Project
Generated: July 16, 2025
PROJECT INFORMATION
Project Name: | Enterprise AI/ML Implementation
Procurement Manager: | Robert Chen, CPSM
Total Procurement Budget: | $1,425,000 (50% of project budget)
Number of Procurements: | 12 major procurement packages
Procurement Timeline: | 18 months (Jan 2025 - Jun 2026)
Contract Types: | Fixed Price, Time & Materials, Cost Plus
Key Vendors: | 5 strategic technology partners
PROCUREMENT OBJECTIVES
1. Secure best-in-class AI/ML technology solutions at competitive prices
2. Establish strategic partnerships with leading technology vendors
3. Ensure all procurements comply with organizational policies and regulations
4. Minimize procurement risks through comprehensive vendor evaluation
5. Achieve cost savings of 15% through competitive bidding and negotiations
6. Maintain procurement schedule to support project timeline requirements
PROCUREMENT STRATEGY
• Make vs Buy Analysis: Focus on core competencies, outsource specialized AI/ML components
• Vendor Strategy: Establish partnerships with 3-5 strategic vendors for long-term collaboration
• Contract Strategy: Use fixed-price contracts for well-defined work, T&M for consulting
• Risk Strategy: Diversify vendor base, include performance guarantees and SLAs
• Cost Strategy: Competitive bidding for major purchases, negotiate volume discounts
• Quality Strategy: Rigorous vendor qualification, proof of concepts, reference checks

## Procurement Register
PROCUREMENT REGISTER
Procurement ID | Description | Category | Contract Type | Estimated Value | Planned Start | Planned Award | Vendor | Status | Risk Level | Owner | Approval Authority | Notes | Actual Cost
PROC-001 | AI/ML Platform License | Software | Fixed Price | $450,000 | 2025-02-01 | 2025-03-15 | DataRobot Inc. | Awarded | Medium | Robert Chen | CTO | 3-year license | $425,000
PROC-002 | Cloud Infrastructure Services | Infrastructure | Time & Materials | $300,000 | 2025-01-15 | 2025-02-28 | AWS | Awarded | Low | Chris Wilson | IT Director | Pay-as-you-go | $285,000
PROC-003 | Data Integration Consulting | Services | Time & Materials | $180,000 | 2025-03-01 | 2025-04-15 | Accenture | In Progress | Medium | Thomas Lee | Project Manager | 6-month engagement | TBD
PROC-004 | Security Assessment Services | Services | Fixed Price | $75,000 | 2025-04-01 | 2025-05-15 | Deloitte Cyber | Planned | High | Security Team | CISO | Comprehensive assessment | TBD
PROC-005 | Training and Certification | Training | Fixed Price | $120,000 | 2025-08-01 | 2025-09-15 | TBD | Planned | Low | HR Manager | CHRO | Team upskilling | TBD
PROC-006 | Development Tools License | Software | Fixed Price | $85,000 | 2025-02-15 | 2025-03-30 | JetBrains | Awarded | Low | Dev Team Lead | CTO | IDE and tools | $80,000
PROC-007 | Data Visualization Platform | Software | Fixed Price | $95,000 | 2025-05-01 | 2025-06-15 | Tableau | Planned | Medium | Analytics Team | CDO | Enterprise license | TBD
PROC-008 | MLOps Platform | Software | Fixed Price | $200,000 | 2025-06-01 | 2025-07-15 | MLflow/Databricks | Planned | Medium | ML Team | CTO | Model lifecycle mgmt | TBD
PROC-009 | Hardware Infrastructure | Hardware | Fixed Price | $150,000 | 2025-03-15 | 2025-04-30 | Dell Technologies | In Progress | Medium | Infrastructure Team | IT Director | GPU servers | TBD
PROC-010 | Change Management Consulting | Services | Time & Materials | $90,000 | 2025-09-01 | 2025-10-15 | Prosci | Planned | Low | Change Manager | CHRO | Change strategy | TBD
PROC-011 | Quality Assurance Tools | Software | Fixed Price | $65,000 | 2025-04-15 | 2025-05-30 | SmartBear | Planned | Low | QA Manager | CTO | Testing automation | TBD
PROC-012 | Legal and Compliance Review | Services | Fixed Price | $45,000 | 2025-01-01 | 2025-02-15 | Baker McKenzie | Awarded | Medium | Legal Team | General Counsel | Contract review | $42,000

## Vendor Management
VENDOR MANAGEMENT MATRIX
Vendor Name | Category | Relationship Type | Contract Value | Performance Rating | Risk Assessment | Key Contact | Contract Start | Contract End | Renewal Option | Status | Notes
DataRobot Inc. | AI/ML Platform | Strategic Partner | $450,000 | 4.5/5 | Low | Sarah Kim, VP Sales | 2025-03-15 | 2028-03-14 | Yes | Active | Primary AI platform
AWS | Cloud Services | Preferred Vendor | $300,000 | 4.8/5 | Low | Mike Johnson, Account Mgr | 2025-02-28 | 2026-02-27 | Yes | Active | Infrastructure provider
Accenture | Consulting | Strategic Partner | $180,000 | 4.2/5 | Medium | Lisa Chen, Partner | 2025-04-15 | 2025-10-14 | Yes | Active | Data integration expert
Deloitte Cyber | Security Services | Specialist Vendor | $75,000 | 4.0/5 | Medium | Robert Taylor, Director | 2025-05-15 | 2025-08-14 | No | Planned | Security assessment
JetBrains | Development Tools | Technology Vendor | $85,000 | 4.6/5 | Low | Anna Petrov, Sales | 2025-03-30 | 2026-03-29 | Yes | Active | Development environment
Tableau | Analytics Platform | Technology Vendor | $95,000 | 4.3/5 | Medium | David Wong, Account Exec | 2025-06-15 | 2026-06-14 | Yes | Planned | Data visualization
Databricks | MLOps Platform | Strategic Partner | $200,000 | 4.4/5 | Medium | Jennifer Liu, Solutions | 2025-07-15 | 2026-07-14 | Yes | Planned | ML lifecycle management
Dell Technologies | Hardware | Preferred Vendor | $150,000 | 4.1/5 | Medium | Kevin Zhang, Sales | 2025-04-30 | 2025-07-29 | No | In Progress | GPU infrastructure
Prosci | Change Management | Specialist Vendor | $90,000 | 4.7/5 | Low | Maria Garcia, Consultant | 2025-10-15 | 2026-01-14 | Yes | Planned | Change methodology
SmartBear | QA Tools | Technology Vendor | $65,000 | 4.2/5 | Low | Tom Wilson, Sales | 2025-05-30 | 2026-05-29 | Yes | Planned | Testing automation
Baker McKenzie | Legal Services | Professional Services | $45,000 | 4.5/5 | Low | Susan Brown, Partner | 2025-02-15 | 2025-05-14 | Yes | Active | Legal compliance