## Risk Scoring Guide
FINANCE - CORE BANKING SYSTEM DEFENSE - RISK SCORING METHODOLOGY
PROBABILITY SCALE (1-5):
1 - Very Low (0-10%): Highly unlikely to occur
2 - Low (11-30%): Unlikely but possible
3 - Medium (31-50%): Moderate chance of occurrence
4 - High (51-80%): Likely to occur
5 - Very High (81-100%): Almost certain to occur
IMPACT SCALE (1-5):
1 - Minimal: <$50K impact, minor schedule delay
2 - Low: $50K-$200K impact, 1-2 week delay
3 - Medium: $200K-$500K impact, 1-4 week delay
4 - High: $500K-$1M impact, 1-2 month delay
5 - Critical: >$1M impact, >2 month delay
RISK SCORE CALCULATION (Probability × Impact):
1-3: Very Low Risk (Accept)
4-7: Low Risk (Accept and monitor)
8-14: Medium Risk (Monitor and manage)
15-19: High Risk (Detailed mitigation plan)
20-25: Critical Risk (Immediate action required)
RISK RESPONSE STRATEGIES:
• Accept: Monitor with no active response
• Mitigate: Reduce probability or impact
• Transfer: Share risk with third party
• Avoid: Eliminate risk through scope change
• Escalate: Elevate to higher authority
RISK SCORE MATRIX
Probability\Impact | 1-Minimal | 2-Low | 3-Medium | 4-High | 5-Critical
1-Very Low | 1 | 2 | 3 | 4 | 5
2-Low | 2 | 4 | 6 | 8 | 10
3-Medium | 3 | 6 | 9 | 12 | 15
4-High | 4 | 8 | 12 | 16 | 20
5-Very High | 5 | 10 | 15 | 20 | 25

## Risks
Risk_ID | Risk_Description | Category | Probability | Impact | Risk_Score | Status | Owner | Mitigation_Strategy | Contingency_Plan | Target_Date | Notes
R001 | Data migration integrity issues during core banking system transition | Strategic | 4 | 4 |  | Open | Business Owner | Implement comprehensive mitigation strategy for Advanced persistent threats targeting critical sys... | Contingency plan for Finance Implementation risk management | 2025-08-30 | Industry-specific risk for Information Banking and Cyber Defense
R002 | Regulatory compliance gaps with SOX, PCI-DSS, and GLBA requirements | Strategic | 3 | 5 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Data breaches exposing sensitive information... | Contingency plan for Finance Implementation risk management | 2025-08-30 | Industry-specific risk for Information Banking and Cyber Defense
R003 | Legacy system integration failures causing transaction processing delays | Strategic | 3 | 4 |  | Open | Technical Lead | Implement comprehensive mitigation strategy for Insider attacks from privileged users... | Contingency plan for Finance Implementation risk management | 2025-08-30 | Industry-specific risk for Information Banking and Cyber Defense
R004 | User adoption resistance from branch staff and operations team | Operational | 4 | 3 |  | Open | Business Owner | Implement comprehensive mitigation strategy for Compliance violations resulting in penalties... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R005 | Vendor dependency and support availability for core banking platform | Strategic | 3 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for System vulnerabilities in legacy applications... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R006 | Budget overruns due to scope creep and additional customization needs | Financial | 4 | 4 |  | Open | Technical Lead | Implement comprehensive mitigation strategy for Phishing attacks compromising credentials... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R007 | Schedule delays impacting go-live date and business operations | Operational | 3 | 4 |  | Open | Business Owner | Implement comprehensive mitigation strategy for Ransomware attacks encrypting critical data... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R008 | Data security breaches during migration exposing customer information | Strategic | 2 | 5 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Supply chain attacks through vendors... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R009 | Performance degradation of new system under peak transaction loads | Technical | 3 | 4 |  | Open | Technical Lead | Implement comprehensive mitigation strategy for Social engineering targeting executives... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R010 | Insufficient training leading to operational errors and customer impact | Operational | 4 | 3 |  | Open | Business Owner | Implement comprehensive mitigation strategy for Zero-day exploits in security tools... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R011 | Third-party API integration failures with payment processors | Technical | 3 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Denial of service attacks disrupting operations... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R012 | Disaster recovery and business continuity plan inadequacies | Strategic | 2 | 4 |  | Open | Technical Lead | Implement comprehensive mitigation strategy for Mobile device security breaches... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R013 | Stakeholder misalignment on project scope and objectives | Operational | 3 | 3 |  | Open | Business Owner | Implement comprehensive mitigation strategy for Cloud security misconfigurations... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R014 | Resource availability constraints for key banking SMEs | Operational | 4 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Third-party vendor security failures... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R015 | Change management resistance from senior leadership | Strategic | 2 | 4 |  | Open | Technical Lead | Implement comprehensive mitigation strategy for Security tool integration failures... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R016 | Testing coverage gaps leading to post-implementation defects | Technical | 3 | 3 |  | Open | Business Owner | Implement comprehensive mitigation strategy for Incident response plan inadequacy... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R017 | Audit findings requiring significant rework and delays | Compliance | 2 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Security awareness training ineffectiveness... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R018 | Customer communication failures causing service disruption concerns | Operational | 3 | 3 |  | Open | Technical Lead | Implement comprehensive mitigation strategy for Regulatory requirement changes... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R019 | Technology obsolescence of selected platform within 5 years | Strategic | 2 | 3 |  | Open | Business Owner | Implement comprehensive mitigation strategy for Budget constraints limiting security investments... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense
R020 | Organizational restructuring impacting project team stability | Operational | 2 | 3 |  | Open | Project Manager | Implement comprehensive mitigation strategy for Talent shortage in cybersecurity roles... | Contingency plan for Cybersecurity Implementation risk management | 2025-08-30 | Industry-specific risk for Information Security and Cyber Defense

## Assumptions
Assumption_ID | Assumption_Description | Category | Confidence_Level | Impact_if_False | Validation_Method | Status | Owner | Validation_Date | Notes
A001 | Threat intelligence feeds remain accurate | Strategic | High | Medium | Document Review | Valid | CIO | 2025-08-15 | Critical assumption for Information Banking and Cyber Defense implementation
A002 | Banking tools function as designed | Strategic | High | Medium | Document Review | Valid | Banking Architects | 2025-08-15 | Critical assumption for Information Banking and Cyber Defense implementation
A003 | Staff security training is effective | Strategic | High | Medium | Document Review | Valid | Banking Engineers | 2025-08-15 | Critical assumption for Information Banking and Cyber Defense implementation
A004 | Budget allocation meets security needs | Strategic | High | Medium | Document Review | Valid | SOC Analysts | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A005 | Management supports security initiatives | Strategic | High | Medium | Document Review | Valid | Compliance Officers | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A006 | Vendor security controls are adequate | Operational | High | Medium | Document Review | Valid | IT Teams | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A007 | Incident response procedures are current | Operational | High | Medium | Document Review | Valid | CISO | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A008 | Compliance frameworks remain stable | Operational | High | Medium | Document Review | Valid | Security Architects | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A009 | Technology platforms are secure | Operational | High | Medium | Document Review | Valid | Security Engineers | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A010 | User behavior follows security policies | Operational | High | Medium | Document Review | Valid | SOC Analysts | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A011 | Third-party integrations are secure | Technical | High | Medium | Document Review | Valid | Compliance Officers | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A012 | Monitoring systems detect threats | Technical | High | Medium | Document Review | Valid | IT Teams | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A013 | Backup and recovery systems function | Technical | High | Medium | Document Review | Valid | CISO | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A014 | Network segmentation is effective | Technical | High | Medium | Document Review | Valid | Security Architects | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A015 | Access controls are properly configured | Technical | High | Medium | Document Review | Valid | Security Engineers | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A016 | Security patches are applied timely | Financial | High | Medium | Document Review | Valid | SOC Analysts | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A017 | Audit findings are addressed promptly | Financial | High | Medium | Document Review | Valid | Compliance Officers | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A018 | Risk assessments are accurate | Financial | High | Medium | Document Review | Valid | IT Teams | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A019 | Business continuity plans are viable | Financial | High | Medium | Document Review | Valid | CISO | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation
A020 | Security metrics provide actionable insights | Financial | High | Medium | Document Review | Valid | Security Architects | 2025-08-15 | Critical assumption for Information Security and Cyber Defense implementation

## Issues
Issue_ID | Issue_Description | Category | Priority | Severity | Status | Owner | Resolution_Plan | Target_Date | Actual_Date | Notes
I001 | Legacy system vulnerabilities requiring patches | Process | Medium | Medium | Open | CIO | Develop comprehensive resolution plan for Legacy system vulnerabilities requiring patches... | 2025-08-21 |  | Critical issue requiring attention for Information Banking and Cyber Defense
I002 | Banking skill gaps in IT team | Process | Medium | Medium | Open | Banking Architects | Develop comprehensive resolution plan for Banking skill gaps in IT team... | 2025-08-21 |  | Critical issue requiring attention for Information Banking and Cyber Defense
I003 | Alert fatigue from security tools | Process | Medium | Medium | Open | Banking Engineers | Develop comprehensive resolution plan for Alert fatigue from security tools... | 2025-08-21 |  | Critical issue requiring attention for Information Banking and Cyber Defense
I004 | False positive rates in threat detection | Process | Medium | Medium | Open | SOC Analysts | Develop comprehensive resolution plan for False positive rates in threat detection... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I005 | Integration challenges between security platforms | Process | Medium | Medium | Open | Compliance Officers | Develop comprehensive resolution plan for Integration challenges between security platforms... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I006 | Compliance gap identification | Technical | Medium | Medium | Open | IT Teams | Develop comprehensive resolution plan for Compliance gap identification... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I007 | Incident response coordination difficulties | Technical | Medium | Medium | Open | CISO | Develop comprehensive resolution plan for Incident response coordination difficulties... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I008 | User security awareness deficiencies | Technical | Medium | Medium | Open | Security Architects | Develop comprehensive resolution plan for User security awareness deficiencies... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I009 | Vendor security assessment delays | Technical | Medium | Medium | Open | Security Engineers | Develop comprehensive resolution plan for Vendor security assessment delays... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I010 | Security policy enforcement inconsistencies | Technical | Medium | Medium | Open | SOC Analysts | Develop comprehensive resolution plan for Security policy enforcement inconsistencies... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I011 | Threat hunting capability limitations | Resource | Medium | Medium | Open | Compliance Officers | Develop comprehensive resolution plan for Threat hunting capability limitations... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I012 | Security metrics reporting gaps | Resource | Medium | Medium | Open | IT Teams | Develop comprehensive resolution plan for Security metrics reporting gaps... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I013 | Access control management complexity | Resource | Medium | Medium | Open | CISO | Develop comprehensive resolution plan for Access control management complexity... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I014 | Security tool configuration errors | Resource | Medium | Medium | Open | Security Architects | Develop comprehensive resolution plan for Security tool configuration errors... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I015 | Penetration testing finding remediation | Resource | Medium | Medium | Open | Security Engineers | Develop comprehensive resolution plan for Penetration testing finding remediation... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I016 | Security architecture documentation gaps | Quality | Medium | Medium | Open | SOC Analysts | Develop comprehensive resolution plan for Security architecture documentation gaps... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I017 | Risk assessment methodology updates | Quality | Medium | Medium | Open | Compliance Officers | Develop comprehensive resolution plan for Risk assessment methodology updates... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I018 | Security training program effectiveness | Quality | Medium | Medium | Open | IT Teams | Develop comprehensive resolution plan for Security training program effectiveness... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I019 | Budget allocation for security priorities | Quality | Medium | Medium | Open | CISO | Develop comprehensive resolution plan for Budget allocation for security priorities... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense
I020 | Executive security briefing requirements | Quality | Medium | Medium | Open | Security Architects | Develop comprehensive resolution plan for Executive security briefing requirements... | 2025-08-21 |  | Critical issue requiring attention for Information Security and Cyber Defense

## Dependencies
Dependency_ID | Dependency_Description | Type | Criticality | Status | Owner | Required_Date | Actual_Date | Impact_if_Delayed | Notes
D001 | Banking tool procurement and deployment | Internal | High | Pending | CIO | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Banking and Cyber Defense success
D002 | Staff security training completion | Internal | High | Pending | Banking Architects | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Banking and Cyber Defense success
D003 | Policy approval and implementation | Internal | High | Pending | Banking Engineers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Banking and Cyber Defense success
D004 | Network infrastructure security hardening | Internal | High | Pending | SOC Analysts | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D005 | Vendor security assessment completion | Internal | High | Pending | Compliance Officers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D006 | Compliance audit preparation | Internal | High | Pending | IT Teams | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D007 | Incident response plan testing | Internal | High | Pending | CISO | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D008 | Security architecture design approval | Internal | Medium | Pending | Security Architects | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D009 | Risk assessment completion | Internal | Medium | Pending | Security Engineers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D010 | Executive security briefing delivery | Internal | Medium | Pending | SOC Analysts | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D011 | Security metrics dashboard implementation | External | Medium | Pending | Compliance Officers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D012 | Threat intelligence feed integration | External | Medium | Pending | IT Teams | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D013 | Security awareness campaign launch | External | Medium | Pending | CISO | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D014 | Penetration testing execution | External | Medium | Pending | Security Architects | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D015 | Vulnerability assessment completion | External | Low | Pending | Security Engineers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D016 | Security control implementation | External | Low | Pending | SOC Analysts | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D017 | Audit finding remediation | External | Low | Pending | Compliance Officers | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D018 | Business continuity plan testing | External | Low | Pending | IT Teams | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D019 | Security budget approval | External | Low | Pending | CISO | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success
D020 | Regulatory compliance validation | External | Low | Pending | Security Architects | 2025-09-14 |  | Project delay and cost impact | Critical dependency for Information Security and Cyber Defense success