## RTM Overview
REQUIREMENTS TRACEABILITY MATRIX
Construction Implementation Project
Generated: July 16, 2025
PROJECT INFORMATION
Project Name: | Enterprise Construction Implementation
Requirements Manager: | Dr. Emily Chen, PMP
Total Requirements: | 85 requirements across 4 categories
Requirements Methodology: | Agile with IIBA BABOK standards
Requirements Timeline: | 18 months (Jan 2025 - Jun 2026)
Requirements Budget: | $350,000 (12.3% of project budget)
Requirements Tools: | JIRA, Confluence, Excel RTM
RTM OBJECTIVES
1. Ensure all business requirements are linked to project objectives and success criteria
2. Maintain bidirectional traceability from requirements to design, development, and testing
3. Verify all requirements are implemented and validated through appropriate test cases
4. Identify and manage the impact of requirement changes throughout the project lifecycle
5. Provide comprehensive requirements coverage analysis for stakeholder review
6. Support regulatory compliance and audit requirements with complete traceability
RTM METHODOLOGY
• Requirements Identification: Gather and document requirements from stakeholders
• Requirements Classification: Categorize requirements by type and priority
• Forward Traceability: Link requirements to design, development, and test artifacts
• Backward Traceability: Ensure all design and test elements link back to requirements
• Coverage Analysis: Verify all requirements are fully covered by test cases
• Change Management: Track requirement changes and assess impact on related artifacts

## Requirements Register
REQUIREMENTS REGISTER
Req ID | Requirement Name | Description | Category | Type | Priority | Source | Owner | Status | Complexity | Dependencies | Dependencies | Acceptance Criteria | Notes
| REQ-001 | Foundation Design | Foundation system shall provide reinforced concrete footings and grade beams meeting structural load requirements | Functional | Functional | Critical | Structural Engineer | Site Superintendent | Approved | High | None
| REQ-002 | Structural Framework | Building shall provide steel frame structure with moment connections meeting seismic design requirements | Functional | Functional | Critical | Structural Engineer | Construction Manager | Approved | High | None
| REQ-003 | Building Envelope | Exterior walls shall provide weather-resistant barrier with insulation meeting energy code requirements | Functional | Functional | High | Architect | Site Superintendent | Approved | Medium | None
| REQ-004 | Roofing System | Roof assembly shall provide waterproof membrane with 20-year warranty and proper drainage | Functional | Functional | High | Architect | Roofing Contractor | Approved | Medium | None
| REQ-005 | HVAC Installation | Mechanical systems shall provide climate control meeting comfort and efficiency standards | Functional | Functional | Critical | Mechanical Engineer | HVAC Contractor | Approved | High | None
| REQ-006 | Electrical Systems | Electrical installation shall provide adequate power distribution and emergency backup systems | Functional | Non-Functional | Critical | Electrical Engineer | Electrical Contractor | Approved | High | None
| REQ-007 | Plumbing Infrastructure | Plumbing systems shall provide potable water supply and waste water removal per code | Functional | Functional | High | Plumbing Engineer | Plumbing Contractor | Approved | Medium | None
| REQ-008 | Fire Safety Systems | Fire protection shall include sprinkler system and fire-rated assemblies per life safety code | Functional | Compliance | Critical | Fire Protection Engineer | Safety Officer | Approved | High | None
| REQ-009 | Accessibility Compliance | Building design shall meet ADA requirements for ramps, doorways, and restroom facilities | Functional | Compliance | Critical | Architect | Building Inspector | Approved | Medium | None
| REQ-010 | Site Preparation | Site work shall include proper grading, drainage, and utility connections per civil plans | Functional | Functional | High | Civil Engineer | Site Superintendent | Approved | Low | None
| REQ-011 | Material Quality | All construction materials shall meet specified grades and certifications per project specifications | Non-Functional | Quality | Critical | Quality Inspector | Material Supplier | Approved | Medium | None
| REQ-012 | Construction Safety | All work shall comply with OSHA safety standards with zero accident target | Non-Functional | Safety | Critical | Safety Officer | Site Superintendent | Approved | High | None
| REQ-013 | Schedule Compliance | Construction activities shall meet milestone dates with substantial completion on schedule | Non-Functional | Performance | High | Project Manager | Construction Manager | Approved | Medium | None
| REQ-014 | Budget Control | Project costs shall remain within approved budget with change order management | Business | Financial | Critical | Project Manager | Construction Manager | Approved | Medium | None
| REQ-015 | Quality Control | Construction quality shall meet industry standards with comprehensive inspection program | Non-Functional | Quality | High | Quality Inspector | Site Superintendent | Approved | Low | None
| REQ-016 | Environmental Compliance | Construction activities shall comply with environmental regulations and permits | Compliance | Compliance | High | Environmental Consultant | Project Manager | Approved | Medium | None
| REQ-017 | Permit Acquisition | All required building permits and approvals shall be obtained before construction | Business | Regulatory | Critical | Project Manager | Building Inspector | Approved | Low | None
| REQ-018 | Warranty Requirements | Completed construction shall include comprehensive warranties for all systems and components | Business | Quality | Medium | Project Manager | Construction Manager | Approved | Low | None
| REQ-019 | Documentation | Project shall include as-built drawings, O&M manuals, and warranty documentation | Business | Documentation | Medium | Project Manager | Construction Manager | Approved | Low | None
| REQ-020 | Final Inspection | Building shall pass all required inspections and receive certificate of occupancy | Compliance | Compliance | Critical | Building Inspector | Project Manager | Approved | Medium | None

## Traceability Matrix
REQUIREMENTS TRACEABILITY MATRIX
Req ID | Requirement Name | Business Objective | Design Document | Development Task | Test Case ID | Test Status | Implementation Status | Verification Method | Verified By | Verification Date | Notes
BR-001 | AI Design Prototype Quality Compliance | Strategic Goal 1 | DS-001: Design Prototype Design | DEV-001 | TC-001, TC-002 | Passed | Implemented | Performance Testing | QA Team | 2025-09-15 | Met acceptance criteria
BR-002 | Data Processing Volume | Strategic Goal 2 | DS-002: System Architecture | DEV-002 | TC-003, TC-004 | Passed | Implemented | Load Testing | QA Team | 2025-09-20 | Exceeded requirements
BR-003 | Cost Reduction | Strategic Goal 3 | DS-003: Process Cost Efficiency | DEV-003 | TC-005 | Passed | Implemented | Cost Analysis | Finance Team | 2025-10-05 | 25% reduction achieved
BR-004 | Permit and Regulatory Approval | Strategic Goal 4 | DS-004: Compliance Framework | DEV-004 | TC-006, TC-007 | Passed | Implemented | Compliance Audit | Compliance Team | 2025-10-10 | All regulations satisfied
BR-005 | User Adoption | Strategic Goal 5 | DS-005: Change Management | DEV-005 | TC-008 | In Progress | Implemented | User Surveys | Change Team | 2025-11-15 | 85% adoption target on track
FR-001 | Data Ingestion | BR-002 | DS-006: Data Architecture | DEV-006 | TC-009, TC-010 | Passed | Implemented | Integration Testing | QA Team | 2025-08-10 | All sources connected
FR-002 | Design Inspection | BR-001 | DS-007: ML Construction Workflow | DEV-007 | TC-011, TC-012 | Passed | Implemented | System Testing | Construction Engineering | 2025-08-15 | Automated construction workflow verified
FR-003 | Project Forecast construction interface | BR-001, BR-002 | DS-008: construction interface Design | DEV-008 | TC-013, TC-014 | Passed | Implemented | construction interface Testing | QA Team | 2025-08-20 | construction interface performance validated
FR-004 | User Dashboard | BR-005 | DS-009: UI Design | DEV-009 | TC-015, TC-016 | Passed | Implemented | UI Testing | UX Team | 2025-09-01 | Dashboard functionality complete
FR-005 | Alert System | BR-004 | DS-010: Monitoring Design | DEV-010 | TC-017 | Passed | Implemented | System Testing | QA Team | 2025-09-05 | Alert triggers verified
TR-001 | Project Management Platform | BR-002, BR-003 | DS-011: Cloud Architecture | DEV-011 | TC-018, TC-019 | Passed | Implemented | Infrastructure Testing | DevOps Team | 2025-07-10 | AWS construction implementation complete
TR-002 | Data Security | BR-004 | DS-012: Security Design | DEV-012 | TC-020, TC-021 | Passed | Implemented | Security Testing | Security Team | 2025-07-15 | All security controls verified
TR-003 | Scalability | BR-002 | DS-013: Scaling Design | DEV-013 | TC-022 | Passed | Implemented | Load Testing | DevOps Team | 2025-07-20 | 2x load capacity confirmed
TR-004 | Availability | BR-001, BR-002 | DS-014: HA Design | DEV-014 | TC-023 | Passed | Implemented | Availability Testing | DevOps Team | 2025-08-01 | 99.9% uptime confirmed
TR-005 | Disaster Recovery | BR-004 | DS-015: DR Design | DEV-015 | TC-024 | Passed | Implemented | DR Testing | DevOps Team | 2025-08-05 | RTO/RPO targets met
UR-001 | User Authentication | BR-004 | DS-016: Auth Design | DEV-016 | TC-025, TC-026 | Passed | Implemented | Security Testing | Security Team | 2025-09-10 | SSO integration complete
UR-002 | Role-Based Access | BR-004, BR-005 | DS-017: RBAC Design | DEV-017 | TC-027, TC-028 | Passed | Implemented | Security Testing | Security Team | 2025-09-15 | All roles verified
UR-003 | Mobile Access | BR-005 | DS-018: Mobile Design | DEV-018 | TC-029, TC-030 | Passed | Implemented | Mobile Testing | QA Team | 2025-09-20 | Mobile functionality verified
UR-004 | Customizable Reports | BR-005 | DS-019: Reporting Design | DEV-019 | TC-031, TC-032 | In Progress | In Progress | UI Testing | UX Team | 2025-10-01 | Custom report builder in testing
UR-005 | Help System | BR-005 | DS-020: Help System Design | DEV-020 | TC-033 | In Progress | In Progress | UI Testing | UX Team | 2025-10-05 | Help content being finalized

## Coverage Analysis
REQUIREMENTS COVERAGE ANALYSIS
Category | Total Requirements | Designed | Developed | Tested | Implemented | Coverage %
Business Requirements | 5 | 5 | 5 | 5 | 5 | 100%
Functional Requirements | 5 | 5 | 5 | 5 | 5 | 100%
Technical Requirements | 5 | 5 | 5 | 5 | 5 | 100%
User Requirements | 5 | 5 | 5 | 3 | 3 | 60%
TOTAL | 20 | 20 | 20 | 18 | 18 | 90%

## Change Log
REQUIREMENTS CHANGE LOG
Change ID | Req ID | Change Description | Rationale | Requested By | Request Date | Impact Level | Approved By | Approval Date | Status | Notes
CR-001 | BR-001 | Increase quality compliance target from 85% to 90% | Competitive analysis | Executive Sponsor | 2025-03-15 | Medium | Change Board | 2025-03-22 | Approved | Updated in requirements
CR-002 | FR-003 | Add batch project forecast capability | Performance cost efficiency | Construction Engineering | 2025-04-10 | Medium | Change Board | 2025-04-17 | Approved | Added to sprint backlog
CR-003 | TR-002 | Add GDPR compliance requirements | European expansion | Legal | 2025-05-05 | High | Change Board | 2025-05-12 | Approved | Security team engaged
CR-004 | UR-004 | Add export to PDF capability | User feedback | Business Users | 2025-06-20 | Low | Change Board | 2025-06-27 | Approved | Added to sprint backlog
CR-005 | FR-005 | Add SMS notification option | User feedback | Product Owner | 2025-07-15 | Low | Change Board | 2025-07-22 | Rejected | Out of scope for v1