## Open Action Items
INFORMATION SECURITY AND CYBER DEFENSE - OPEN ACTION ITEM LOG
Project: Cybersecurity Implementation
Date: July 31, 2025
PMI 2025 Standards Compliant
ACTION ITEM TRACKING
Action_ID | Action_Description | Priority | Status | Owner | Due_Date | Completion_Date | Progress_% | Dependencies | Notes
AI001 | Implement continuous threat intelligence feed updates | High | In Progress | CISO | 2025-08-30 |  | 25 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI002 | Deploy comprehensive security awareness training program | High | In Progress | Security Architects | 2025-09-04 |  | 32 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI003 | Conduct quarterly incident response tabletop exercises | High | In Progress | Security Engineers | 2025-09-09 |  | 39 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI004 | Roll out multi-factor authentication across all systems | High | In Progress | SOC Analysts | 2025-09-14 |  | 46 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI005 | Complete security tool integration and automation | Medium | In Progress | Compliance Officers | 2025-09-19 |  | 53 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI006 | Implement behavioral analytics for insider threat detection | Medium | In Progress | IT Teams | 2025-09-24 |  | 60 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI007 | Map compliance requirements to business process controls | Medium | Not Started | CISO | 2025-09-29 |  | 67 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI008 | Establish business-focused security metrics dashboard | Medium | Not Started | Security Architects | 2025-10-04 |  | 74 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI009 | Complete vendor security assessment and risk evaluation | Low | Not Started | Security Engineers | 2025-10-09 |  | 81 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success
AI010 | Schedule monthly executive security briefings | Low | Completed | SOC Analysts | 2025-10-14 | 2025-07-31 | 100 | Dependent on Cybersecurity Implementation milestone completion | Critical action for Information Security and Cyber Defense success