## Engagement Overview
STAKEHOLDER ENGAGEMENT PLAN
GOVERNMENT Stakeholder Engagement Plan Project
Generated: July 16, 2025
PROJECT INFORMATION
Project Name: | Enterprise AI/ML Implementation
Stakeholder Manager: | Jennifer Martinez, PMP
Total Stakeholders: | 45 identified stakeholders
Stakeholder Categories: | 8 primary stakeholder groups
Engagement Duration: | 18 months (Jan 2025 - Jun 2026)
Engagement Budget: | $95,000 (3.3% of project budget)
Engagement Frequency: | Daily to Quarterly based on stakeholder
STAKEHOLDER ENGAGEMENT OBJECTIVES
1. Maintain active support from key stakeholders throughout project lifecycle
2. Ensure timely stakeholder input and decision-making for project success
3. Build stakeholder confidence and trust in AI/ML transformation initiative
4. Minimize stakeholder resistance and maximize adoption readiness
5. Establish sustainable stakeholder relationships for future initiatives
6. Create transparent communication channels for feedback and concerns
ENGAGEMENT PRINCIPLES
• Inclusive: Engage all affected stakeholders with appropriate level of involvement
• Transparent: Provide honest, timely, and accurate information about project status
• Respectful: Value stakeholder time, expertise, and perspectives in all interactions
• Responsive: Address stakeholder concerns and feedback promptly and effectively
• Consistent: Maintain regular engagement patterns and reliable communication
• Value-Focused: Emphasize benefits and value creation for each stakeholder group

## Stakeholder Analysis
STAKEHOLDER ANALYSIS MATRIX
Stakeholder Name | Role/Title | Organization | Interest Level | Influence Level | Attitude | Impact on Project | Project Impact on Them | Engagement Strategy | Key Concerns | Success Criteria | Preferred Communication | Frequency | Owner
John Smith | CEO | Executive | High | High | Supportive | High | High | Manage Closely | ROI and timeline | Business success | Executive briefing | Monthly | Sarah Johnson
Maria Garcia | CTO | Technology | High | High | Champion | High | High | Manage Closely | Technical feasibility | Innovation leadership | Technical review | Bi-weekly | Alex Rodriguez
David Chen | CFO | Finance | Medium | High | Neutral | High | Medium | Keep Satisfied | Budget control | Cost management | Financial report | Monthly | Sarah Johnson
Lisa Wang | CHRO | HR | Medium | Medium | Supportive | Medium | High | Keep Informed | Employee impact | Change success | HR meeting | Bi-weekly | Mark Thompson
Robert Taylor | Business Director | Operations | High | Medium | Supportive | Medium | High | Keep Informed | Business continuity | Operational efficiency | Business review | Weekly | Lisa Wang
Jennifer Liu | Data Director | Analytics | High | Medium | Champion | High | High | Keep Informed | Data quality | Analytics capability | Data meeting | Weekly | Thomas Lee
Michael Johnson | IT Director | Technology | Medium | Medium | Neutral | Medium | Medium | Keep Informed | Infrastructure impact | System stability | IT review | Bi-weekly | Chris Wilson
Sarah Brown | Compliance Officer | Legal | Medium | Medium | Cautious | Medium | Medium | Keep Informed | Regulatory compliance | Risk mitigation | Compliance review | Monthly | Sarah Johnson
Kevin Zhang | Tech Lead | Technology | High | Low | Champion | Low | High | Monitor | Technical execution | Career development | Team meeting | Weekly | Alex Rodriguez
Amanda Davis | End User Rep | Business | High | Low | Cautious | Low | High | Monitor | Usability concerns | Job security | User session | Bi-weekly | Mark Thompson
Dr. Susan Clark | Board Member | Governance | Medium | High | Neutral | High | Low | Keep Satisfied | Strategic alignment | Governance oversight | Board report | Quarterly | CEO
Tom Wilson | Union Rep | Labor | Medium | Medium | Resistant | Medium | High | Keep Informed | Job displacement | Worker protection | Union meeting | Monthly | CHRO
Rachel Green | Customer Rep | External | Low | Low | Neutral | Low | Medium | Monitor | Service quality | Customer satisfaction | Customer update | Quarterly | Customer Success
James Miller | Vendor Partner | External | Medium | Low | Supportive | Low | Medium | Monitor | Partnership impact | Business opportunity | Vendor meeting | Monthly | Procurement
Patricia Lewis | Regulator | External | Low | High | Neutral | High | Low | Keep Satisfied | Compliance adherence | Regulatory oversight | Regulatory report | Quarterly | Compliance Officer

## Engagement Activities
STAKEHOLDER ENGAGEMENT ACTIVITIES
Activity ID | Activity Name | Target Stakeholders | Objective | Method | Frequency | Start Date | End Date | Owner | Status | Budget | Notes
SE-001 | Executive Steering Committee | C-Suite | Strategic oversight | Monthly meeting | Monthly | 2025-01-01 | 2026-06-30 | Sarah Johnson | Active | $12,000 | Strategic decisions
SE-002 | Project Kickoff Event | All Stakeholders | Project launch | Town hall | One-time | 2025-01-15 | 2025-01-15 | Communications | Completed | $8,000 | Project introduction
SE-003 | Technical Advisory Board | Technical Leaders | Technical guidance | Bi-weekly meeting | Bi-weekly | 2025-02-01 | 2026-04-30 | Alex Rodriguez | Active | $15,000 | Technical decisions
SE-004 | Business User Sessions | End Users | Requirements gathering | Workshop | Monthly | 2025-02-15 | 2025-06-30 | Business Analyst | Active | $10,000 | User input
SE-005 | Change Champion Network | Champions | Change advocacy | Monthly meeting | Monthly | 2025-03-01 | 2026-06-30 | Mark Thompson | Active | $8,000 | Change support
SE-006 | Vendor Partner Reviews | Key Vendors | Partnership alignment | Quarterly review | Quarterly | 2025-03-15 | 2026-06-30 | Procurement | Active | $5,000 | Vendor coordination
SE-007 | Regulatory Briefings | Compliance/Legal | Compliance assurance | Quarterly briefing | Quarterly | 2025-04-01 | 2026-06-30 | Compliance Officer | Active | $6,000 | Regulatory updates
SE-008 | Customer Advisory Panel | Key Customers | Customer perspective | Quarterly session | Quarterly | 2025-04-15 | 2026-03-31 | Customer Success | Planned | $7,000 | Customer feedback
SE-009 | Union Consultation | Labor Representatives | Worker concerns | Monthly meeting | Monthly | 2025-05-01 | 2026-06-30 | HR Manager | Planned | $4,000 | Labor relations
SE-010 | Board Reporting | Board of Directors | Governance reporting | Quarterly report | Quarterly | 2025-01-01 | 2026-06-30 | CEO | Active | $8,000 | Board oversight
SE-011 | All-Hands Updates | All Employees | Company-wide updates | Quarterly meeting | Quarterly | 2025-01-01 | 2026-06-30 | CEO | Active | $12,000 | Company communication
SE-012 | Feedback Surveys | All Stakeholders | Sentiment tracking | Survey | Quarterly | 2025-03-01 | 2026-06-30 | Communications | Active | $5,000 | Feedback collection

## Engagement Metrics
STAKEHOLDER ENGAGEMENT METRICS
Metric Category | Metric Name | Target | Current | Trend | Measurement Method | Frequency | Owner | Status | Action Required
Participation | Meeting Attendance | 90% | 88% | Stable | Meeting records | Weekly | Meeting Owners | Yellow | Improve scheduling
Satisfaction | Stakeholder Satisfaction | 4.0/5 | 4.2/5 | Improving | Quarterly survey | Quarterly | Engagement Manager | Green | None
Communication | Response Rate | 80% | 75% | Declining | Communication tracking | Monthly | Communications | Yellow | Follow-up process
Engagement | Active Participation | 70% | 72% | Improving | Participation tracking | Monthly | Engagement Manager | Green | None
Support | Stakeholder Support Level | 4.0/5 | 3.8/5 | Stable | Support assessment | Quarterly | Project Manager | Yellow | Address concerns
Feedback | Feedback Quality | 4.0/5 | 4.1/5 | Improving | Feedback analysis | Monthly | Business Analyst | Green | None
Influence | Influencer Engagement | 95% | 93% | Stable | Influencer tracking | Monthly | Engagement Manager | Green | None
Resistance | Resistance Level | < 20% | 18% | Improving | Resistance assessment | Monthly | Change Manager | Green | None
Escalation | Issue Escalation Rate | < 10% | 8% | Stable | Issue tracking | Weekly | Project Manager | Green | None
Commitment | Commitment Level | 4.0/5 | 3.9/5 | Stable | Commitment survey | Quarterly | Engagement Manager | Yellow | Reinforce value