## Open Action Items
BUSINESS OPERATIONS AND PROCESS IMPROVEMENT - OPEN ACTION ITEM LOG
Project: Operations Improvement
Date: July 31, 2025
PMI 2025 Standards Compliant
ACTION ITEM TRACKING
Action_ID | Action_Description | Priority | Status | Owner | Due_Date | Completion_Date | Progress_% | Dependencies | Notes
AI001 | Complete process standardization with stakeholder input and validation | High | In Progress | Operations Managers | 2025-08-30 |  | 25 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI002 | Implement continuous change management communication strategy | High | In Progress | Process Analysts | 2025-09-04 |  | 32 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI003 | Deploy real-time performance measurement and analytics systems | High | In Progress | Quality Managers | 2025-09-09 |  | 39 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI004 | Execute technology integration with comprehensive testing procedures | High | In Progress | Training Specialists | 2025-09-14 |  | 46 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI005 | Develop role-specific staff training programs and certification | Medium | In Progress | IT Support | 2025-09-19 |  | 53 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI006 | Implement quality management system calibration and validation | Medium | In Progress | End Users | 2025-09-24 |  | 60 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI007 | Establish customer feedback collection and integration processes | Medium | Not Started | Operations Managers | 2025-09-29 |  | 67 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI008 | Ensure executive sponsorship visibility through regular reporting | Medium | Not Started | Process Analysts | 2025-10-04 |  | 74 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI009 | Create comprehensive process documentation and maintenance procedures | Low | Not Started | Quality Managers | 2025-10-09 |  | 81 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success
AI010 | Build continuous improvement culture through recognition and support | Low | Completed | Training Specialists | 2025-10-14 | 2025-07-31 | 100 | Dependent on Operations Improvement milestone completion | Critical action for Business Operations and Process Improvement success